## IBR
“Systems Engineering for Mission Success”
|  | Integrated Baseline Review | [6 empty] | Name of the program being reviewed / date
Program Risk Assessment Checklist (28 September 2009)
OVERVIEW: Although the checklist can be printed and completed as a "hard copy", it is designed to be completed electronically as an Excel spreadsheet. When viewed electronically, the small number buttons in the upper left corner of the screen are used to select the level of indenture for the questions in the checklist. A left mouse click on a number button will expand or collapse the entire checklist to the desired level. A left click on the "+" or "-" symbols in the left margin of the spreadsheet will expand or collapse the level of indenture for that section. The buttons in Row 11 run specific macros. The buttons in Column A allow a user to designate and sort specific questions as "Special Interest" (i.e., High Priority, Flagged, Question). The colored buttons in Row 11, Column C allow the user to sort questions by Technical Discipline, to provide a Level 1 roll-up of the risk characters assigned, or to hide specific information. For example selecting the "Logistics" button results in the display of all Level 1 Logistics-related questions, and assigned information. All other questions will be hidden. COMPLETING THE CHECKLIST: 1. In the upper right corner of the checklist, enter the name of the program being reviewed, the date(s) of the review, along with the name, code and technical specialty of the person(s) completing the checklist. 2. A "Risk Character" (i.e., R / Y / G / U / NA) should be assigned for each question by direct entry or left clicking in each box to activate the "drop down" menu. The assigned Risk Characters will automatically total and display in the Level 1 (and Level 2, as applicable) row(s). Selection of a summary tab (Excel "Sheet") at the bottom of the checklist will provide a summary of all questions assigned a particular risk character (e.g., selecting the RED tab will display all questions assigned a RED risk character). 3. Any question requiring further attention (Special Interest) should be similarly marked in Column A as "High Priority", "Flagged", or "Question" to facilitate follow-up. 4. Narrative, amplifying, and / or mitigation information should be entered in the "Comments / Mitigation" box (Column J) at the right of each question.
Name / Code / Technical Specialty of reviewer
SAVING THE CHECKLIST: Save the completed checklist in a new file with a unique name such as "UAV IBR 28Sept09ajo".
|  |  | Risk Character | [6 empty] | High Priority
[8 empty] | R = Red, Y = Yellow, G = Green, U = Unknown / Unavailable, NA = Not Applicable |  | Flagged
Special Interest | Technical Discipline | Legend: | R | Y | G | U | NA | Item | Comments / Mitigation | Question
| programmatic | 1. Timing / Entry Criteria | 0 | 0 | 0 | 0 | 0 | 1
| programmatic | a. Has the contractor / government activity implemented / planned the baseline? | [5 empty] | 1.a
| programmatic | b. Is the Integrated Baseline Review (IBR) being planned to be conducted within six months of when the effort was authorized to proceed? | [5 empty] | 1.b
| training, T&E, logistics, risk, software, RAM, hardware, EVM, programmatic | 2. Planning | 0 | 0 | 0 | 0 | 0 | 2
| training, logistics, software, RAM, hardware, EVM, programmatic | a. Has team leadership / team membership been assigned? Does the team have representation from all necessary technical areas including software development? | [5 empty] | 2.a
| hardware, software, EVM, programmatic | b. Has a Plan of Action and Milestones (POA&M) been developed for the review execution? | [5 empty] | 2.b
| hardware, software, risk, programmatic | c. Has the Risk Management Plan been used to establish focus areas for the review? | [5 empty] | 2.c
| EVM, programmatic | d. Was a team handbook developed? | [5 empty] | 2.d
| EVM, programmatic | e. Has training been provided in accordance with the Technical Review Handbook? | [5 empty] | 2.e
| hardware, programmatic | f. Was a location chosen for the on-site portion of the review that allows the most access to data? (preferable on-site to where work is being performed) | [5 empty] | 2.f
| hardware, software, logistics, EVM, programmatic | g. Is the team familiar with the work scope and management processes? | [5 empty] | 2.g
| programmatic | (1) Is the team familiar with the project scope of work? Have team members been provided a copy of the statement of work or statement of objectives? | [5 empty] | 2.g(1)
| EVM, programmatic | (2) Has a Control Account Manager (CAM) been assigned? How much experience and training does the CAM have? What is the CAM's primary program function? Does the CAM plan the cost accounts? | [5 empty] | 2.g(2)
| EVM, programmatic | (3) How does the CAM get authorization to start work? | [5 empty] | 2.g(3)
| EVM, programmatic | (4) How much material is the CAM responsible for? | [5 empty] | 2.g(4)
| EVM, programmatic | (5) Are all of the accounts discrete? | [5 empty] | 2.g(5)
| EVM, hardware, risk, software, programmatic | h. Was there an independent cost estimate, and was it used to identify risk / focus areas? | [5 empty] | 2.h
| EVM, programmatic | i. Have data been requested to facilitate team training and preparation? | [5 empty] | 2.i
| EVM, T&E, programmatic | j. Has the full Test and Evaluation (T&E) scope been accounted for in the baseline plan? | [5 empty] | 2.j
| hardware, RAM, logistics, HSI, software, T&E, technology, risk, programmatic | 3. Technical | 0 | 0 | 0 | 0 | 0 | 3
| hardware, RAM, logistics, HSI, software, T&E, technology, risk, programmatic | a. Has all scope been accounted for in the baseline plan? | [5 empty] | 3.a
| hardware, RAM, logistics, HSI, software, T&E, technology, risk, programmatic | b. What effect will the availability of technology, software development capability, human systems design options, design maturity, rework, etc have on the plan? Is the technical scope of the work fully identified including the impact of available technology? | [5 empty] | 3.b
| hardware, software, risk, programmatic | c. What are the major risks or opportunities included / not included in the plan? Are the technical risks identified for the program identified in the Risk Management Plan? | [5 empty] | 3.c
| risk, T&E, programmatic | d. Is there an understanding of the technical risks associated with the T&E plan as it stands now? | [5 empty] | 3.d
| software, programmatic | e. Has the maturity of the software organization been assessed? Is there a process improvement plan in place? | [5 empty] | 3.e
| HSI, T&E, hardware, risk, software, programmatic, | 4. Schedule | 0 | 0 | 0 | 0 | 0 | 4
| hardware, logisitcs, T&E, software, HSI, programmatic | a. Does the program have an updated network schedule with sufficient detail to support development? At what level are the tasks linked? Is the schedule horizontally / vertically integrated? Does the plan contain all activities and functions? | [5 empty] | 4.a
| hardware, logisitcs, T&E, software, HSI, programmatic | b. Is the schedule built upon “bottom-up” task planning? | [5 empty] | 4.b
| hardware, logisitcs, T&E, software, HSI, programmatic | c. Is the schedule reflective of available resources? | [5 empty] | 4.c
| hardware, logisitcs, T&E, software, HSI, programmatic | d. Does the program schedule have an identified critical path and is that critical path consistent with overall technical risk? | [5 empty] | 4.d
| hardware, logisitcs, T&E, software, HSI, programmatic | e. What is the current status versus critical path? | [5 empty] | 4.e
| hardware, logisitcs, T&E, software, HSI, programmatic | f. Will the program be able to meet contractual delivery / performance dates? | [5 empty] | 4.f
| hardware, logisitcs, T&E, software, HSI, programmatic | g. How have subcontracted efforts been integrated into the schedule? Which functional areas or activities have been subcontracted? | [5 empty] | 4.g
| programmatic, T&E | h. Is the T&E schedule executable with respect to timeframe and required resources (manpower, ranges, facilities)? | [5 empty] | 4.h
| programmatic, T&E | i. Is there sufficient room in the T&E plan for unexpected down time and re-test? | [5 empty] | 4.i
| T&E, risk, software, logistics, EVM, programmatic | 5. Cost | 0 | 0 | 0 | 0 | 0 | 5
| EVM, programmatic | a. How does the CAM know who is charging to what accounts? How often is the information reported? How often is it checked? | [5 empty] | 5.a
| EVM, programmatic | b. How does the CAM plan, track, and take credit for material buys? | [5 empty] | 5.b
| EVM, programmatic | c. Will the contract / effort be able to execute to its objectives? | [5 empty] | 5.c
| EVM, programmatic | d. Does the time phasing of the Performance Management Baseline (PMB) track to the program office budget, funding, and schedule? | [5 empty] | 5.d
| logistics, hardware, risk, software, EVM, programmatic | e. As part of the IBR is the program team able to update the Estimate at Completion (EAC) to include identified risk items? | [5 empty] | 5.e
| T&E, EVM, logistics, programmatic | f. Is there a method for tracing T&E costs to specific capabilities? | [5 empty] | 5.f
| hardware, software, T&E, logistics, PQM, programmatic | 6. Resources | 0 | 0 | 0 | 0 | 0 | 6
| hardware, software, T&E, logistics, PQM, programmatic | a. Does the project have the required resources available to perform the effort? Are they available when needed? | [5 empty] | 6.a
| hardware, software, T&E, logistics, PQM, programmatic | b. Do the resources identified possess the required experience to execute the effort? How do these resources breakdown by activities and function and what is the plan to deal with any shortfall? | [5 empty] | 6.b
| hardware, software, T&E, logistics, PQM, programmatic | c. Are the required facilities available for the project execution? Are the facilities shared and are agreements in place to support this program? | [5 empty] | 6.c
| hardware, logistics, T&E, software, EVM, programmatic | 7. Management Processes | 0 | 0 | 0 | 0 | 0 | 7
| hardware, logistics, T&E, software, EVM, programmatic | a. Have the management processes been implemented to provide effective integrated cost, schedule, and technical planning, execution, and baseline control? (documentation versus implementation) | [5 empty] | 7.a
| hardware, logistics, software, EVM, programmatic | (1) How often is the earned value statused? What earned value data are looked at, and how often? Are dollars or hours managed? | [5 empty] | 7.a(1)
| EVM, programmatic | (2) What tool is used to plan the work packages? What tool is used to track / manage the work packages? What tool is used to status the work packages? | [5 empty] | 7.a(2)
| EVM, programmatic | (3) How much time is spent each week statusing the cost accounts? What is the peak staffing level that works control accounts? | [5 empty] | 7.a(3)
| EVM, programmatic | (4) How often is the EAC calculated? What triggers a new EAC calculation? | [5 empty] | 7.a(4)
| EVM, programmatic | (5) If a forecast shows a slip to a critical path item, how is it statused? | [5 empty] | 7.a(5)
| EVM, programmatic | (6) How and when are credits for Contract Data Requirements List (CDRL) deliveries taken? How are reworks accounted for? | [5 empty] | 7.a(6)
| EVM, programmatic | (7) What is the area of greatest concern on this effort? | [5 empty] | 7.a(7)
| EVM, programmatic | (8) When is an earned value variance report initiated? | [5 empty] | 7.a(8)
| EVM, programmatic | (9) Is there any negative lag in the schedule? Why? | [5 empty] | 7.a(9)
| EVM, programmatic | (10) Where are travel dollars and hours books kept? | [5 empty] | 7.a(10)
| EVM, programmatic | (11) What is the process for requesting the release of Management Reserve (MR)? | [5 empty] | 7.a(11)
| EVM, programmatic | b. Have significant management process issues been identified, or a Corrective Action Request been issued? | [5 empty] | 7.b
| EVM, programmatic | c. Has Integrated Project Management / Earned Value Management (EVM) been integrated into the normal course of business for the execution of the effort? (team meetings, Program Management Reviews (PMRs), etc.) | [5 empty] | 7.c
| hardware, logistics, T&E, software, EVM, programmatic | d. What is the contractor's concept for tracking earned value for all planned efforts and activities including Software and T&E (metrics, success criteria)? | [5 empty] | 7.d
| risk, EVM, programmatic | 8. Completion / Exit Criteria | 0 | 0 | 0 | 0 | 0 | 8
| EVM, programmatic | a. Have concerns been identified, and closure plans developed? | [5 empty] | 8.a
| risk, EVM, programmatic | b. Have action items been included in the risk management plan? | [5 empty] | 8.b
| risk, EVM, programmatic | c. Does the PMB reflect the scope of work that was contracted? Is the PMB achievable? | [5 empty] | 8.c
High Priority
Flagged
Question
CAUTION: Entries, changes or deletions to risk characters or comments should only be made on the expanded checklist page; NOT on any of the summary pages. Any entries entered directly on the summary pages will disable linkage within the checklist.
Hide TD
Unhide TD
Unhide NA
Hide NA
Show All
HSI
Interoperability
Logistics
Training
PQM
Programmatic
Risk
Software
T&E
Technology
Level 1
EVM
Hardware
RAM

## Red
“Systems Engineering for Mission Success”
|  | Integrated Baseline Review | [6 empty] | Name of the program being reviewed / date
|  | Program Risk Assessment Checklist | [6 empty] | 0
Name / Code / Technical Specialty of reviewer
0
Risk Character
R = Red, Y = Yellow, G = Green, U = Unknown / Unavailable, NA = Not Applicable
Special Interest | Technical Discipline | Legend: | R | Y | G | U | NA | Item | Comments / Mitigation

## Yellow
“Systems Engineering for Mission Success”
|  | Integrated Baseline Review | [6 empty] | Name of the program being reviewed / date
|  | Program Risk Assessment Checklist | [6 empty] | 0
Name / Code / Technical Specialty of reviewer
0
Risk Character
R = Red, Y = Yellow, G = Green, U = Unknown / Unavailable, NA = Not Applicable
Special Interest | Technical Discipline | Legend: | R | Y | G | U | NA | Item | Comments / Mitigation

## Unknown
“Systems Engineering for Mission Success”
|  | Integrated Baseline Review | [6 empty] | Name of the program being reviewed / date
|  | Program Risk Assessment Checklist | [6 empty] | 0
Name / Code / Technical Specialty of reviewer
0
Risk Character
R = Red, Y = Yellow, G = Green, U = Unknown / Unavailable, NA = Not Applicable
Special Interest | Technical Discipline | Legend: | R | Y | G | U | NA | Item | Comments / Mitigation

## NA
“Systems Engineering for Mission Success”
|  | Integrated Baseline Review | [6 empty] | Name of the program being reviewed / date
|  | Program Risk Assessment Checklist | [6 empty] | 0
Name / Code / Technical Specialty of reviewer
0
Risk Character
R = Red, Y = Yellow, G = Green, U = Unknown / Unavailable, NA = Not Applicable
Special Interest | Technical Discipline | Legend: | R | Y | G | U | NA | Item | Comments / Mitigation

## Level 1
“Systems Engineering for Mission Success”
|  | Integrated Baseline Review | [6 empty] | Name of the program being reviewed / date
|  | Program Risk Assessment Checklist | [6 empty] | 0
Name / Code / Technical Specialty of reviewer
0
Risk Character
R = Red, Y = Yellow, G = Green, U = Unknown / Unavailable, NA = Not Applicable
Special Interest | Technical Discipline | Legend: | R | Y | G | U | NA | Item | Comments/Mitigation
0 | programmatic | 1. Timing / Entry Criteria | 0 | 0 | 0 | 0 | 0 | 1 | 0
0 | training, T&E, logistics, risk, software, RAM, hardware, EVM, programmatic | 2. Planning | 0 | 0 | 0 | 0 | 0 | 2 | 0
0 | hardware, RAM, logistics, HSI, software, T&E, technology, risk, programmatic | 3. Technical | 0 | 0 | 0 | 0 | 0 | 3 | 0
0 | HSI, T&E, hardware, risk, software, programmatic, | 4. Schedule | 0 | 0 | 0 | 0 | 0 | 4 | 0
0 | T&E, risk, software, logistics, EVM, programmatic | 5. Cost | 0 | 0 | 0 | 0 | 0 | 5 | 0
0 | hardware, software, T&E, logistics, PQM, programmatic | 6. Resources | 0 | 0 | 0 | 0 | 0 | 6 | 0
0 | hardware, logistics, T&E, software, EVM, programmatic | 7. Management Processes | 0 | 0 | 0 | 0 | 0 | 7 | 0
0 | risk, EVM, programmatic | 8. Completion / Exit Criteria | 0 | 0 | 0 | 0 | 0 | 8 | 0
|  | Total | 0 | 0 | 0 | 0 | 0
Return to IBR