## ISR
“Systems Engineering for Mission Success”
|  | In-Service Review | [7 empty] | Name of the program being reviewed / date
Program Risk Assessment Checklist (27 January 2010)
OVERVIEW: Although the checklist can be printed and completed as a "hard copy", it is designed to be completed electronically as an Excel spreadsheet. When viewed electronically, the small number buttons in the upper left corner of the screen are used to select the level of indenture for the questions in the checklist. A left mouse click on a number button will expand or collapse the entire checklist to the desired level. A left click on the "+" symbol in the left margin of the spreadsheet will expand the level of indenture for that section. A left click on the "-" symbol in the left margin of the spreadsheet will collapse the level of indenture for that section. The buttons in Row 11 run specific macros. The buttons in Column A allow a user to designate and sort specific questions as "Special Interest" (i.e., High Priority, Flagged, Question). The colored buttons in Row 11, Column C allow the user to sort questions by Technical Discipline, to provide a Level 1 roll-up of the risk characters assigned, or to hide specific information. For example selecting the "Logistics" button results in the display of all Level 1 Logistics-related questions and assigned information. All other questions will be hidden. COMPLETING THE CHECKLIST: 1. In the upper right corner of the checklist, enter the name of the program being reviewed, the date(s) of the review, along with the name, code and technical specialty of the person(s) completing the checklist. 2. A "Risk Character" (i.e., R / Y / G / U / NA) should be assigned for each question by direct entry or left clicking in each box to activate the "drop down" menu. To delete a "Risk Character" from a box, click in the box and press the "delete" button on hte keyboard, or right click on hte cell and select "clear contents". The assigned Risk Characters will automatically total and display in the Level 1 (and Level 2, as applicable) row(s). Selection of a summary tab (Excel "Sheet") at the bottom of the checklist will provide a summary of all questions assigned a particular risk character (e.g., selecting the RED tab will display all questions assigned a RED risk character). 3. Any question requiring further attention (Special Interest) should be similarly marked in Column A as "High Priority", "Flagged", or "Question" to facilitate follow-up. 4. Narrative, amplifying, and / or mitigation information should be entered in the "Comments Mitigation" box (Column J) at the right of each question.
Name / Code / Technical Specialty of reviewer
If any of the ISR questions require written vice R / Y / G / U / NA responses, check or type NA in the appropriate column of the checklist.
SAVING THE CHECKLIST: Save the completed checklist in a new file with a unique name such as "UAV ISR 17May07ajo".
|  |  | Risk Character | [7 empty] | High Priority
[8 empty] | R = Red, Y = Yellow, G = Green, U = Unknown / Unavailable, NA = Not Applicable |  |  | Flagged
Special Interest | Technical Discipline | Legend: | R | Y | G | U | NA | Item | Comments / Mitigations |  | Question
| training, HSI, software, T&E, logistics, PQM, technology, risk, programmatic, interoperability | 1. Program Overview | 0 | 0 | 0 | 0 | 6 | 1
| logistics, PQM, programmatic | a. Production Overview Fielded Status | 0 | 0 | 0 | 0 | 3 | 1.a
| logistics, PQM, programmatic | (1) What is the number of systems supporting the operational requirements including systems in the pipeline for maintenance and modifications? (Indicate answer in "Comments" block.) | NA |  |  |  |  | 1.a(1)
| logistics, PQM, programmatic | (2) What is the number of permanent sites including facilities required to support pipeline systems and spares? (Indicate answer in "Comments" block.) | NA |  |  |  |  | 1.a(2)
| logistics, PQM, programmatic | (3) What is the number of unclassified deployed sites including facilities required to support pipeline systems and spares? (Indicate answer in "Comments" block.) | NA |  |  |  |  | 1.a(3)
| PQM, HSI, logistics, programmatic | b. Modification Program Status | 0 | 0 | 0 | 0 | 0 | 1.b
| logistics, PQM, programmatic | (1) Is there a process in place for system modification management, and is it being applied to properly address in-service support of the program? | [5 empty] | 1.b(1)
| PQM, programmatic | (2) Are modifications being managed and traced from higher level (parent) requirements to lower level (offspring) requirements? | [5 empty] | 1.b(2)
| HSI, PQM, logistics, programmatic | (3) Is adequate modification traceability in place to ensure flow across the Product Support Plan (PSP) elements? | [5 empty] | 1.b(3)
| risk, HSI, logistics, RAM, programmatic | c. Engineering and Logistics Overview | 0 | 0 | 0 | 0 | 0 | 1.c
| logistics, RAM, programmatic | (1) Is there adequate documentation to support the in-service requirements identified in the Logistics Requirements and Funding Summary (LRFS)? | [5 empty] | 1.c(1)
| HSI, RAM, logistics, programmatic | (2) Do the funding requirements in the LRFS coincide with the support requirements in the PSP and other planning documents? | [5 empty] | 1.c(2)
| logistics, risk, programmatic | (3) Are the impacts of funding shortfalls understood, and are there plans in place to mitigate the risk? | [5 empty] | 1.c(3)
| logistics, HSI, programmatic | (4) Has the LRFS been staffed and approved? | [5 empty] | 1.c(4)
| training, logistics, HSI, T&E, software, technology, risk, programmatic, interoperability | d. Program Staffing | 0 | 0 | 0 | 0 | 0 | 1.d
| training, risk, software, HSI, logistics, T&E, technology, programmatic | (1) Is there a complete organization structure shown, and is the organization consistent with the technical challenges / risks of the program? | [5 empty] | 1.d(1)
| risk, programmatic, interoperability | (2) Are key Government / contractor interfaces identified, and are they consistent with the program risks? | [5 empty] | 1.d(2)
| risk, programmatic | (3) Are resources being adequately applied as indicated by the planned verses actual resource curve? | [5 empty] | 1.d(3)
| software, T&E, HSI, training, logistics, risk, programmatic | e. Budget Overview | 0 | 0 | 0 | 0 | 3 | 1.e
| logistics, HSI, software, T&E, training, programmatic | (1) What are the current fiscal year funding requirements and controls, and what is the execution status of the current funding? (Indicate answer in "Comments" block.) | NA |  |  |  |  | 1.e(1)
| training, logistics, HSI, software, T&E, programmatic | (2) What are the prioritized unfunded requirements? (Indicate answer in "Comments" block.) | NA |  |  |  |  | 1.e(2)
| HSI, risk, logistics, programmatic | (3) Do the funding requirements reflect all of the in-service requirements identified by the program policies and metrics? | [5 empty] | 1.e(3)
| HSI, training, software, T&E, programmatic | (4) What are the identified impacts for the prioritized unfunded requirements? (Indicate answer in "Comments" block.) | NA |  |  |  |  | 1.e(4)
| training, risk, HSI, software, logistics, T&E, programmatic | (5) Are the impacts of funding shortfalls understood and plans in place to mitigate the risk? | [5 empty] | 1.e(5)
| training, T&E, risk, software, logistics, HSI, programmatic | 2. Program Risk Assessment | 0 | 0 | 0 | 0 | 3 | 2
| risk, programmatic | a. What is the operational system hazard risk status? (Indicate answer in "Comments" block.) | NA |  |  |  |  | 2.a
| risk, software, training, T&E, logistics, HSI, programmatic | b. What are the risk items and mitigation options? (Indicate answer in "Comments" block.) | NA |  |  |  |  | 2.b
| risk, logistics, training, T&E, software, HSI, programmatic | c. What are the cost and schedule impacts of risk and / or mitigation options? (Indicate answer in "Comments" block.) | NA |  |  |  |  | 2.c
| training, logistics, hardware, T&E, software, HSI, technology, risk, programmatic, interoperability | 3. In-Service Management Metrics | 0 | 0 | 0 | 0 | 0 | 3
| training, logistics, hardware, T&E, software, HSI, technology, risk, programmatic | a. Safety Program Status | 0 | 0 | 0 | 0 | 0 | 3.a
| training, hardware, HSI, risk, logistics, software, T&E, programmatic | (1) Is the defined system safety management process identifying all appropriate safety issues? | [5 empty] | 3.a(1)
| training, hardware, HSI, risk, logistics, software, T&E, programmatic | (2) Is the defined system safety management process prioritizing all appropriate safety issues? | [5 empty] | 3.a(2)
| training, hardware, logistics, T&E, software, HSI, technology, risk, programmatic | (3) Is the defined system safety management process identifying the appropriate technical resources to staff all appropriate issues? | [5 empty] | 3.a(3)
| training, hardware, HSI, risk, logistics, software, T&E, programmatic | (4) Are mitigation approaches in place for all “yellow” and “red” risks, and are risk mitigations resourced? | [5 empty] | 3.a(4)
| training, hardware, logistics, T&E, software, HSI, technology, risk, programmatic | (5) Is the defined system safety management process supporting the technical resources in accomplishing resolution to the safety action items? | [5 empty] | 3.a(5)
| training, hardware, logistics, HSI, T&E, software, technology, risk, programmatic | b. Aging Aircraft Status | 0 | 0 | 0 | 0 | 0 | 3.b
| training, hardware, risk, software, T&E, HSI, logistics, programmatic | (1) Is the defined aging aircraft management process identifying all appropriate issues? | [5 empty] | 3.b(1)
| training, hardware, software, T&E, HSI, logistics, programmatic | (2) Is the defined aging aircraft management process prioritizing all appropriate issues? | [5 empty] | 3.b(2)
| training, hardware, logistics, HSI, T&E, software, technology, programmatic | (3) Is the defined aging aircraft management process identifying the appropriate technical resources to staff all appropriate issues? | [5 empty] | 3.b(3)
| training, hardware, risk, software, HSI, logistics, T&E, programmatic | (4) Are mitigation approaches in place for all prioritized issues, and are issue mitigations resourced? | [5 empty] | 3.b(4)
| training, hardware, HSI, software, T&E, logistics, risk, programmatic | (5) Is the user involved in the prioritization and mitigation process? | [5 empty] | 3.b(5)
| training, software, hardware, logistics, T&E, technology, HSI, programmatic | (6) Is the defined aging aircraft management process supporting the technical resources in accomplishing resolution to the action items? | [5 empty] | 3.b(6)
| logistics, technology, HSI, programmatic | c. Appropriate Discrepancy Reporting Program Status | 0 | 0 | 0 | 0 | 0 | 3.c
| logistics, HSI, programmatic | (1) Is the defined appropriate discrepancy reporting program management process identifying all appropriate issues? | [5 empty] | 3.c(1)
| logistics, HSI, programmatic | (2) Is the defined appropriate discrepancy reporting program management process prioritizing all appropriate issues? | [5 empty] | 3.c(2)
| logistics, HSI, technology, programmatic | (3) Is the defined appropriate discrepancy reporting program management process identifying the appropriate technical resources to staff all appropriate issues? | [5 empty] | 3.c(3)
| logistics, HSI, technology, programmatic | (4) Is the defined appropriate discrepancy reporting program management process supporting the technical resources in accomplishing resolution to the action items? | [5 empty] | 3.c(4)
| logistics, technology, HSI, programmatic | d. Configuration Management (CM) Program Status | 0 | 0 | 0 | 0 | 0 | 3.d
| logistics, HSI, programmatic | (1) Is the defined CM process identifying all appropriate issues? | [5 empty] | 3.d(1)
| logistics, HSI, programmatic | (2) Is the defined CM process prioritizing all appropriate issues? | [5 empty] | 3.d(2)
| logistics, technology, HSI, programmatic | (3) Is the defined CM process identifying the appropriate technical resources to staff all appropriate issues? | [5 empty] | 3.d(3)
| logistics, technology, HSI, programmatic | (4) Is the defined CM process supporting the technical resources in accomplishing resolution to the action items? | [5 empty] | 3.d(4)
| logistics, T&E, software, risk, technology, HSI, programmatic | e. Software Program Status | 0 | 0 | 0 | 0 | 0 | 3.e
| logistics, HSI, software, risk, programmatic | (1) Is the defined software management process identifying all appropriate safety issues? | [5 empty] | 3.e(1)
| logistics, HSI, software, risk, programmatic | (2) Is the defined software management process prioritizing all appropriate safety issues? | [5 empty] | 3.e(2)
| logistics, software, technology, HSI, programmatic | (3) Is the defined software management process identifying the appropriate technical resources to staff all appropriate issues? | [5 empty] | 3.e(3)
| logistics, software, technology, HSI, programmatic | (4) Is the defined software management process supporting the technical resources in accomplishing resolution to the action items? | [5 empty] | 3.e(4)
| T&E, risk, software, logistics, HSI, programmatic | (5) Have supportability and obsolescence issues within the software development and software test environments been identified, and are the identified issues being adequately addressed? | [5 empty] | 3.e(5)
| training, software, logistics, T&E, technology, HSI, programmatic | f. Operational Advisory Group (OAG) Status (or equivalent) | 0 | 0 | 0 | 0 | 0 | 3.f
| training, logistics, HSI, software, T&E, programmatic | (1) Is the defined OAG management process identifying all appropriate issues? | [5 empty] | 3.f(1)
| training, logistics, HSI, software, T&E, programmatic | (2) Is the defined OAG management process prioritizing all appropriate issues? | [5 empty] | 3.f(2)
| training, software, logistics, T&E, technology, HSI, programmatic | (3) Is the defined OAG management process identifying the appropriate technical resources to staff all appropriate issues? | [5 empty] | 3.f(3)
| training, software, logistics, T&E, technology, HSI, programmatic | (4) Is the defined OAG management process supporting the technical resources in accomplishing resolution to the action items? | [5 empty] | 3.f(4)
| HSI, RAM, logistics, technology, programmatic | g. Readiness and Maintenance Status | 0 | 0 | 0 | 0 | 0 | 3.g
| HSI, logistics, technology, programmatic | (1) Readiness Improvement Plan (or appropriate) | [5 empty] | 3.g(1)
| HSI, logistics, programmatic | (a) Is the defined readiness improvement plan management process identifying all appropriate readiness issues? | [5 empty] | 3.g(1)(a)
| HSI, logistics, programmatic | (b) Is the defined readiness improvement plan management process prioritizing all appropriate readiness issues? | [5 empty] | 3.g(1)(b)
| logistics, HSI, technology, programmatic | (c) Is the defined readiness improvement plan management process identifying the appropriate technical resources to staff all appropriate issues? | [5 empty] | 3.g(1)(c)
| logistics, HSI, technology, programmatic | (d) Is the defined readiness improvement plan management process supporting the technical resources in accomplishing resolution to the action items? | [5 empty] | 3.g(1)(d)
| HSI, RAM, logistics, technology, programmatic | (2) Conditioned Based Maintenance Plan | [5 empty] | 3.g(2)
| HSI, RAM, logistics, programmatic | (a) Is the defined conditioned based maintenance plan management process identifying all appropriate issues? | [5 empty] | 3.g(2)(a)
| HSI, RAM, logistics, programmatic | (b) Is the defined conditioned based maintenance management process prioritizing all appropriate issues? | [5 empty] | 3.g(2)(b)
| HSI, RAM, logistics, technology, programmatic | (c) Is the defined conditioned based maintenance management process identifying the appropriate technical resources to staff all appropriate issues? | [5 empty] | 3.g(2)(c)
| HSI, RAM, logistics, technology, programmatic | (d) Is the defined conditioned based maintenance management process supporting the technical resources in accomplishing resolution to the action items? | [5 empty] | 3.g(2)(d)
| training, logistics, software, RAM, technology, HSI, programmatic, interoperability | h. Product Support Plan (PSP) Status | 0 | 0 | 0 | 0 | 0 | 3.h
| HSI, RAM, logistics, programmatic | (1) Is the maintenance planning program adequate to support the in-service requirements of the fielded system and spares? | [5 empty] | 3.h(1)
| HSI, RAM, logistics, programmatic | (2) Is the manpower and personnel adequate to support the in-service requirements of the fielded system and spares? | [5 empty] | 3.h(2)
| HSI, RAM, logistics, programmatic | (3) Is the supply support program adequate to support the in-service requirements of the fielded system and spares? | [5 empty] | 3.h(3)
| HSI, RAM, logistics, programmatic | (4) Is the support equipment program adequate to support the in-service requirements of the fielded system and spares? | [5 empty] | 3.h(4)
| HSI, RAM, logistics, technology, programmatic | (5) Is the technical data program adequate to support the in-service requirements of the fielded system and spares? | [5 empty] | 3.h(5)
| training, RAM, logistics, HSI, programmatic | (6) Is the training and training support program adequate to support the in-service requirements of the fielded system and spares? | [5 empty] | 3.h(6)
| logistics, software, hardware, RAM, technology, HSI, programmatic | (7) Is the computer resources support program adequate to support the in-service requirements of the fielded system and spares? | [5 empty] | 3.h(7)
| HSI, RAM, logistics, programmatic | (8) Are the facilities adequate to support the in-service requirements of the fielded system and spares? | [5 empty] | 3.h(8)
| HSI, RAM, logistics, programmatic | (9) Is the packaging, handling, storage, and transportation (PHS&T) program adequate to support the in-service requirements of the fielded system and spares? | [5 empty] | 3.h(9)
| logistics, hardware, software, HSI, programmatic, interoperability | (10) Is the design interface elements adequate to support the in-service requirements of the fielded system and spares? | [5 empty] | 3.h(10)
| risk, HSI, logistics, programmatic | i. Funding Status | 0 | 0 | 0 | 0 | 0 | 3.i
| logistics, HSI, programmatic | (1) Is there adequate documentation to support the in-service requirements identified in the funding requirements? | [5 empty] | 3.i(1)
| logistics, HSI, programmatic | (2) Do the funding requirements reflect all the in-service requirements identified by the program policies and metrics? | [5 empty] | 3.i(2)
| risk, HSI, logistics, programmatic | (3) Are the impacts of funding shortfalls understood and plans in place to mitigate risk, and is the user involved in the mitigation process? | [5 empty] | 3.i(3)
| logistics, HSI, programmatic | (4) Has the budget been staffed and approved? | [5 empty] | 3.i(4)
| training, risk, hardware, RAM, logistics, HSI, software, T&E, programmatic | j. ISR Action Items Status | 0 | 0 | 0 | 0 | 0 | 3.j
| training, risk, hardware, RAM, logistics, HSI, software, T&E, programmatic | (1) Have all action items from this review been documented? | [5 empty] | 3.j(1)
| training, risk, hardware, RAM, logistics, HSI, software, T&E, programmatic | (2) Have all action items from previous reviews been briefed? | [5 empty] | 3.j(2)
| training, risk, hardware, RAM, logistics, HSI, software, T&E, programmatic | (3) Are unresolved issues staffed and prioritized? | [5 empty] | 3.j(3)
| software, hardware, logistics, HSI, technology, risk, programmatic, interoperability | 4. Process Review | 0 | 0 | 0 | 0 | 0 | 4
| training, hardware, software, T&E, logistics, HSI, technology, risk, programmatic | a. Program Management Plan (PMP) | 0 | 0 | 0 | 0 | 0 | 4.a
| training, risk, T&E, software, logistics, HSI, technology, programmatic | (1) Are the program management processes that are in place adequate to address the technical challenges of the program and adequate to address program risks? | [5 empty] | 4.a(1)
| training, hardware, software, T&E, logistics, HSI, risk, technology, programmatic | (2) Is there an updated PMP that is reflective of the emergent technical issues and risks? | [5 empty] | 4.a(2)
| programmatic, technology | (3) Are there program management processes in place to properly manage the system requirements and attendant technical emphasis areas? | [5 empty] | 4.a(3)
| programmatic | (4) Is the program being managed to adjust resources, while addressing the issues? | [5 empty] | 4.a(4)
| logistics, HSI, programmatic | b. Operational Requirements Management Plan | 0 | 0 | 0 | 0 | 0 | 4.b
| logistics, RAM, programmatic | (1) Is there a process in place for requirements management and is it being applied to properly address in-service support of the program? | [5 empty] | 4.b(1)
| programmatic | (2) Are requirements being managed and traced from higher level (parent) requirements to lower level (offspring) requirements? | [5 empty] | 4.b(2)
| logistics, HSI, programmatic | (3) Is adequate requirements traceability in place to ensure flow across the PSP elements? | [5 empty] | 4.b(3)
| hardware, software, training, T&E, logistics, HSI, technology, risk, programmatic, interoperability | c. System Safety Management Plan | 0 | 0 | 0 | 0 | 0 | 4.c
| training, software, HSI, hardware, risk, logistics, T&E, programmatic | (1) Is there a defined system safety management process? | [5 empty] | 4.c(1)
| training, software, HSI, hardware, risk, logistics, T&E, programmatic | (2) Is the system safety management plan up to date and being used? | [5 empty] | 4.c(2)
| training, software, HSI, hardware, risk, logistics, T&E, programmatic, interoperability | (3) Is the system safety management process shared by the Government and contractor (if applicable) team? | [5 empty] | 4.c(3)
| training, hardware, RAM, logistics, HSI, T&E, software, programmatic | (4) Is the user involved in the system safety management process? | [5 empty] | 4.c(4)
| risk, logistics, hardware, RAM, HSI, software, T&E, training, programmatic | (5) Does the system safety management process properly track all risks on a continuous basis and provide for update of the mitigation approaches? | [5 empty] | 4.c(5)
| training, logistics, HSI, software, T&E, hardware, risk, programmatic | (6) Are mitigation approaches in place for all "yellow" and "red" risks, and are the risk mitigations resourced? | [5 empty] | 4.c(6)
| training, logistics, T&E, software, HSI, hardware, risk, technology, programmatic | (7) Does the system safety management process provide for risk updates to support the technical reviews and program management reviews? | [5 empty] | 4.c(7)
| training, hardware, risk, logistics, HSI, software, T&E, technology, programmatic, interoperability | d. Risk Management Process | 0 | 0 | 0 | 0 | 0 | 4.d
| training, hardware, risk, software, HSI, logistics, T&E, programmatic | (1) Is there a defined risk management process? | [5 empty] | 4.d(1)
| training, hardware, risk, software, HSI, logistics, T&E, programmatic | (2) Is the risk management plan up to date and being used? | [5 empty] | 4.d(2)
| training, logistics, risk, software, HSI, hardware, T&E, programmatic, interoperability | (3) Is the risk management process shared by the Government and contractor (if applicable) team? | [5 empty] | 4.d(3)
| risk, programmatic | (4) Is the user involved in the risk management process? | [5 empty] | 4.d(4)
| training, logistics, risk, software, HSI, hardware, T&E, programmatic | (5) Does the risk management process properly track all risks on a continuous basis and provide for update of the mitigation approaches? | [5 empty] | 4.d(5)
| risk, technology, programmatic | (6) Does the risk management process provide for risk updates to support the technical reviews and program management reviews? | [5 empty] | 4.d(6)
| hardware, logistics, HSI, programmatic, interoperability | e. Configuration Management (CM) Plan | 0 | 0 | 0 | 0 | 0 | 4.e
| HSI, logistics, programmatic | (1) Is the CM plan in place and up-to-date? | [5 empty] | 4.e(1)
| hardware, logistics, HSI, programmatic | (2) Is the system requirement for each Configuration Item (CI) documented and being managed in accordance with the CM plan? | [5 empty] | 4.e(2)
| HSI, logistics, programmatic, interoperability | (3) Are changes to the managed CI configurations controlled and tracked to higher level (System Specification, Capability Development Document (CDD), Net-Centric Operation and Warfare, and battle space engineering), and lower level (system requirements) documents? | [5 empty] | 4.e(3)
| HSI, RAM, logistics, technology, risk, programmatic, interoperability | f. Readiness Improvement Program (or appropriate) | 0 | 0 | 0 | 0 | 0 | 4.f
| HSI, RAM, logistics, programmatic | (1) Is there a defined readiness improvement program management process, and is the readiness improvement program management plan up to date and being used? | [5 empty] | 4.f(1)
| logistics, HSI, programmatic, interoperability | (2) Is the readiness improvement program management process shared by the Government and contractor (if applicable) team? | [5 empty] | 4.f(2)
| HSI, RAM, logistics, programmatic | (3) Is the user involved in the readiness improvement program management process? | [5 empty] | 4.f(3)
| HSI, risk, logistics, programmatic | (4) Does the readiness improvement program management process properly track all readiness gaps on a continuous basis and provide for update of the mitigation approaches? | [5 empty] | 4.f(4)
| HSI, risk, logistics, programmatic | (5) Are mitigation approaches in place for all readiness gaps? | [5 empty] | 4.f(5)
| HSI, risk, logistics, programmatic | (6) Are gap mitigations resourced with cross functional teams? | [5 empty] | 4.f(6)
| HSI, risk, logistics, programmatic | (7) Is the user involved in the gap mitigation process? | [5 empty] | 4.f(7)
| logistics, HSI, technology, programmatic | (8) Does the readiness improvement program management process provide for gap updates to support the technical reviews and program management reviews? | [5 empty] | 4.f(8)
| risk, RAM, logistics, HSI, technology, programmatic, interoperability | g. Conditioned Based Maintenance Plan | 0 | 0 | 0 | 0 | 0 | 4.g
| HSI, RAM, logistics, programmatic | (1) Is there a defined conditioned based maintenance management process, and is the conditioned based maintenance management plan up to date and being used? | [5 empty] | 4.g(1)
| HSI, RAM, logistics, programmatic, interoperability | (2) Is the conditioned based maintenance management process shared by the Government and contractor (if applicable) team? | [5 empty] | 4.g(2)
| HSI, risk, logistics, RAM, programmatic | (3) Does the conditioned based maintenance management process properly track all IMP gaps on a continuous basis and provide for update of the mitigation approaches? | [5 empty] | 4.g(3)
| HSI, risk, logistics, RAM, programmatic | (4) Are mitigation approaches in place for all conditioned based maintenance gaps? | [5 empty] | 4.g(4)
| HSI, risk, logistics, RAM, programmatic | (5) Are gap mitigations resourced with cross functional teams? | [5 empty] | 4.g(5)
| HSI, RAM, logistics, technology, programmatic | (6) Does the conditioned based maintenance management process provide for gap updates to support the technical reviews and program management reviews? | [5 empty] | 4.g(6)
| risk, HSI, logistics, RAM, programmatic | 5. Completion / Exit Criteria | 0 | 0 | 0 | 0 | 0 | 5
| HSI, RAM, logistics, programmatic | a. Have system problems been categorized to support the operation and maintenance funding requirements determination process? | [5 empty] | 5.a
| HSI, logistics, programmatic | b. Have required budgets (in terms of work years) been established to address all system problems in all priority categories? | [5 empty] | 5.b
| HSI, logistics, programmatic | c. Has required staffing (in terms of skills) been established to address all system problems in all priority categories? | [5 empty] | 5.c
| HSI, risk, logistics, programmatic | d. Have the current levels of system operational risk and system readiness been quantified and related to current operation and maintenance funding and acquisition funding budgets? | [5 empty] | 5.d
| HSI, risk, logistics, programmatic | e. Have the future levels of system operational risk and system readiness have been quantified and related to future year operation and maintenance funding and acquisition funding budgets? | [5 empty] | 5.e
CAUTION: Entries, changes, deletions or comments should only be made on the checklist. Any entries entered directly on the summary pages will not be recorded within the checklist and will disable linkage between the checklist and the summary pages.
Question
Flagged
High Priority
Show All
HSI
Interoperability
Logistics
Training
PQM
Programmatic
Risk
Software
T&E
Technology
Unhide TD
Level 1
Hide TD
Unhide NA
Hide NA
EVM
Hardware
RAM

## Red
“Systems Engineering for Mission Success”
|  | In-Service Review | [6 empty] | Name of the program being reviewed / date
|  | Program Risk Assessment Checklist | [6 empty] | 0
Name / Code / Technical Specialty of reviewer
0
Risk Character
R = Red, Y = Yellow, G = Green, U = Unknown / Unavailable, NA = Not Applicable
Special Interest | Technical Discipline | Legend: | R | Y | G | U | NA | Item | Comments / Mitigations
Special Interest | Technical Discipline | Legend: | R |  |  |  |  | Item | Comments / Mitigations | Question

## Yellow
“Systems Engineering for Mission Success”
|  | In-Service Review | [6 empty] | Name of the program being reviewed / date
|  | Program Risk Assessment Checklist | [6 empty] | 0
Name / Code / Technical Specialty of reviewer
0
Risk Character
R = Red, Y = Yellow, G = Green, U = Unknown / Unavailable, NA = Not Applicable
Special Interest | Technical Discipline | Legend: | R | Y | G | U | NA | Item | Comments / Mitigations

## Unknown
“Systems Engineering for Mission Success”
|  | In-Service Review | [6 empty] | Name of the program being reviewed / date
|  | Program Risk Assessment Checklist | [6 empty] | 0
Name / Code / Technical Specialty of reviewer
0
Risk Character
R = Red, Y = Yellow, G = Green, U = Unknown / Unavailable, NA = Not Applicable
Special Interest | Technical Discipline | Legend: | R | Y | G | U | NA | Item | Comments / Mitigations

## NA
“Systems Engineering for Mission Success”
|  | In-Service Review | [6 empty] | Name of the program being reviewed / date
|  | Program Risk Assessment Checklist | [6 empty] | 0
Name / Code / Technical Specialty of reviewer
0
Risk Character
R = Red, Y = Yellow, G = Green, U = Unknown / Unavailable, NA = Not Applicable
Special Interest | Technical Discipline | Legend: | R | Y | G | U | NA | Item | Comments / Mitigations
| logistics, PQM, programmatic | (1) What is the number of systems supporting the operational requirements including systems in the pipeline for maintenance and modifications? (Indicate answer in "Comments" block.) | NA |  |  |  |  | 1.a(1)
| logistics, PQM, programmatic | (3) What is the number of unclassified deployed sites including facilities required to support pipeline systems and spares? | NA |  |  |  |  | 1.a(3)
| logistics, PQM, programmatic | (2) What is the number of permanent sites including facilities required to support pipeline systems and spares? (Indicate answer in "Comments" block.) | NA |  |  |  |  | 1.a(2)
| logistics, PQM, programmatic | (3) What is the number of unclassified deployed sites including facilities required to support pipeline systems and spares? (Indicate answer in "Comments" block.) | NA |  |  |  |  | 1.a(3)
| logistics, HSI, software, T&E, training, programmatic | (1) What are the current fiscal year funding requirements and controls, and what is the execution status of the current funding? | NA |  |  |  |  | 1.e(1)
| training, logistics, HSI, software, T&E, programmatic | (2) What are the prioritized unfunded requirements? | NA |  |  |  |  | 1.e(2)
| HSI, training, software, T&E, programmatic | (3) What are the identified impacts for the prioritized unfunded requirements? | NA |  |  |  |  | 1.e(3)
| HSI, training, software, T&E, programmatic | (4) What are the identified impacts for the prioritized unfunded requirements? | NA |  |  |  |  | 1.e(4)
| logistics, HSI, software, T&E, training, programmatic | (1) What are the current fiscal year funding requirements and controls, and what is the execution status of the current funding? (Indicate answer in "Comments" block.) | NA |  |  |  |  | 1.e(1)
| training, logistics, HSI, software, T&E, programmatic | (2) What are the prioritized unfunded requirements? (Indicate answer in "Comments" block.) | NA |  |  |  |  | 1.e(2)
| HSI, training, software, T&E, programmatic | (4) What are the identified impacts for the prioritized unfunded requirements? (Indicate answer in "Comments" block.) | NA |  |  |  |  | 1.e(4)
| risk, programmatic | a. What is the operational system hazard risk status? (Indicate answer in "Comments" block.) | NA |  |  |  |  | 2.a

## Level 1
“Systems Engineering for Mission Success”
|  | In-Service Review | [6 empty] | Name of the program being reviewed / date
|  | Program Risk Assessment Checklist | [6 empty] | 0
Name / Code / Technical Specialty of reviewer
0
Risk Character
R = Red, Y = Yellow, G = Green, U = Unknown / Unavailable, NA = Not Applicable
Special Interest | Technical Discipline | Legend: | R | Y | G | U | NA | Item | Comments / Mitigations
0 | training, HSI, software, T&E, logistics, PQM, technology, risk, programmatic, interoperability | 1. Program Overview | 0 | 0 | 0 | 0 | 6 | 1 | 0
0 | training, T&E, risk, software, logistics, HSI, programmatic | 2. Program Risk Assessment | 0 | 0 | 0 | 0 | 3 | 2 | 0
0 | training, logistics, hardware, T&E, software, HSI, technology, risk, programmatic, interoperability | 3. In-Service Management Metrics | 0 | 0 | 0 | 0 | 0 | 3 | 0
0 | software, hardware, logistics, HSI, technology, risk, programmatic, interoperability | 4. Process Review | 0 | 0 | 0 | 0 | 0 | 4 | 0
0 | risk, HSI, logistics, RAM, programmatic | 5. Completion / Exit Criteria | 0 | 0 | 0 | 0 | 0 | 5 | 0
|  | Total: | 0 | 0 | 0 | 0 | 9
Return to ISR