NAVAIRINST 4355.19D

AIR-4.0/5.0/6.0

# NAVAIR INSTRUCTION 4355.19D

## From:  Commander, Naval Air Systems Command

Subj:  SYSTEMS ENGINEERING TECHNICAL REVIEW PROCESS

#### Ref:   (a) DoDD 5000.1, The Defense Acquisition System, of 12 May 03

(b) DoDI 5000.2, Operation of the Defense Acquisition System, of 12 May 03

(c) USD(AT&L) Memorandum, Prototyping and Competition, of 19 Sep 07

(d) USD(AT&L) Memorandum, Policy Addendum for Systems Engineering in DoD, of 20 Feb 04

(e) USD(AT&L) Memorandum, Policy for Systems Engineering, of 22 Oct 04

(f) SECNAVINST 5000.2D, Implementation and Operation of the Defense Acquisition System and the Joint Capabilities Integration and Development System, of 16 Oct 08

(g) Defense Acquisition Guidebook, of 8 Oct 04

(h) Naval Systems Engineering Guide, of Oct 04

(i) NAVSO P-3690, of Sep 01 (NOTAL)

(j) DoD Systems Engineering Plan Preparation Guide, Version 2.01, of Apr 08

(k) NAVAIRINST 3960.2C, of 9 May 94

(l) NAVAIRINST 5000.21A, of 2 Nov 05

(m) USD(AT&L) Memorandum, Competitive Source Selection, of 24 August 07

(n) NAVAIRINST 4200.36C, of 2 Jun 04

## Encl:  (1) Systems Engineering Technical Review Process Handbook

(2) Systems Engineering Technical Review Timing

1.  Purpose.  To establish policy, outline the process, and assign responsibilities for the planning and conduct of Systems Engineering Technical Reviews (SETRs) of Naval Air Systems Command (NAVAIR) programs.

2.  Cancellation.  This instruction supersedes and cancels NAVAIRINST 4355.19C, of 10 Apr 06.  Since this is a major revision, individual changes are not indicated.

3.  Scope.  This instruction applies to all personnel supporting all NAVAIR and Aviation Program Executive Officer (PEO) programs involved with the design, development, test and evaluation, acquisition, in-service support, and disposal of naval aviation weapon systems and equipment.

4.  Discussion

a.  References (a) and (b) provide policies and principles applicable to all Department of Defense (DoD) acquisition programs.  Among other things, these references require that acquisition programs be managed by application of systems engineering (SE) that optimizes operational capability, total system performance, and minimizes total ownership costs.  Additionally, cost realism and knowledge-based risk management are mandated.  Specifically, knowledge about key aspects of a system shall be demonstrated by the time decisions are to be made.  Appropriate Modeling and Simulation (M&S) will be performed to validate Capability Based Assessments and to verify system performance and interoperability requirements.  A proactive approach to bridging the transition process between capability gap identification and capability gap solutions will be applied.  This requires a broad assessment of the war fighting environment, strategies, and processes as well as materiel solutions.  Technology risk shall be reduced and critical technology elements shall have been demonstrated in a relevant environment, with alternatives identified, prior to program initiation.  Joint interoperability requires that critical information sharing is defined and documented in a Net-Ready Key Performance Parameter.  Integration risk shall be reduced and product design demonstrated prior to the Critical Design Review (CDR).  Manufacturing risk shall be reduced and producibility demonstrated prior to full-rate production.  Reference (c) directs that DoD Services “formulate all pending and future programs with acquisition strategies and funding that provide for two or more competing teams producing prototypes (of key system elements) through Milestone (MS) B.”  It also states “that this acquisition strategy should be extended to all appropriate programs below ACAT 1.”  Reference (d) mandates that programs develop a Systems Engineering Plan (SEP) for Milestone Decision Authority (MDA) approval in conjunction with each Milestone review.  The SEP shall describe the program’s overall technical approach, and detail the timing, conduct, and success criteria of technical reviews.  Additional policy was established by reference (e) which requires each PEO to have a lead or chief systems engineer on staff responsible to the PEO for the application of SE, review of assigned programs’ SEPs, and oversee SEP implementation across the PEO’s portfolio of programs.  This reference also states that technical reviews of program progress shall be event driven (vice schedule driven), be conducted when the system under development meets the review entrance criteria as documented in the SEP, and include participation by SMEs who are independent of the program.  Reference (f) established a Navy (2 pass/6 gate) review process to improve governance and insight into the development, establishment, and execution of Department of the Navy (DON) acquisition programs.  Reference (g) is a comprehensive guide to be used for best practices, lessons learned, and expectations.  It is accessible at http://akss.dau.mil/dag.

b.  The SETRs are an integral part of the SE process and life cycle management, and are consistent with existing and emerging commercial/industrial standards.  These reviews are not the place for problem solving, but to verify that problem solving has been accomplished.  Reference (h) provides SE processes for use in support of the acquisition of NAVAIR systems.  As a part of the overall SE process, SETRs enable an independent assessment of emerging designs against plans, processes and key knowledge points in the development process.  An integrated team consisting of Integrated Product Team (IPT) members and independent competency SMEs conducts these reviews.  Engineering rigor, interdisciplinary communications, and competency insight are applied to the maturing design in the assessment of requirements traceability, product metrics, and decision rationale.  These SETRs bring to bear additional knowledge to the program design/development process in an effort to ensure program success.  Overarching objectives of these reviews are a well-managed engineering effort leading to a satisfactory Technical Evaluation, which will meet all of the required technical and programmatic specifications.  This, in turn, will ensure a satisfactory Operational Evaluation (OPEVAL), and the fielding of an effective and suitable system for the warfighter.

c.  Additionally, Reference (a) requires that Program Managers (PMs) develop and implement performance-based logistics (PBL) strategies that optimize total system availability while minimizing costs and logistics footprint.  Reference (i), “Acquisition Logistics for the Rest of Us”, states as fundamental principles that logistics planning is part of the SE process, cannot be accomplished independently, and that reliability and maintainability (R&M) engineering are cornerstones of a successful logistics program.

d.  To completely assess the system under review, the SETR process also reviews warfare analysis, logistics, test and evaluation, and engineering initiatives.  These initiatives include, but are not limited to, the Joint Service Specification Guide (JSSG), the Technology Readiness Assessment (TRA), “Section 804” software acquisition initiative, Defense Information Technology Standards Registry (DISR), and the DoD Architecture Framework (DoDAF).  The JSSG is a DoD initiative that provides guidance in the form of tailorable templates utilized in the preparation of aviation performance specifications.  The TRA is a requirement of reference (b) that consistently assesses the maturity of critical technology elements (CTEs) associated with enabling technologies for all DoD Acquisition Category (ACAT) programs.  Section 804 of the National Defense Authorization Act for Fiscal Year 2003 mandates improvement of the DoD’s software acquisition processes.  The DISR provides information technology standards, and the DoDAF defines a standard way to organize the system architecture into complementary and consistent views.

e. In addition, the SETR process will review the system's conformance and performance relative to its Joint Warfare Capability; Preferred System Concept; Concept of Operations (CONOPS); Information Assurance; Interoperability; Integrated Architecture; and Net Centric Warfare; and Doctrine, Organization, Training, Materiel, Leadership and Education, Personnel and Facilities (DOTMLPF) Requirements.

5.  Policy

a.  Assistant Program Managers for Systems Engineering (APMSEs), Assistant Program Managers for Test and Evaluation (APMT&Es) and Assistant Program Managers for Logistics (APMLs), as part of Program Teams, shall ensure that planning for SETRs is fully integrated with the overall program plans for all PEO and NAVAIR managed acquisition programs in ACATs I through IV.  Programs already in progress should comply, to the maximum extent possible, within the constraints of their existing budget and contract(s).  This SETR planning shall be coordinated with the Program Manager, Air (PMA), the cognizant Assistant Program Executive Officer for Engineering (APEO(E)), the cognizant Assistant Program Executive Officer for Logistics (APEO(L)) and the cognizant Assistant Program Executive Officer for Test and Evaluation (APEO(T&E)).  The SETRs should form the technical basis for establishing:

(1) operational capability and program definition in terms of (cost, schedule, and performance);

(2) an independent NAVAIR cost estimate of the program; and,

(3) program milestone reviews.

The SETRs may also be applied to Abbreviated Acquisition Programs (AAPs) and other non-ACAT programs as determined and tailored by the cognizant PEO and/or Program/Project Manager.  Programs already in progress should comply, to the maximum extent possible, within the constraints of their existing budget and contract(s).  Joint and other external organization programs should incorporate these policies, as applicable.

b.  The SETRs provide the PEOs, and PMAs with sound analytical basis for the system's acquisition and confidence that the system will satisfy its Joint Capability requirements.  The SETRs provide the PMA with an integrated technical (e.g., logistics, engineering, test and evaluation (T&E), in-service support) baseline evaluation, and confidence that the technical baseline is mature enough for the next stage of development.  This is accomplished via a multi-discipline, engineering assessment of the program’s progress towards demonstrating and confirming completion of required accomplishments as defined in the program SEP.  These SETRs include an overall technical assessment of cost, schedule, and performance risk, which forms the basis for an independent NAVAIR cost estimate.  End products of these SETRs include a capability assessment, technical baseline assessment, an independent review of risk assessments and mitigation options, Request for Action (RFA) forms, and minutes.  A TRA Report with the determination on the CTEs, if any, and their Technology Readiness Level (TRL) maturity level is provided from TRAs.

c.  Program APMSEs shall ensure naval aviation acquisition programs include a SEP as part of program documentation.  Reference (d) establishes SE policy, and mandates a SEP for all programs.  An extract from this reference states, “All programs responding to a capabilities or requirements document, regardless of acquisition category, shall apply a robust SE approach that balances total system performance and total ownership costs within the family-of-systems, systems-of-systems context.  Programs shall develop a SEP for MDA approval in conjunction with each Milestone review, and integrated with the Acquisition Strategy.  This plan shall describe the program's overall technical approach, including processes, resources, metrics, and applicable performance incentives.  It shall also detail the timing, conduct, and success criteria of technical reviews.”  Additionally, reference (e) requires that technical reviews of program progress shall be event driven (vice schedule driven), be conducted when the system under development meets the review entrance criteria as documented in the SEP, and include participation by SMEs who are independent of the program.  The policies mandated by these memoranda will be incorporated in the next update to reference (b).

d.  References (h) and (j) are valuable tools in preparing the SEP, which should define the overall plan (who, what, where, when, how, etc.) for SETRs and the SE processes to be employed by the program.  The following essential SETRs should be conducted, as applicable, on all ACAT programs:

(1) Initial Technical Review (ITR);

(2) Alternative Systems Review (ASR);

(3) System Requirements Review I (SRR-I);

(4) System Requirements Review II (SRR-II);

(5) System Functional Review (SFR);

(6) Software Specification Review (SSR);

(7) Preliminary Design Review (PDR);

(8) Critical Design Review (CDR);

(9) Integration Readiness Review (IRR);

(10) Test Readiness Review (TRR);

(11) Flight Readiness Review (FRR) (for airborne systems);

(12) System Verification Review/Production Readiness Review (SVR/PRR);

(13) Physical Configuration Audit (PCA); and,

(14) In-Service Review (ISR)

At a minimum, SRRs, PDRs, CDRs and SVRs should be conducted on all non-ACAT acquisition programs.  For acquisition programs with multiple software increments, the program should conduct a SSR, CDR, and IRR for each increment.

In addition to SETRs, programs conduct Integrated Baseline Reviews (IBRs) and Operational Test Readiness Reviews (OTRRs) in accordance with references (g) and (k) respectively.  AIR-4.0 personnel do not normally chair these reviews, but they do provide technical elements and support as detailed in enclosure (1).  The Program SEP should provide the technical elements of the IBR and OTRR.

e.  Enclosure (1) describes the objective of each SETR, IBR, OTRR, and provides additional information concerning implementation of this instruction, and guidelines for compliance.  Elimination of reviews should be coordinated with the APEO(E), APEO(L), and APEO(T&E), and must be approved by the MDA as documented in the Program’s approved SEP.  For any review not held, the SEP shall document when the critical work elements, products, and maturity metrics associated with that phase of development will be approved.  Programs need not conduct SETRs that do not apply given the structure of the program, i.e., where in the acquisition cycle the program will enter.  Functional and/or SMEs, together with government and contractor IPT membership, will participate in these SETRs.  Customer representatives and other stakeholders are invited to provide the warfighter’s perspective with a clear linkage to their requirements.

f.  One or more stand-alone technical review Assessment Checklists are available for each of the reviews.  Specifically, there are four ITR checklists, based on the product (aircraft, propulsion, avionics or missile/weapon) being acquired, and two SRR checklists.  The first SRR, SRR-I, is typically conducted by the government with limited contractor involvement in the first part of the Technology Development (TD) acquisition phase before MS B.  The second SRR, SRR-II, is conducted with multiple contractors during requirements development, also before MS B.  These SETR checklists may be tailored to suit individual program scope and complexity at the discretion of the Technical Review Board (TRB) Chairperson.  This tailoring may be updated as part of setting the review agenda and participants, in conjunction with the program APMSE, APMT&E, APML, APEO(E), APEO(L), and APEO(T&E).  These checklists are living documents, and are intended to be updated based on user experiences.  Reference (l) establishes policy and assigns responsibilities for a standardized Risk Management process across NAVAIR programs.

g.  The cognizant APMSE, with APML and APMT&E assistance, shall ensure SETRs are conducted in accordance with the Program SEP and the enclosures of this instruction.  The SETRs are structured to assess a program’s progress towards demonstrating and confirming completion of required accomplishments and their readiness to proceed to the next key milestone.  These reviews should be event driven and conducted when the system’s design/development is ready for review.  As a product develops, it passes through a series of SETRs of increasing detail.  SETRs are structured to be an approval of the technical baseline, and confidence that the technical baseline is mature enough for the next stage of development.  Each SETR must have defined entry criteria tied to the required level of design/development maturity and applied across all requirements and technical disciplines.  These reviews are confirmation of a process.  New issues should not come up at SETRs.  If significant new issues do emerge, the review is being held prematurely, with an inherent increase in program risk.  Enclosure (2) aligns the chronology of these SETRs in relation to acquisition program events (milestones and reviews).  The Program SEP should detail the specific SETR chronology for the program.  This is especially important for evolutionary acquisition strategies, using incremental development processes, or multi-component programs.

h.  Per reference (m), DoD has experienced a significant increase in the number of competitive source selection decisions which are protested by industry.  The protests consume vast amounts of time, delay program initiation, delivery of capability, and strain relations with industry partners and stakeholders.  DoD must take steps in an effort to avoid these protest situations.  In order to mitigate this situation, the NAVAIR Source Selection Office (AIR-4.10) should be utilized to the maximum extent possible in conjunction with the SETR checklists.  Although primarily addressing competitive source selections and government contractor dialogue prior to contract approval, the issue of SETRs is frequently not adequately addressed in many contracts.  It is imperative to adequately define all program SETRs contractually.  Acquisition program plans and contracts should provide for the conduct of these SETRs as part of the acquisition planning process, in accordance with reference (n).  Careful consideration should be given before using individual SETRs as a basis for progress or performance-based contract payments.  However, payments for successful closure of SETRs as part of the established award fee criteria may be considered.  The SETRs are formally completed by the TRB Chairperson via a letter of closure.  Unless specifically provided for in the contract(s), successful completion of SETRs does not affect the requirements, terms, and conditions set forth in the program’s contract(s).  SETRs should not be used to:

(1) constitute government approval of the design;

(2) change the responsibility as set forth in the contract(s);

(3) change or affect ownership of the design; or,

(4) relieve the contractor from meeting specification requirements as set forth in the contract(s).

i.  The SETR process depends on objective documentation, analysis, and process plans.  These documents are inherently part of the engineering process and are prepared to document the progress of a configuration managed design and archive design decisions.  Early reviews such as the ITR and ASR may include non-NAVAIR participants and contractors other than the system prime.  Each review begins with preparation of documentation and analysis for government technical experts to review.  The correctness and completeness of this information should be measured against clearly stated objective standards.  The PM, APMSE, AMPL, and APMT&E shall ensure the Statement of Work (SOW), System Specification, and Contract Data Requirements Lists (CDRLs) contain the required plans, specifications, and analysis to support the SETR process.  The method and timing of delivery should provide for government review and adjudication of comments prior to the SETR.

j.  All action items generated at a technical review shall be captured in the AIR-4.1 SETR archival database.  This includes action items that were duplicates of otherwise captured or categorized action items as well as any action items closed prior to conclusion of the review.  The following categories shall be used to categorize action items.  Any action item that is satisfied prior to the conclusion of the review should be captured under the appropriate category below and dispositioned as “Closed” with the appropriate supporting information.

- Request for Action:  Critical action item; Required to close the Technical Review.  Not to be confused with the RFA Form described in enclosure (1)

- Request for Information (RFI):  Action item to only provide information/data in support of the current review.  (Not required to close the Technical Review)

- Action to Minutes:  Action Items that are not required to close each Technical Review.  Sometimes this is programmatic in nature.  Planned close-out date should be tied as entry/completion criteria to a future milestone.

- Not Accepted:  Category used to document any action items generated at a Technical Review that were duplicates of other accepted action items or otherwise declined by the Chairperson/TRB.  A clear statement must be included in the Action Item database to indicate why each action item was categorized as “not accepted”.  This category should not be used to capture action items that were satisfied/closed prior to conclusion of the review.

k.  At any given SETR, the chairperson leads the review.  The SETR itself is conducted and approved by the extended IPT (program IPT together with convened SMEs and other competency representatives).  Approval of a SETR, as it relates to this instruction, is defined as:

(1) approval of the RFAs generated during the SETR;

(2) approval of the technical baseline evaluation;

(3) confidence that the technical baseline is mature enough for the next stage of development; and,

(4) promulgation of the assessment of risk in progressing toward an operationally effective and suitable system evaluation generated during the SETR.  Completion of SETRs occurs after the TRB Chairperson formally closes the review by letter.

6.  Action.  The following responsibilities are assigned relative to the planning and conduct of SETRs, and the reporting of SETR results as indicated below:

a.  The SE Department (AIR-4.1) shall nominate qualified SETR Chairpersons and coordinate the designation of the SETR Chairperson(s) from the appropriate competency.  The technical authority, AIR-4.0 or AIR-4.1 will appoint TRB chairpersons.  The appointed TRB chairpersons shall be independent of the program team.  Specific guidance concerning Chairpersons (and Co-chairs, if applicable) is addressed in enclosure (1).  The designated Chairperson, with the assistance of the APMSE, APMT&E and APML, shall assemble and convene the TRB for the system under review.  The TRB analyzes the material presented to develop a technical assessment of the system under review, determine disposition of RFAs in an executive session, and issue minutes of the SETR.

b.  Research and Engineering Department Heads (AIR-4.x) shall provide representatives, analysts, and other SMEs, as required, to update cost estimates, support a Schedule Risk Assessment, and evaluate objective evidence within their technical authority as part of each SETR.

c.  Integrated Systems Evaluation Experimentation and Test Division Heads (AIR-5.1)/Squadron Commanding Officers shall provide SMEs, as required, to make technical assessments as part of each SETR.

d.  Program APMSEs, with APMT&E and APML assistance, shall support the PMA:

(1) to ensure program acquisition plans and strategies provide for the conduct of SETRs, and that those reviews are considered in the milestone decision-making process.  This planning shall be coordinated with the PMA, the cognizant APEO(E), the cognizant APEO(L), and the cognizant APEO(T&E);

(2) to ensure each program has a SEP, and that SETRs are addressed in that plan, as well as in the contract(s); and,

(3) to ensure the program contract(s), SOWs, CDRLs, and master schedule include provisions for these identified SETRs, and the required documentation and data to support each Technical Review

e.  Program APMSEs, with APMT&E and APML assistance, shall:

(1) ensure the performing activity provides the supporting data and stakeholder participation in the SETRs;

(2) develop, coordinate, and execute, in cooperation with the performing activity, individual SETR arrangements;

(3) ensure the preparation of appropriate material is coordinated across the IPTs; and,

(4) organize and supervise the documentation of RFAs in support of the TRB Chairperson.

7.  Review.  The AIR-4.1, AIR-5.1 and Logistics Management Integration (AIR-6.6) shall coordinate the review of this instruction annually, and implement updates and changes as appropriate.

DAVID J. VENLET

Distribution:

Electronic only, via NAVAIR Directives Web site:

http://directives.navair.navy.mil/.

Systems Engineering Technical Review

Process Handbook

Table of Contents

Title                         Page

Use of this Handbook and associated Assessment Checklists	  1

SETR Scheduling					                      2

Getting on Contract – Suggested Contract Language		       4

Request For Action (RFA) Procedures			            6

Sample RFA Form							            9

Acronym definitions						                10

Initial Technical Review				                     14

Alternative Systems Review				                20

#### System Requirements Review I				                28

#### System Requirements Review II				                37

#### System Functional Review				                     46

Software Specification Review			                     54

#### Preliminary Design Review I				                63

#### Integrated Baseline Review				                74

#### Critical Design Review					                81

Integration Readiness Review				                90

#### Test Readiness Review				                     99

#### Flight Readiness Review				                    108

#### Operational Test Readiness Review                           119

#### System Verification Review/Production Readiness Review     	124

#### Physical Configuration Audit				               131

#### In-Service Review							          136

Use of this Handbook and associated Assessment Checklists

This SETR Process Handbook, plus the associated Assessment Checklists are utilized to facilitate the implementation of NAVAIRINST 4355.19D.  This enclosure (Enclosure (1)) provides introductory information, plus 18 individual sections, each describing a SETR or the technical elements of program reviews.  Enclosure (2) summarizes SETR timing in the acquisition cycle.  The Program SEP should detail the specific SETR chronology for each program.  The individual technical review sections describe the purpose, timing, entry criteria, planning, conduct, and completion of each SETR.  They are provided for guidance, and should not be modified.

One or more Assessment Checklists are provided for each SETR.  Specifically, there are four ITR checklists, based on the product (aircraft, propulsion, avionics or missile/weapon) being acquired, and two SRR checklists.  These checklists should be utilized in conjunction with the program SEP while executing the program.  The checklists are an effective tool/guide for use during preparation for each SETR, during SETRs, and may be used during special audits and reviews (such as Non-Advocate Reviews, Green/Red Teams, etc.).  The Assessment Checklists are living documents, intended to be updated based on inputs from user experiences.

SETR Scheduling

- Timing of review:  SETRs are scheduled when the required system baseline has achieved a level of maturity sufficient for the intended review

- Subsystem reviews precede system level SETR

- Subsystem review process may take months or years

- To minimize cost, the review facility chosen should be   adequate to meet the needs of the working group members

- As early as possible, but not later than (NLT) 3 months before SETR [earlier start for more complex programs]

- APMSE/APML/APMT&E/APEO review checklist for applicability of each question and add new questions as appropriate

- APMSE/APML/APMT&E/APEO(E)/APEO(L)/APEO(T&E) identify relevant Competencies required for TRB and solicit Competency leadership to nominate TRB candidates

- APEO(E) to coordinate TRB Chair

- APMSE/APML/APMT&E create repository of relevant program data for TRB use (standard "Entry Criteria" for each SETR)

- AIR-4.0 or AIR-4.1 designates the TRB chairperson who is independent of the program team.

- NLT 2 months before SETR

- Level II Competency leaders identify TRB members

- TRB Chairperson approves tech review checklist and schedule

- TRB Chairperson identifies any special interest areas for detailed briefing

- TRB Chairperson approves TRB membership

- APMSE leads planning meeting with APML, APMT&E, TRB, Chairperson, and contractor(s)

- NLT 1 month before the SETR

– APMSE or Chairperson designee in-briefs all TRB members

– TRB members review data repository

- TRB members interact with IPT counterparts

– Notify SMEs of their participation

- The SETR meeting

- Includes all TRB members (and other stakeholders), often held at contractor's facility, and typically 2 - 3 days duration (for large programs)

– Each TRB member responsible for comprehensively evaluating his or her area of expertise

- For overall program assessment at end of review, TRB Chairperson may ask TRB members to provide inputs independently, or to meet as group to discuss findings and provide single integrated input

- As soon as possible, but NLT 1 month after SETR

- Chairperson, APMSE, APML, and APMT&E review RFAs, summary assessment, and findings

– Chairperson presents finding and assessment to PMA/PM, and signs out memo

- APMSE and IPT begin acting on RFAs

- SETRs are considered complete when all draft RFAs are signed off, and an acceptable level of program risk is ascertained

### Getting on Contract – Suggested Contract Language

A recurring issue that Programs conducting SETRs face is what contractual or legal significance attaches to a Contractor’s successful completion of a required technical review.  It is recommended that the NAVAIR Source Selection Office (AIR-4.10) and the NAVAIR Office of Counsel (AIR-11.0) be consulted for guidance and/or assistance.  Often times the question will arise whether the Government’s approval of a particular technical review results in the Government henceforth waiving its rights to enforce the performance terms and conditions of the contract in the event the Contractor is ultimately unsuccessful in completing this contract.

This is a very complex question to be sure, and the precise answer will necessarily turn on the particular facts and circumstances of individual programs.  That is not to say, however, that some certainty cannot be introduced into the process.  At the outset it is important that the contracting parties reach agreement as to the fundamental purpose of the SETRs.  As this instruction makes clear, that purpose is to evaluate, at particular points in time, the progress of a system’s design or development towards meeting the Joint Capabilities Documents (JCDs), Initial Capabilities Documents (ICDs), Capability Development Documents (CDDs), or Capability Production Documents (CPDs).  As this iterative process progresses, the SETRs become increasingly detailed, and as such become more sharply focused on the final system configuration, implementation, and support.  At some point along the review continuum, the Government oversight of the Contractor’s design results in either expressly or tacitly agreeing that the design is compliant with the objective.  After this point in time, it is important to note that while it might be said that the Government has “assumed responsibility” for the design, the Government does not necessarily also assume the burden for any subsequent technical failures.  Again, that is a very complex question the resolution of which will depend on an assessment of the particular facts and circumstances to determine the cause of the failure.

In order to clarify the responsibilities of the contracting parties under the SETR process, you are encouraged to coordinate with your Procuring Contracting Officer (PCO) to incorporate a standard clause into the contract, “SIGNIFICANCE OF SYSTEMS ENGINEERING TECHNICAL REVIEWS REQUIRED UNDER THIS CONTRACT”.  The clause can be found in the NAVAIR clause book.  Since AIR-2.0 maintains configuration control of clauses in the clause book, the clause is not presented here, and the user must obtain the most current version from their AIR-2.0 PCO.

The clause states that the review process and any results of the reviews do not eliminate the contractor’s responsibility to meet the contract requirements.  The clause also states that regardless of Government interaction in the design review process, the contractor maintains design responsibility for the system.

Request For Action Procedures

1.  The RFA form, or its equivalent, will be used to document a situation where a technical approach does not appear to meet the specification requirement or where a change must be made even though the design appears to meet the specification requirement.  The RFA process will consist of the originator’s identification of a problem, level of urgency, recommended action, the IPT response, and Executive Session disposition.  The form may also be used to document a RFI or to reflect meeting minutes or actions.  NAVAIR 4355/4 (01/99) will be included as part of the technical review report.  A sample format is provided on page 11 of this enclosure.

2.  RFA Initiator.  The upper portion of each RFA shall be completed by the person identifying the action and may be supplemented by additional sheets as required.  It is the responsibility of the person identifying an action to complete the first portion in sufficient detail to clearly document the design issue.  Specific entries are as follows:

a.  Type.  Indicate type of review.

b.  Assignment.  Indicate the intended use of the form.

c.  Subject/Title.  Enter a meaningful short title for the item discussed.

d.  Subsystem Panel.  Indicate the technical review data package or panel session where the problem was identified.

e.  Request No.  This number is assigned by the TRB Recorder for tracking purposes.

f.  Referenced Document.  List paragraph reference to design specification, SOW, or its applicable requirement document.

g.  Specific Problem or Concern.  Enter an explanation of the problem.  Define a problem in clear, concise terms that can be understood and answered.  Relate the problem to either a specification requirement either not met or a technical specification change required.

h.  Recommended Action.  Self-explanatory

i.  Recommend Category.  Assign category according to the following definitions:

(1) Category I.  Within the scope of the current contract.  When approved by the Executive Session, action will be initiated as specified on the RFA format to meet the estimated completion date.  The RFA constitutes authority to proceed, and no further direction is required.

(2) Category II.  Not within the scope of the current contract.  When approved by the Executive Session, and when directed by the Navy contracting officer, the contractor will prepare either a cost and schedule impact statement or a formal proposal, as indicated, and submit to NAVAIR.

(3) Category III.  Rejected.  By agreement of the technical review board or at the Executive Session, no further action will be undertaken.

j.  Recommend Urgency/Date.  Assign the urgency according to the following definitions, and a recommended completion date:

(1) Level 1.  Indicates the existence of a hazardous condition such as safety of flight or personnel hazard.

(2) Level 2.  Indicates the existence of condition(s) requiring attention, which could affect mission performance.

(3) Level 3.  Indicates desired, but not mandatory, design improvements or changes, which would improve mission or aircraft performance.

k.  Initiator’s Name/IPT, Activity/Code/Phone, and Date.  Fill in the self-explanatory information.

3.  IPT Response.  The IPT personnel are to document the response to the problem or concern.  They should use the middle portion of the RFA.  Specific entries as follows:

a.  Proposed Action.  The appropriate IPT person shall add pertinent facts regarding the RFA to include comments on discrepancies, recommended actions, alternate recommended actions, and impact.

b.  Proposed Schedule.  Provided the best available estimate of the schedule for accomplishment of the recommended action.

c.  Recommended Category/Urgency/Date.  Enter per category/urgency level definitions given previously, and the recommended completion date.

d.  Engineer’s Name, Function/Department/Phone, and Date.  Enter the information for the IPT member assigned to prepare the response and the date of the response.

4.  Executive Session.  Following the IPT response with the proposed action and categories, RFAs will be referred to the Executive Session for resolution of any differences between NAVAIR and contractor positions.  The final Executive Session decision, assigned category, urgency level, and the scheduled completion date will be recorded.  An assessment of the impact of this decision upon the program will also be indicated.  The program and contractor representative signatures, followed by the TRB Chairperson’s signature, are entered as a concluding event after the disposition of the RFA has been determined.

SAMPLE REQUEST FOR ACTION FORM

| RFA INITIATOR | TYPE: (SRR (PDR (CDR (Other: | ASSIGNMENT: (RFA (RFI (Minutes/Action |
| --- | --- | --- |
|  | SUBJECT/TITLE: | SUBSYSTEM PANEL: | REQUEST NO: |
|  | REFERENCED DOC: |
|  | SPECIFIC PROBLEM OR CONCERN: |
|  | RECOMMENDED ACTION: |
|  | RECOMMENDED CATEGORY: | RECOMMENDED URGENCY/DATE: |
|  | INITIATOR’S NAME: IPT: | ACTIVITY/CODE/PHONE: | DATE: |
| IPT RESPONSE | PROPOSED ACTION: |
|  | PROPOSED SCHEDULE: |
|  | RECOMMENDED CATEGORY: | RECOMMENDED URGENCY/DATE: |
|  | ENGINEER’S NAME: | FUNCTION/DEPT/PHONE: | DATE: |
| EXECUTIVE SESSION | EXECUTIVE REVIEW AND DECISION: |
|  | ASSIGNED CATEGORY: | ASSIGNED URGENCY/DATE: |
|  | IMPACT: |
|  | PROGRAM REPRESENTATIVE: DATE: | CONTRACTOR REPRESENTATIVE: DATE: |
|  | TRB Chairperson: DATE: |

NAVAIR 4355/4 (1/99)

Acronym Definitions

AAP                   Abbreviated Acquisition Program

ACAT                  Acquisition Category

ADM			       Acquisition Decision Memorandum

AoA                   Analysis of Alternatives

APEO(E)               Assistant Program Executive Officer

(Engineering)

APEO(L)               Assistant Program Executive Officer

(Logistics)

APEO(T&E)             Assistant Program Executive Officer (Test

and Evaluation)

APML                  Assistant Program Manager for Logistics

APMSE                 Assistant Program Manager for Systems

Engineering

APMT&E                Assistant Program Manager for Test and

Evaluation

ASN(RDA)              Assistant Secretary of the Navy (Research,

Development and Acquisition)

ASR                   Alternative Systems Review

CARD                  Cost Analysis Requirements Description

CDD                   Capability Development Document

CDR                   Critical Design Review

CDRL                  Contract Data Requirements List

CI                    Configuration Item

CM                    Configuration Management

CNR                   Chief of Naval Research

COMOPTEVFOR           Commander, Operational Test and Evaluation

Force

CONOPS                Concept of Operations

COTS                  Commercial Off-the Shelf

CPD                   Capability Production Document

CSCI                  Computer Software Configuration Item

CSI                   Critical Safety Item

CTE                   Critical Technology Element

DASN                  Deputy Assistant Secretary of the Navy

DISR                  Defense Information Technology Standards

Registry

DoD                   Department of Defense

DoDAF                 Department of Defense Architecture

Framework

DON                   Department of the Navy

Acronym Definitions

DOTMLPF               Doctrine, Organization, Training,

Materiel, Leadership and Education,

Personnel, and Facilities

DT                    Developmental Testing

DUSD(S&T/DDR&E)       Deputy Under Secretary of Defense (Science

and Technology / Director, Defense

Research and Engineering (Office of the

Secretary of Defense)

ECP                   Engineering Change Proposal

EDRAP                 Engineering Data Requirements Agreement

Plan

ERB                   Executive Review Board

ESOH                  Environment, Safety and Occupational

Health

EVM                   Earned Value Management

FCA                   Functional Configuration Audit

FMECA                 Failure Modes, Effects, and Criticality

Analysis

FOT&E                 Follow on Operational Test and Evaluation

FRP                   Full Rate Production

FRR                   Flight Readiness Review

FST                   Fleet Support Team

FY                    Fiscal Year

FYDP                  Future Years Defense Program

IBR                   Integrated Baseline Review

ICD                   Initial Capabilities Document

IDE                   Integrated Data Environment

ILSMT                 Integrated Logistics Support Management

Team

IMP                   Integrated Maintenance Program

IMS                   Integrated Master Schedule

IPT                   Integrated Product Team

IRR                   Integration Readiness Review

IRS                   Interface Requirement Specification

IRT                   In Response To

ISRB                  In-Service Review Board

ITR                   Initial Technical Review

JCD                   Joint Capabilities Document

JSSG                  Joint Service Specification Guide

KPP                   Key Performance Parameter

LRIP                  Low Rate Initial Production

MAIS                  Major Automated Information Systems

Acronym Definitions

M&S                   Modeling and Simulation

MCOTEA                Marine Corps Operational Test and

Evaluation Activity

MDA                   Milestone Decision Authority

MOE                   Measure of Effectiveness

MOP                   Measure of Performance

MS	                 Milestone

MTBF                  Mean Time Between Failure

NAMDRP	Naval Aviation Maintenance Discrepancy

Reporting Program

NAVRIIP               Naval Aviation Readiness Integrated

Improvement Program

NAVAIR                Naval Air Systems Command

NDI                   Non-developmental Item

NLT                   Not later than

OAG                   Operational Advisory Group

O&M/N                 Operation and Maintenance, Navy

OPEVAL                Operational Evaluation

OSD                   Office of the Secretary of Defense

OT                    Operational Testing

OT&E                  Operational Test and Evaluation

OTA                   Operational Test Agency

OTRR                  Operational Test Readiness Review

OV                    Operational View

PBL                   Performance-Based Logistics

PCA                   Physical Configuration Audit

PCO                   Procuring Contracting Officer

PDR                   Preliminary Design Review

PEO                   Program Executive Officer

PM                    Program Manager

PMA                   Program Manager, Air

PMB                   Performance Management Baseline

POM                   Program Objectives Memorandum

PPIP                  Program Protection Implementation Plan

PPP                   Program Protection Plan

PRR                   Production Readiness Review

R&M                   Reliability and Maintainability

RCM                   Reliability Centered Maintenance

RFA                   Request for Action

RFI                   Request for Information

RMP                   Risk Management Plan

S&T                   Science and Technology

Acronym Definitions

SDD                   System Development and Demonstration

SDS                   System Design Specification

SDP                   Software Development Plan

SE                    Systems Engineering

SEMP                  Systems Engineering Management Plan

SEP                   Systems Engineering Plan

SETR                  Systems Engineering Technical Review

SFR                   System Functional Review

SOW                   Statement of Work

SQT                   System Qualification Test

SRD                   Software Requirements Description

SRR                   System Requirements Review

SRS                   System Requirement Specification

SSR                   Software Specification Review

SVR                   System Verification Review

SwRS                  Software Requirements Specification

SYSCOM                Systems Command

T&E                   Test and Evaluation

TD                    Technology Development

TDP                   Technical Data Package

TEMP                  Test and Environment Master Plan

TIM                   Technical Interchange Meeting

TPM                   Technical Performance Measurement

TRA                   Technology Readiness Assessment

TRAC                  Technology Readiness Assessment

Coordinator

TRB                   Technology Readiness Board

TRL                   Technology Readiness Level

TRR                   Test Readiness Review

USD(AT&L)             Under Secretary of Defense (Acquisition,

Technology and Logistics)

V&V                   Verification and Validation

WBS                   Work Breakdown Structure

##### Initial Technical Review

1.  ITR Purpose - The ITR is a multi-disciplined technical review to support a Program’s initial Program Objective Memorandum (POM) submission.  This review is intended to ensure that a Program’s technical baseline is of sufficient rigor to support a valid (acceptable cost risk) cost estimate and enable an independent assessment of that estimate by cost, technical and program management SMEs.  The technical baseline must also properly capture the validated operational capabilities and performance constraints.  The ITR assesses the envisioned requirements and conceptual  approach of a proposed Program and verifies that the requisite analyses of alternatives, capability assessments, M&S, research, development, test, engineering, logistic, and programmatic bases for the program reflect the complete spectrum of technical and developmental challenges and risks.  The enabling/critical technologies, constraints, and cost/risk drivers are identified and quantified.  Additionally, the ITR ensures that historical and prospective drivers of Weapon System cost have been quantified to the maximum extent and that the range of uncertainty in these parameters have been captured and reflected in the Program cost estimates.

A different SETR ITR Assessment Checklist is available for each of four types of weapons systems.  These specific checklists include Aircraft, Propulsion, Avionics, and Missile/Weapon.

Large acquisition programs are required to define program and system parameters in accordance with the Cost Analysis Requirements Description (CARD) as described in DoD 5000.4-M, of Dec 92.  The basic CARD technical and programmatic guidance, tailored to suit the scope and complexity of the program, should be followed to ensure that all pertinent technical cost drivers are addressed.  The term CARD-like document will be used in this SETR Handbook to describe the minimum technical description required to achieve the objectives of the ITR.  The success of the ITR will also depend on independent SME review of each of the identified cost drivers.  It is critical that SMEs be drawn from the correct technical competencies that specialize in each of the areas addressed in the CARD-like document, and that the document must be completed and provided to the cost analyst 60 days before the desired review completion date.  AIR-4.2 (Cost Analysis) ensures (via independent assessment) that the cost drivers detailed in the CARD-like document have been used properly in the development of the Program cost estimate.  Completion of this review should provide:

a.  A complete CARD-like document detailing system overview, risk, system operational concept (see separate document, AIR-4.2 Technical and Programmatic Checklist, Appendix 2).

b.  An assessment of the technical and cost risks of the proposed Program.

c.  An independent NAVAIR assessment of the Program’s cost estimate.

2.  ITR Timing - The ITR should be conducted to support formal Program cost estimate submission, that is prior to POM submission or Program Review  updates in the fall timeframe.  The ITR should be held well in advance of the actual cost estimate submission to allow time for issue resolution and proper executive level concurrence on process and results.  While the ITR may first be accomplished well in advance of Program initiation (MS B) or even prior to a ICD or CDD, the ITR may be repeated as necessary to support POM or Program Review cycles, major changes in scope, breach of Acquisition Program Baseline Agreement, or following ICD or CDD approvals.

3.  ITR Entry Criteria

a.  A preliminary agenda has been coordinated by the APMSE 30 days (nominally) prior to the ITR.

b.  A Program CARD-like document has been prepared by the IPT and made available to all ITR participants 45–60 days prior to the review.

c.  Documented assumptions that relate to the CARD-like document.  These assumptions will be critical to understanding the CARD-like document and its relevance to understanding costs.

d.  The AIR-4.2 preliminary cost estimates for the Program.

e.  The ICD, Analysis of Alternatives (AoA) Plan, Supportability Objectives, Preliminary Integrated Architecture and Best Material Approach(es) are made available.

4.  ITR Planning

a.  TRB Chairperson – Planning for a technical review should start with a request for a TRB Chairperson who is independent of the program team, nominally 45 days prior to conduct of the review.  Typically the PMA, assigned IPT leader, or assigned APMSE requests a TRB chairperson be appointed /coordinated by AIR-4.1.  Prior to this request, the assigned APMSE should have coordinated chairperson requirements with the cognizant APEO(E).  Chairperson assignments should be reflective of program scope and risk.  With the concurrence of AIR-4.0, the ITR TRB Chairperson may be assigned from AIR-4.2.  The role of the chairperson includes:

(1) Determination of TRB membership;

(2) Development of the final review elements;

(3) Oversight of the technical review and RFA process; and,

(4) Issuance of the Technical Review Summary Report.

b.  Technical Review Elements – The APMSE and the assigned Chairperson shall coordinate with the cognizant APEO(E) in the development of a preliminary agenda for the planned review.  A sample review is shown below in paragraph 5.a.  This agenda should be made available to the review participants 30 days prior to conduct of the review.

c.  Technical Review Participants

(1) TRB (typical composition):

(a) TRB Chairperson;

(b) PM representative; and,

(c) APMSE, who should:

1. Ensure the performing activity provides the  supporting data and participation in the required review;

2. Develop, coordinate, and execute, in cooperation with the performing activity, individual review arrangements;

3. Ensure the preparation of requirements performance material is coordinated across IPTs;

4. Conduct the review for the TRB; and,

5. Organize and supervise the documentation of RFAs in support of the TRB Chairperson.

(d) Warfare Analysts, to ensure that operational capability requirements are established and validated in conjunction with the appropriate stakeholders;

(e) The APML, who should ensure all relevant supportability requirements are addressed;

(f) Software (AIR-4.1) representative, as appropriate;

(g) The APMT&E who should ensure all T&E requirements are addressed;

(h) Cost Team (AIR-4.2) representatives (should include Lead for the Cost Estimate effort as well as a Senior AIR-4.2 Competency representative).  With the concurrence of AIR-4.0, the ITR TRB Chairperson may be assigned from AIR-4.2.

(i) Recorder who is responsible for collating RFAs for submission to the TRB.  The recorder should have the Technical Review Report prepared for distribution by the Chairperson.

(j) Resource Sponsor (Requirements Officer); and,

(k) User representatives, if appropriate

(2) Technical Competency representatives as required to brief CARD-like document inputs.

.

(3) Non-advocate SMEs, as required, to review and validate CARD-like document technical and programmatic descriptions.

d. ITR Location – The facility chosen should be adequate to ensure complete participation by all cognizant competencies and organizations.  Selection of the location should consider minimizing participant travel and associated costs.

5.  Conduct of ITR Review - All TRB participants are to assess the materials at the review, document concerns by means of RFAs, and submit RFAs to the TRB Recorder.

a.  ITR Review Elements:

(1) Introduction/agenda/administrative

(a) Purpose of review

(b) RFA procedures overview

(c) Program overview

(2) Follow ITR Program Assessment Checklist (one of four aircraft; propulsion; avionics; or missile/weapon)

b.  ITR Products:

(1) Technical Review Summary Report, with the following attachments:

(a) List of attendees, to include; name, functional area represented, NAVAIR code, phone number, and email address;

(b) Completed RFA forms;

(c) Meeting minutes; and,

(d) Independent assessment as to the technical suitability of the CARD-like document to support the estimate of Program costs and an independent assessment of the Program’s Cost Estimate.

(2) An updated, approved CARD-like document.

- ITR Completion

a.  The ITR is considered complete when all draft RFAs are signed off, the CARD-like document has been updated, reviewed and approved, and the TRB chairperson formally closes the review by letter.

b.  Typically at completion, the ITR should affirmatively answer the following questions:

(1) Does the CARD-like document capture the key program, cost drivers development costs (all aspects of hardware, test, human integration, and software), production costs, operation and support costs?  Is the CARD-like document complete and thorough?)

(2) Are the underlying assumptions used in developing the CARD-like document technically and programmatically sound and complete?

(3) Have the appropriate technical and programmatic competencies been involved in the CARD-like document development, and have the proper SMEs been involved in its review?

(4) Are the risks known and manageable within the cost estimate?

(5) Will the program achieve the requirements embodied in its ICD, AoA Plan, Supportability Objectives, Preliminary Integrated Architecture, and Interoperability Requirements?

(6) Is the program, as captured in the CARD-like document, executable?

Alternative Systems Review

1.  ASR Purpose - The ASR is a multi-disciplined product and process assessment to ensure that the resulting set of requirements agrees with the customers needs and expectations, to ensure that the system concepts align with the external environment (systems, information networks, and infrastructure), and to ensure the system under review can proceed into the TD acquisition phase.  The ASR should be complete prior to MS A.  The ASR is to assess whether the user's needs, advanced technologies and new concepts of employment can be resolved to define a potential system or a set of systems that warrant proceeding into the TD acquisition phase.  A key premise is that the infinite number of possible solutions has been narrowed as a result of the AoA.  The AoA decisions and additional constraints placed on the next phase of development need to be captured and documented as part of the SE process.

The role of the acquisition community in holding this review is to establish the trade-space baseline that will be further matured as the system is defined and preparations are made for the first SRR.  Generally this review assesses the alternative systems that have been evaluated during Concept Refinement, primarily through the AoA, and ensures that the preferred system is cost effective, affordable, operationally effective and suitable, and can be developed to provide a timely solution to a need at an acceptable level of risk.  Of critical importance to this review is the understanding of available system concepts to meet the requirements from the ICD or the CDD, as well as the affordability/operational effectiveness/ technologies / adaptability to the evolving external environment / risk inherent in each alternative concept.  Depending on the overall acquisition strategy, one or more preferred system solutions may be carried forward into the TD acquisition phase.  By reviewing alternative system concepts, the ASR also helps ensure that sufficient effort has been given to conducting trade studies that consider and incorporate alternative system designs that may more effectively and efficiently meet the defined requirements.  Acceptable level of risk is key to a successful review.

Completion of this review should provide:

a.  An agreement on the preferred system concept(s) to take forward into the TD acquisition phase / Concept Refinement Maturity Assessment;

b.  A comprehensive definition and assessment of the initial Preferred System Concept(s) to ensure that capability objectives and operational requirements are defined in conjunction with the appropriate stakeholders.  The ICD, AoA, Supportability Objectives and Concept, Preliminary Integrated Architecture and Best Materiel Approach(es) are supported by thorough M&S and were subjected to rigorous warfare analysis;

c.  A review of the draft CDD, Preliminary System Specification, T&E Strategy, and Technology implementation plan;

d.  A comprehensive rationale for preferred system concept solution, which includes an AoA evaluating relative cost / schedule / performance (hardware, human, software) / process integration / technology risks;

e.  A comprehensive assessment on the relative risks associated with including Commercial Off-The Shelf (COTS) or Non-Developmental Items (NDI) as opposed to a new design, with emphasis on host platform environmental design, diagnostic information integration, dependence on other government programs and maintenance concept compatibility;

f.  A comprehensive risk assessment for the TD acquisition phase;

g.  Trade studies/technical demonstrations for concept risk reduction;

h.  Joint requirements for the purposes of compatibility, interoperability, and integration;

i.  Refine threshold and objectives initially stated as broad measures of effectiveness;

j.  A comprehensive plan for the TD acquisition phase (hardware and software) that addresses critical components to be developed and demonstrated, their cost, and critical path drivers;

k.  Initial planning for the System Development and Demonstration (SDD) acquisition phase; and,

l.  Draft system requirements document if one does not already exist.  (This is the highest-level document that includes key relationships among subsystems to be created by the project to represent the customer/user requirements).  This systems requirement document should include a system level description of all software elements required by the preferred system concept.

The review may be tailored in accordance with the technical scope and risk of the system.  Under no circumstances should the review be tailored completely out of the development plan.  Details of any tailoring should be described in the SEP, or should occur as part of the APMSE or systems engineer coordination of the review elements with the AIR-4.1 cognizant authority (APEO(E)).

2.  ASR Timing - The ASR is typically conducted at the conclusion of the Concept Refinement phase, before MS A, following completion of TD acquisition planning, and prior to the TD acquisition phase.  The ASR should not be scheduled at a particular number of months after contract award; rather, ASR should be scheduled after the AoA has been conducted, and results are favorable to proceed with a narrower definition of the system(s) to be developed.

3.  ASR Entry Criteria

a.  A preliminary agenda has been coordinated (nominally) 30 days prior to the ASR.

b.  ASR technical products listed below for both hardware and software system elements have been made available to the cognizant ASR participants prior to the review:

(1) AoA, Warfare Analysis findings and recommendations, M&S results and DOTMLPF impacts and considerations;

(2)	 Preferred System Concept(s);

(3) High level CONOPS documented in an Operational View (OV)-1 for each proposed mission area and drafts of the OV-2, 4, and 5;

(4) Analyses results and definition;

(5) Risk assessment and associated risk management / mitigation plan that includes the evolving external environment;

(6) 	System requirements document including interoperability and system distributed services requirements;

(7) Updated cost and schedule data; and,

(8) TD acquisition phase plan.

4.  ASR Planning

a.  The TRB Chairperson – Planning for a technical review should start with a request for a TRB Chairperson who is independent of the program team., nominally 45 days prior to conduct of the review.  Typically the PMA, assigned IPT leader, or assigned APMSE requests a TRB chairperson be appointed by AIR-4.1.  Prior to this request, the assigned APMSE should have coordinated chairperson requirements with the cognizant (APEO(E)).  Chairperson assignments should be reflective of program scope and risk.  The role of the chairperson includes:

(1) Determination of TRB membership;

(2) Development of the final review elements;

(3) Oversight of the technical review and RFA process; and,

(4) Issuance of the Technical Review Summary Report.

b.	Technical Review Elements – The APMSE and the assigned Chairperson shall coordinate with the cognizant APEO(E) in the development of a preliminary agenda for the planned review.  A sample review agenda is shown below in paragraph 5.a.  This agenda should be made available to the IPT 30 days prior to conduct of the review.

c.  Technical Review Participants:

(1) TRB (typical composition):

(a) TRB Chairperson;

(b) PM representatives (Industry and Government);

(c) APMSE, who should:

1.  Ensure the performing activity provides the supporting data and participation in the required review;

2.  Develop, coordinate, and execute, in review arrangements;

3.  Cooperation with the performing activity individuals.  Ensure the preparation of requirements performance material is coordinated across IPTs; and,

4.  Organize and supervise the documentation of RFAs in support of the TRB Chairperson.

(d) Appropriate warfare analyst SMEs, who would ensure that initial capability and operational requirements are addressed, established and validated in conjunction with the appropriate stakeholders;

(e) APML, who should ensure all relevant supportability requirements are addressed;

(f) Software (AIR-4.1) representative;

(g) APMT&E who should ensure all Test and Evaluation requirements are met;

(h) Cost Team (AIR-4.2) representative;

(i) Counsel, if required;

(j) Contracting Officer;

(k) Recorder; who is responsible for collating RFAs for submission to the TRB and recording the minutes of the ASR.  The recorder should have the Technical Review Report prepared for distribution by the Chairperson;

(l) Resource Sponsor (Requirements Officer); and,

(m) User representatives.

(2)	 SMEs as required to address system concepts, enabling technologies, certification, safety, etc.  These SMEs represent their NAVAIR competencies in the adjudication of RFAs, to include cost and schedule impacts.  SMEs should be notified at least 30 days prior to the scheduled review date; and,

(3) IPT briefers in accordance with the ASR agenda.

d.  ASR Location – The facility chosen should be adequate to ensure complete participation by all cognizant competencies and organizations.  The ASR is typically conducted at a government provided facility.  The facility must be able to support a meeting at the appropriate classification level to ensure effective information exchange and to address maturity of the system to enter system TD acquisition phase.  Selection of the location should consider minimizing participant travel and associated costs.

5.  Conduct of ASR Review - All TRB participants are to assess the materials at the review, document concerns by means of RFAs, and submit RFAs to the TRB Recorder.

a.  ASR Review Elements:

(1) Introduction/agenda/administrative;

(a) Purpose of review;

(b) RFA procedures overview;

(c) Risk Assessment procedures overview;

(d) Program overview; and,

(e) External Environment (System of Systems) overview.

(2) Review of ITR RFAs, if applicable;

(3) Risks;

(4) Program schedule;

(5) Metrics; and,

(6) Summary of Preferred Concept;

(a) Traceability of resulting requirements to customer’s needs and expectations;

(b) Assessment of the alternative systems;

(c).Description of the preferred concept; and,

(d) Cost, operational suitability, and schedule for preferred concept.

(7) Follow ASR Program Assessment checklist structure;

(8)	 Recommendation to proceed into requirements development; and,

(9) Review of RFAs.

b.  ASR Products:

(1) 	Technical Review Summary Report, with the following attachments:

(a) List of attendees, to include; name, functional area represented, NAVAIR code, phone number, and email address;

(b) Completed RFA forms;

(c) Meeting minutes; and,

(d) Recommendation to PMA as to the technical readiness of the program to enter requirements development.

(2) 	Updated Risk Assessment, including risks and recommended mitigations.

6.  ASR Completion - The ASR is considered complete when all draft RFAs are signed off, the Preferred Systems Concept is complete and acceptable, and an acceptable level of program risk is ascertained.  After the RFAs are closed, the system APMSE shall prepare a letter for the TRB Chairperson formally closing the review.  An ASR data package shall be prepared containing the products of the review and the closure letter, and submitted to the AIR-4.1 SETR archival database.

System Requirements Reviews

This section addresses both of the Pre-MS B System Requirements Reviews (SRR-I and SRR-II).  These two reviews are different and therefore presented separately in this enclosure.  The first SRR, SRR-I, is described below.  The description of SRR-II begins on page 8 in this enclosure.

System Requirements Review - I

1.  SRR-I Purpose - The primary purpose of SRR-I is to ensure that the government has established performance requirements and non-tailorable design requirements that are directly traceable to the CDD.  SRR-I is a technical assessment establishing the specification of the system under review, previously represented by the Performance Based Specification, continuing the requirements decomposition process prior to MS B.  This review ensures the CDD, DoD Directives, statutory and regulatory guidance, threshold design and certification standards, and applicable public law has been correctly and completely represented in the specification, Statement of Objective (SOO)/ SOW, and Request for Proposal (RFP).  This review begins a program definition process to establish the system description, program cost, and schedule constraints.  This review assesses the performance requirements as captured in the specification, correctly captures derived and correlated requirements, has well-understood verification criteria and processes, and is achievable through available technologies resulting from the TD acquisition  phase.  The understanding of requirements and verification procedures will be characterized in a technical risk assessment representing the ability of a contractor to comply with the contractual specification.  The ability to achieve the capabilities specified in the CDD within the program budget and schedule will be characterized in a program execution risk assessment.  Once the program risk has been identified, PMs can focus resources in documented mitigation plans early to avoid overruns and non-compliance.

A successful review is predicated on the IPT’s determination that the system requirements, preferred system concepts, available technology, and program resources (funding, schedule, staffing, and processes) form a satisfactory basis for proceeding to RFP release for contractor(s) to develop system definitions.  The review will also determine where the system specification drives solutions that are at a Technology Readiness Level less than 6.

The review may be tailored to the technical scope of the system.  Under no circumstances should the review be tailored completely out of the development plan.  The TRB Chairperson, who is independent of the program team and a representative of AIR-4.1, shall ensure that the details of any tailoring result in a complete evaluation of the system under review and fully characterizes the risk to successful execution.

SRR-I, as a component of the SETR process, serves as technical monitoring of program execution by senior functional area experts.  The contractor(s) selected at MS B will be responsible for the system design/performance requirements within the specification that flows from this design review.

2.  SRR-I Timing - SRR-I is typically conducted after the CDD is released for Joint Requirements Oversight Council approval prior to MS A during the Concept Refinement Phase.  It also serves as the final step in the Specification Review Board process administered by the APEO(E).  Adequate time should be allowed for critical RFAs to be closed prior to RFP release for continued development.  The TRB Chairperson, as a representative of AIR-4.1, may sign the system specification.  This signature by the TRB Chairperson completes the specification approval process for RFP release, as specified by NAVAIRINST 4120.9A (Preparation, Application, and Tailoring of Program Unique Specifications within the Naval Air Systems Command).

An additional SRR, SRR-II, will be conducted after the contractor(s) participating in the TD phase have established technology constraints impacting the specification and incorporated tailorable NAVAIR design requirements.

3.  SRR-I Entry Criteria

a.  System Requirements and Capabilities:

(1)	 System Specification complete and ready for Air-4.0 and AIR-6.0 approvals;

(2)	 Non-tailorable Design Requirements Identified;

(3)	 Level II review of specification complete;

(4)	 Traceability from CDD to specification;

(5)	 Integrated Architecture Operational, System and Technical Views;

(6) Applicable Information Assurance Controls Identified; and,

(7) 	Approved CONOPS, Tactical Situations, and Operational Situations.

b.  Test, Evaluation, and Certification of Product:

(1) M&S role in testing identified;

(2) Airworthiness criteria, in accordance with the most current policy, such as, but not limited to NAVAIRINST 13034.1C (Flight Clearance Policy for Air Vehicles and Aircraft Systems) and MIL-HDBK-516 (DoD Airworthiness Certification Criteria), understood and reflected in the specification and SOO/SOW;

.

(3) 	Requirement verification methodology with the type of analyses, tests, inspection, or demonstrations planned;

(4) All Certifying Agencies defined and requirements understood; and,

(5) Draft Test and Evaluation Master Plan (TEMP) available and reviewed.

c.  Engineering Processes, Control, and Analysis:

(1) Measures of Effectiveness (MOEs);

(2) Measures of Performance (MOPs) defined;

(3) Key Performance Parameters (KPPs) defined;

(4) Preliminary TRA complete;

(5) SEP complete; and,

(6) Software Development Plan (SDP) complete.

d.  Programmatic Processes, Control, and Analysis:

(1) SOO/SOW review for TD Phase complete;

(2) Section L & M criteria for the TD Phase established;

(3) Preliminary CARD;

(4) Program Protection Plan (PPP) Complete,

(5) Risk Management Plan (RMP) Complete,

(6) Configuration Management (CM) strategy;

(7) M&S Plan;

(8) Measurement Plan complete;

(9) Integrated Data Environment (IDE) procedures defined;

(10) Methodology for evaluating Life Cycle Cost established; and,

(11) CDRL and data requirements reviewed and approved in accordance with current policy, NAVAIRINST 4200.21D.

e.  Program Master Schedule, Earned Value, Cost:

(1) Government Integrated Master Schedule (IMS) is resourced at reasonable levels with realistic performance expectations;

(2) Functional IPT ownership of IMS established; and,

(3) Criteria for assigning, crediting, and establishing earned value is contained in Section L for the SDD acquisition phase.

f.  Program Execution Risk and Performance Risk:

(1) Program Technical risks identified; and,

(2) Program Execution risks identified.

4.  SRR-I Planning

a.  TRB Chairperson – Planning for a technical review should start at least 90 days prior to the review.  Technical working groups in all functional areas should begin in preparation for the SRR.  A request for a TRB Chairperson should occur at least 90 days prior to conduct of the review.  Typically the PMA, assigned IPT leader, or assigned APMSE requests a TRB chairperson who is independent of the program team be appointed by AIR-4.1.  Prior to this request, the assigned APMSE should have coordinated chairperson requirements with the cognizant APEO(E).  Chairperson assignments should be reflective of program scope and risk.  For software-only SRRs, AIR-4.1 still approves the appointment of the TRB Chairperson from the NAVAIR Software (AIR-4.1) organization.  The role of the chairperson includes:

(1) Determination of TRB membership;

(2) Approval authority for tailoring of checklist review items;

(3) Identifies elements for in depth review as required;

(4) Development of the final review elements;

(5) Oversight of the technical review and RFA process; and,

(6) Issuance of the Technical Review Summary Report.

b.  Technical Review Build-Up Technical Interchange Meetings (TIMs) – The APMSE should establish subsystem TIMs to review design readiness for SRR-I, establish completeness of documentation, adjudicate design disagreements, and prepare SRR-I presentation material.  These TIMs, usually begin at least 60 days prior to the SRR-I and are used to prepare the TRB membership for a successful review.  The TRB provides independent oversight of the design and is not the designing activity. Problem resolution should be completed during the build-up TIMs.

c.  Technical Review Elements – The APMSE and the assigned Chairperson shall coordinate with the cognizant APEO(E) in the development of a preliminary agenda for the planned review.  A sample review agenda is shown below in paragraph 5.a.  This agenda should be made available to the IPT at least 30 days prior to conduct of the review.

d.  Technical Review Participants:

(1) TRB (typical composition):

(a) TRB Chairperson;

(b) PM Representatives (Industry and Government);

(c) The APMSE, who should;

1.  Ensure the performing activity provides the supporting data and participation in the required review;

2.  Develop, coordinate, and execute, in cooperation with the performing activity, individual review arrangements;

3.  Ensure the preparation of SRR-I material is coordinated across IPTs;

4.  Participate in the review;

5.  Organize and supervise the documentation of  RFAs in support of the TRB Chairperson; and,

6.  Obtain concurrence between government and contractor SMEs on requirements decomposition.

(d) Warfare Analyst SMEs, to ensure that all capability, operational effectiveness are addressed;

(e) The APML, who should ensure all relevant supportability requirements are addressed;

(f) Cost Team (AIR-4.2) representative;

(g) Software (AIR-4.1) representative;

(h) Counsel, if required;

(i) Contracting Officer;

(j) Recorder; who is responsible for collating RFAs for submission to the TRB and recording of the minutes of the SRR-I.  The recorder should have the Technical Review Report prepared for distribution by the Chairperson;

(k) Resource Sponsor (Requirements Officer); and,

(l) User representatives, as appropriate;

(2) Technical Warrant Holders and Certificate Holders as required addressing system concepts and enabling technologies.  These Technical Warrant Holders represent their NAVAIR competencies in the adjudication of RFAs, to include cost and schedule impacts.  These need to include Certificate Holders for any planned Flight Clearance actions, if applicable.  These assignments should be coordinated with AIR-4.0P.  Certificate Holders should be notified at least 30 days prior to the scheduled review date.

(3) Developmental Testing (DT) personnel;

(4) Operational Testing (OT) personnel; and,

(5) IPT Briefers in accordance with the SRR-I agenda.

e.  Location – The facility chosen should be adequate to ensure complete participation by all cognizant competencies and organizations.  The SRR-I is typically conducted at a contractor or government provided facility, as mutually agreed upon, or specified in the contract.  The facility must be able to support a meeting at the appropriate classification level to ensure effective information exchange and to address maturity of the system to enter system functional requirements development.  The intent is to minimize travel and travel costs.

5.  Conduct of SRR-I Review - All TRB participants are to assess the materials at the review, document concerns by means of RFAs, and submit RFAs to the TRB Recorder.

a.  SRR-I Review Elements:

(1) Introduction/agenda/administrative:

(a) Purpose of review;

(b) RFA procedures overview;

(c) Risk Assessment procedures overview; and,

(d) Program Overview.

(2) Requirements Briefing:

(a) Proposed Organizational Structure;

(b) Requirements traceability, methodology, completeness;

(c) KPPs, MOPs, and MOEs;

(d) Verification/Certification requirements;

(e) Representative DT/OT Missions;

(f) Design Decomposition/System Concept;

(g) Interoperability;

(h) Software;

(i) Logistics/Manpower requirements;

(j) Training requirements;

(k) Schedule/Budget;

(l) Resource requirements estimates to support SDD;

(m) Risk Plan/Risks/Mitigation;

(n) SRR Checklist (as completed before the review); and,

(o) Measurement Plan.

b.  SRR-I Products:

(1) Technical Review Summary Report, with the following attachments:

(a) List of attendees, to include: name, functional area represented, NAVAIR code, phone number, and email address;

(b) Final Presentations;

(c) Updated risks and mitigation plans;

(d) Completed RFA forms;

(e) SRR Checklist (as completed following the review); and,

(f) Meeting minutes.

6.  SRR-I Completion - The SRR-I is considered complete when all draft RFAs are signed off, and an acceptable level of program risk is ascertained.  After the RFAs are closed, the system APMSE shall prepare a letter for the TRB Chairperson formally closing the review.  An SRR-I data package shall be prepared containing the products of the review and the closure letter, and submitted to the AIR-4.1 SETR archival database.

System Requirements Review - II

1.  SRR-II Purpose - SRR-II is a technical assessment of the developing system specification under review to ensure a reasonable expectation of the final system being judged operationally effective and suitable.  This review builds on the specification developed in SRR-I, Tier 1 of the System Design Specification (SDS), establishing thresholds for tailorable requirements.  This review ensures the contractor(s) understand that the requirements of the contract including the system specification, SOW, CDD, DoD Directives, statutory and regulatory guidance, and applicable public law has been correctly and completely represented in the system specification and can be developed within program cost and schedule constraints.  The understanding of requirements and verification procedures will be characterized in a technical risk assessment representing the ability of the contractor to comply with the system specification.  The ability to achieve the capabilities specified in the CDD within the program budget and schedule will be characterized in a program execution risk assessment.  Once the program risk has been identified, PMs can construct an acquisition plan for the SDD Phase with realistic resource and schedule requirements.

Tailorable, derived, and correlated requirements are established within the framework of a candidate physical architecture and fully derived functional segments.  To support a complete understanding of the specific design, cost, and schedule balancing of Tailorable requirements, a segmented functional architecture is finalized and documented.

A successful review is predicated on the IPT’s determination that the system performance requirements, non-tailorable design requirements, tailorable design requirements, available technology, and program resources (funding, schedule, staffing, and processes) are understood and will support further definition of the system architecture.

The review may be tailored to the technical scope of the system.  Under no circumstances should the review be tailored completely out of the development plan.  The TRB Chairperson, who is independent of the program team and a representative of AIR-4.1, shall ensure that the details of any tailoring result in a complete evaluation of the system under review and fully characterizes the risk to successful execution.

Successful completion of either SRR-II does not represent concurrence from the procuring authority that future design maturity will result in acceptable system performance.  SRR-II, as a component of the SETR process, serves as technical monitoring of program execution by senior functional area experts.  The contractor(s) remains responsible for the system design/performance requirements within the terms of the contract.

2.  SRR-II Timing - SRR–II is typically conducted three to six months after multiple contractors have been engaged during the TD Phase award.  SRR-I will have been conducted prior to this review to identify threshold requirements aligned to the draft CDD.  SRR-II is the initial technical review engaging contractors and sub-contractors teams to establish a baseline reference of threshold requirements, CONOPS for the proposed system, and areas of tailorable requirement for further definition to end the TD Phase and develop prototype architecture for the system.  SRR-II will also support a realistic evaluation of the requirements in the CDD prior to approval and release at MS B.  SRR-II should not be scheduled at a particular number of months after contract award; rather, it should occur relative to the maturity of the system technical baseline as described above.

3.  SRR-II Entry Criteria

a.  System Requirements and Capabilities:

(1) SDS, Tier 1, complete;

(2) Tier 1 SDS expanded to include tailorable, derived, and correlated requirements;

(3) Traceability from CDD to all system specifications;

(4) Completely derived functional segment specifications;

(5) Inter-segment control specifications complete;

(6) Preliminary physical system description;

(7) Approved Integrated Architecture views; and,

(8) Approved Set of Information Assurance Controls.

b.  Test, Evaluation, and Certification of Product:

(1) M&S role in testing identified;

(2) Airworthiness criteria, in accordance with the most current directives, such as NAVAIRINST 13034.1C (Flight Clearance Policy for Air Vehicles and Aircraft Systems) and MIL-HDBK-516 (DoD Airworthiness Certification Criteria), understood;

(3) Draft Verification and Validation (V&V) Methodology defined for each Specification Requirement;

(4) Draft Engineering Data Requirements Agreement Plan (EDRAP) to support Airworthiness Certification;

(5) All Certifying Agencies defined and requirements understood;

(6) Draft TEMP updated, as required; and,

(7) Updated requirement verification methodology detailing the type of analyses, test, inspection, or demonstrations planned.

c.  Engineering Processes, Control, and Analysis:

(1) MOEs defined;

(2) MOPs defined;

(3) KPPs defined;

(4) Critical Safety Items (CSIs)/Safety critical software identification understood;

(5) SEP updated after contract award and contractor Systems Engineering Management Plan (SEMP) complete;

(6) Updated SDP; and,

(7) All systems and subsystems at the TRL identified; Draft TRA Procedures established in preparation for MS B.

d.  Programmatic Processes, Control, and Analysis:

(1) CARD updated as required;

(2) PPP complete;

(3) RMP complete;

(4) CM Plan complete;

(5) Manufacturing and Production strategy;

(6) M&S plan for lifecycle support including training devices, tactics, air vehicle, mission system etc.;

(7) IDE procedures defined;

(8) Methodology for evaluating Life Cycle Cost established;

(9) CDRL and data requirements updated and approved in accordance with the most current policy, NAVAIRINST 4200.21D; and,

(10) Measurement Plan Complete.

e.  Program Master Schedule, Earned Value, Cost:

(1) Integrated government/contractor IMS is resourced at reasonable levels with realistic performance expectations;

(2) Functional IPT ownership of IMS established; and,

(3) Criteria for assigning, crediting, and establishing earned value is complete.

f.  Program Execution Risk and Performance Risk:

(1) Program technical risks identified; and,

(2) Program execution risks identified.

4.  SRR-II Planning

a.  TRB Chairperson – Planning for a technical review should start at least 90 days prior to the review.  Technical working groups in all functional areas should begin in preparation for the SRR-II.  A request for a TRB Chairperson should occur at least 90 days prior to conduct of the review.  Typically the PMA, assigned IPT leader, or assigned APMSE requests a TRB chairperson who is independent of the program team be appointed by AIR-4.1.  Prior to this request, the assigned APMSE should have coordinated chairperson requirements with the cognizant APEO(E).  Chairperson assignments should be reflective of program scope and risk.  For software-only SRRs, AIR-4.1 still approves the appointment of the TRB Chairperson from the NAVAIR Software (AIR-4.1) organization.  The role of the chairperson includes:

(1) Determination of TRB membership;

(2) Approval authority for tailoring of checklist review items;

(3) Identifies elements for in depth review as required;

(4) Development of the final review elements;

(5) Oversight of the technical review and RFA process; and,

(6) Issuance of the Technical Review Summary Report.

b.  Technical Review Build-Up TIMs – The APMSE should establish subsystem TIMs to review design readiness for SRR-II, establish completeness of documentation, adjudicate design disagreements, and prepare SRR-II presentation material.  These TIMs, usually begin at least 60 days prior to the SRR-II and are used to prepare the TRB membership for a successful review.  The TRB provides independent oversight of the design and is not the designing activity. Problem resolution should be completed during the build-up TIMs.

c.  Technical Review Elements – The APMSE and the assigned Chairperson shall coordinate with the cognizant APEO(E) in the development of a preliminary agenda for the planned review.  A sample review agenda is shown below in paragraph 5.a.  This agenda should be made available to the IPT at least 30 days prior to conduct of the review.

d.  Technical Review Participants:

(1) TRB (typical composition):

(a) TRB Chairperson;

(b) PM Representatives (Industry and Government); and,

(c) APMSE, who should:

1.  Ensure the performing activity provides the supporting data and participation in the required review;

2.  Develop, coordinate, and execute, in cooperation with the performing activity, individual review arrangements;

3.  Ensure the preparation of SRR-II material is coordinated across IPTs;

4.  Participate in the review;

5.  Organize and supervise the documentation of  RFAs in support of the TRB Chairperson; and,

6.  Obtain concurrence between government and contractor SMEs on requirements decomposition.

(d) Warfare Analyst SMEs, to ensure that all capability, operational effectiveness are addressed;

(e) APML, who should ensure all relevant supportability requirements are addressed;

(f) Cost Team (AIR-4.2) representative;

(g) Software (AIR-4.1) representative;

(h) Counsel, if required;

(i) Contracting Officer;

(j) Recorder, who is responsible for collating RFAs for submission to the TRB and recording of the minutes of the SRR-II.  The recorder should have the Technical Review Report prepared for distribution by the Chairperson;

(k) Resource Sponsor (Requirements Officer); and,

(l) User representatives, as appropriate

(2) Technical Warrant Holders and Certificate Holders as required addressing system concepts and enabling technologies.  These Technical Warrant Holders represent their NAVAIR competencies in the adjudication of RFAs, to include cost and schedule impacts.  These need to include Certificate Holders for any planned Flight Clearance actions, if applicable.  These assignments should be coordinated with AIR-4.0P.  Certificate Holders should be notified at least 30 days prior to the scheduled review date.

(3) DT and OT personnel; and,

(4) IPT Briefers in accordance with the SRR-II agenda.

e.  Location – The facility chosen should be adequate to ensure complete participation by all cognizant competencies and organizations.  The SRR-II is typically conducted at a contractor or government provided facility, as mutually agreed upon, or specified in the contract.  The facility must be able to support a meeting at the appropriate classification level to ensure effective information exchange and to address maturity of the system to enter system functional requirements development.  The intent is to minimize travel and travel costs.

5.  Conduct of SRR-II Review - All TRB participants are to assess the materials at the review, document concerns by means of RFAs, and submit RFAs to the TRB Recorder.

a.  SRR-II Review Elements:

(1) Introduction/agenda/administrative:

(a) Purpose of review;

(b) RFA procedures overview;

(c) Risk Assessment procedures overview; and,

(d) Program Overview.

(2) Requirements Briefing:

(a) Proposed Organizational Structure;

(b) Requirements traceability, methodology, completeness;

(c) KPPs, MOPs, and MOEs;

(d) Verification/Certification requirements;

(e) Representative DT/OT Missions;

(f) Design Decomposition/System Concept;

(g) Interoperability;

(h) Software;

(i) Logistics/Manpower requirements;

(j) Training requirements;

(k) Schedule/Budget;

(l) Resource requirements estimate to support SDD;

(m) Risk Plan/Risks/Mitigation;

(n) SRR Checklist (as completed before the review); and,

(o) Measurement Plan.

b.  SRR-II Products:

(1) Technical Review Summary Report, with the following attachments:

(a) List of attendees, to include; name, functional area represented, NAVAIR code, phone number, and email address;

(b) Final Presentations;

(c) Updated risks and mitigation plans;

(d) Completed RFA forms;

(e) SRR Checklist (as completed following the review); and,

(f) Meeting minutes.

6.  SRR-II Completion - The SRR-II is considered complete when all draft RFAs are signed off, and an acceptable level of program risk is ascertained.  After the RFAs are closed, the system APMSE shall prepare a letter for the TRB Chairperson formally closing the review.  An SRR-II data package shall be prepared containing the products of the review and the closure letter, and submitted to the AIR-4.1 SETR archival database.

System Functional Review

1.  SFR Purpose - The SFR is a technical assessment establishing the system functional baseline of the system under review to ensure a reasonable expectation of being judged operationally effective and suitable.  This review assesses the decomposition of the system specification to subsystem functional specifications derived from use case analysis.  A critical component of this review is the development of representative operational use cases for the system.  The anticipated functional requirements for operations and maintenance are assigned to subsystems, hardware, software, or support after detailed reviews of the architecture in the environment it will be employed.  The SFR determines whether the systems functional definition is fully decomposed to its lower level, and that the IPT can complete system architecting in preparation for preliminary design.

The system’s lower level performance requirements are evaluated to determine whether they are fully defined and consistent with the mature system concept, and whether traceability of lower-level systems requirements to top-level system performance and the CDD is maintained.  The SFR is the first review which begins to allocate requirements to separated subsystems and organizational IPTs.  As such, it is also the first review where the need for Interface Design Documents becomes necessary to define areas of responsibility and constraints requiring coordination across IPTs.  Interface Design Documents describe and document criteria for developing interfaces between the subsystem segments.  They do not reach the level of Interface Control Documents which are achieved at PDR-II.  A successful review is predicated on the IPT’s determination that the system performance requirements, lower level performance requirements and plans for design and development form a satisfactory basis for proceeding into preliminary design.

The review may be tailored to the technical scope of the system.  Under no circumstances should the review be tailored completely out of the development plan.  The TRB Chairperson, who is independent of the program team and a representative of AIR-4.1, shall ensure that the details of any tailoring result in a complete evaluation of the system under review and fully characterizes the risk to successful execution.  The SFR has importance as the last review that ensures that the system is credible and feasible before more technical design work commences.

Successful completion of the SFR does not represent concurrence from the procuring authority that future design maturity will result in acceptable system performance.  The SFR, as a component of the SETR process, serves as technical monitoring of program execution by senior functional area experts.  The contractor remains responsible for the system design/performance requirements within the terms of the contract.

2.  SFR Timing - The SFR is typically the last review of the TD Phase, following full system functional definition, completion of preliminary functional baseline documentation, and prior to preliminary design activity.  The SFR should not be scheduled at a particular number of months after contract award; rather, SFR should occur relative to the maturity of the system technical baseline as described above.

3.  SFR Entry Criteria

a.  System Requirements and Capabilities:

(1) System functional specification to subsystem level complete;

(2) Use case analysis complete;

(3) Completeness of specification, derived, correlated requirements evaluated;

(4) Requirements trace from CDD to system specification, functional specification, and subsystems specifications;

(5) Preliminary subsystem specification and Interface Design Documents complete;

(6) Functional requirements for operations and maintenance are assigned to subsystems, hardware, software, or support after detailed reviews of the architecture;

(7) Information Assurance Controls allocated to system components

(8) Training requirements identified in system and subsystem specifications; and,

(9) Logistics requirements identified in system and subsystem specifications

b.  Test, Evaluation, and Certification of Product:

(1) Functional Requirements assigned to M&S;

(2) Airworthiness criteria traceability;

(3) EDRAP to support Airworthiness Certification;

(4) Functional Requirements assigned to Certifying Agencies; and,

(5) Draft Software Test Plan, if not a software-intensive program (and no SSR is planned).

c. Engineering Processes, Control, and Analysis:

(1) Preliminary Technical Performance Measurements (TPMs) identified and traceable to Measures of Effectiveness (MOEs) and Measures of Performance (MOPs);

(2) Functionality assigned to KPPs;

(3) Updated Integrated Architecture System and Technical Views;

(4) Verification & Validation Methodology Defined for each Specification Requirement;

(5) CSIs identification understood;

(6) SEP updated;

(7) Updated SDP; and,

(8) Current technology maturation plans exist for identified CTEs

d.  Programmatic Processes, Control, and Analysis:

(1) CARD updated as required;

(2) CPI Identified;

(3) Program Protection Implementation Plan (PPIP) derived from PPP and CPIs;

(4) Risk Management Program Fully Functioning;

(5) CM Board Established and Functioning;

(6) IDE Functioning; and,

(7) Measurement Program Fully Functioning.

e.  Program Master Schedule, Earned Value, Cost:

(1) IMS is resourced at reasonable levels with realistic performance expectations;

(2) IBR has been held or will be held prior to PDR; and,

(3) Criteria for assigning, crediting, and establishing earned value is complete.

f.  Program Execution Risk and Performance Risk:

(1) Program Technical risks identified; and,

(2) Program Execution risks identified.

4.  SFR Planning

a.  TRB Chairperson – Planning for a technical review should start at least 90 days prior to the review.  Technical working groups in all functional areas should begin in preparation for the SFR.  A request for a TRB Chairperson who is independent of the program team should occur at least 90 days prior to conduct of the review.  Typically the PMA, assigned IPT leader, or assigned APMSE requests a TRB chairperson be appointed by AIR-4.1.  Prior to this request, the assigned APMSE should have coordinated chairperson requirements with the cognizant APEO(E).  Chairperson assignments should be reflective of program scope and risk.  The role of the chairperson includes:

(1) Determination of TRB membership;

(2) Approval authority for tailoring of checklist review items;

(3) Identifies elements for in depth review as required;

(4) Development of the final review elements;

(5) Oversight of the technical review and RFA process; and,

(6) Issuance of the Technical Review Summary Report.

b.  Technical Review Build-Up TIMs – The APMSE should establish subsystem TIMs to review design readiness for SFR, establish completeness of documentation, adjudicate design disagreements, and prepare SFR presentation material.  These TIMs, usually begin at least 60 days prior to the SFR and are used to prepare the TRB membership for a successful review.  The TRB provides independent oversight of the design and is not the designing activity.  Problem resolution should be completed during the build-up TIMs.

c.  Technical Review Elements – The APMSE and the assigned Chairperson shall coordinate with the cognizant APEO(E) in the development of a preliminary agenda for the planned review.  A sample review agenda is shown below in paragraph 5.a.  This agenda should be made available to the IPT 30 days prior to conduct of the review.

d.  Technical Review Participants:

(1) TRB (typical composition):

(a) TRB Chairperson;

(b) PM Representatives (Industry and Government); and,

(c) APMSE, who should;

1. Ensure the performing activity provides the supporting data and participation in the required review;

2. Develop, coordinate, and execute, in cooperation with the performing activity, individual review arrangements;

3. Ensure the preparation of SFR material is coordinated across IPTs;

4. Participate in the review;

5. Organize and supervise the documentation of RFAs in support of the TRB Chairperson; and,

6. Obtain concurrence between government and contractor SMEs on requirements decomposition

(d) The APML, who should ensure all relevant supportability requirements are addressed;

(e) Warfare Analysts, who ensure all capability, operational effectiveness, and capability are addressed;

(f) Cost Team (AIR-4.2) representative;

(g) Software (AIR-4.1) Representative;

(h) Counsel, if required;

(i) Contracting Officer;

(j) Recorder; who is responsible for collating RFAs for submission to the TRB and recording of the minutes of the SFR.  The recorder should have the Technical Review Report prepared for distribution by the Chairperson;

(k) Resource Sponsor (Requirements Officer); and

(l) User representatives.

(2) Technical Warrant Holders and Certificate Holders as required addressing system concepts and enabling technologies.  These Technical Warrant Holders represent their NAVAIR competencies in the adjudication of RFAs, to include cost and schedule impacts.  These need to include Certificate Holders for any planned Flight Clearance actions, if applicable.  These assignments should be coordinated with AIR-4.0P.  Certificate Holders should be notified at least 30 days prior to the scheduled review date.

(3) DT/OT personnel; and,

(4) IPT briefers in accordance with the SFR agenda.

e.  SFR Location – The facility chosen should be adequate to ensure complete participation by all required competencies and organizations.  The SFR is typically conducted at a contractor or government provided facility, as mutually agreed upon, or specified in the contract.  The facility should support classified discussions at the appropriate level for a complete system review.  The intent is to minimize travel and travel costs.

5.  Conduct of SFR Review - All TRB participants are to assess the materials at the review, document concerns by means of RFAs, and submit RFAs to the TRB Recorder.

a.  SFR Review Elements:

(1) Introduction/agenda/administrative:

(a) Purpose of Review;

(b) RFA Procedures Overview;

(c) Risk Assessment Procedures Overview; and,

(d) Program Overview.

(2) Detailed review of total system, subsystems, and logistics elements:

(a) Design Overview;

(b) Use Case Analysis and alignment to enterprise architectures;

(c) Functional Requirements Trace and Completeness;

(d) Software/System Architecture;

(e) Measurement Data;

(f) Allocated Baselines;

(g) Sufficiency of Design; and,

(h) Test and Certification Requirements.

b.  Products:

(1) Technical Review Summary Report, with the following attachments:

(a) List of attendees, to include: name, functional area represented, NAVAIR code, phone number, and email address;

(b) Final Presentations;

(c) Updated risk assessment with mitigation plans;

(d) Completed RFA forms;

(e) Meeting minutes; and,

(f) Recommendation to PMA on the probability the system will be judged operationally effective and suitable

(2) Completed SFR checklist.

6.  SFR Completion - The SFR is considered complete when all draft RFAs are signed off, and an acceptable level of program risk is ascertained.  After the RFAs are closed, the system APMSE shall prepare a letter for the TRB Chairperson formally closing the review.  An SFR data package shall be prepared containing the products of the review and the closure letter, and submitted to the AIR-4.1 SETR archival database.

Software Specification Review

1.  SSR Purpose - The SSR is a technical assessment establishing the software requirements baseline of the system under review to ensure the preliminary design and ultimately the software solution has a reasonable expectation of being judged operationally effective and suitable.  The SSR is a review of the finalized Computer Software Configuration Item (CSCI) requirements and operational concept. The SSR is conducted when CSCI requirements have been sufficiently defined to evaluate the developer’s interpretation of the system, subsystem, or prime item level requirements described in the performance-based specification or System Requirements Specification (SRS). A successful SSR is predicated upon the acquirer’s determination that the Software Requirements Specification (SwRS) or Software Requirements Description (SRD); Interface Requirements Specification(s) (IRS) or Software Interface Requirements Description (SIRD); Software Integration Plan; and the user’s CONOPS Description or User Documentation Description form a satisfactory basis for proceeding into preliminary software design.  The SSR determines whether the software requirements are fully decomposed to the lowest level, and that the IPT is prepared to start software preliminary design.  At this point requirements have become stable and requirements changes shall only be made through a formal change (document control board) review process with the approval based on a thorough understanding of the cost, schedule and technical performance impacts, and resources to implement the change.

The software’s lower level performance requirements are evaluated to determine whether they are fully defined and consistent with a mature system concept, and whether traceability of lower-level software requirements to top-level system performance and the CDD is maintained.  The SSR is the first software review where the interaction between hardware items described in the Interface Control Documents becomes necessary and requires consistency between the hardware and the software.  During this review the SwRS or SRD is baselined to enable beginning design.  A draft Software Test Plan is presented to enable scheduling of test facilities and to ensure availability of test resources and tools.  A successful review is predicated on the acquirer’s determination that the software performance requirements, lower level software requirements, software interface requirements, and system level architectural analysis form a satisfactory basis for proceeding into preliminary software design.

The review may be tailored to the technical scope of the system.  Under no circumstances should the review be tailored completely out of the development plan for software-intensive systems or software-only changes to a system.  The SSR TRB Chairperson, who is independent of the program team and a representative of NAVAIR AIR-4.1, shall ensure that the details of any tailoring result in a complete evaluation of the software under review and fully characterizes the risk to successful execution.  The SSR has importance as the last review that ensures that the system is credible and feasible before software design work commences.  Acquisition programs with an incremental development approach are required to conduct an SSR for each increment.

Successful completion of the SSR does not represent concurrence from the acquirer that future software design maturity will result in acceptable software performance.  The SSR, as a component of the SETR process, serves as technical monitoring of program execution by senior functional area experts.  The developer remains responsible for the system software performance requirements within the terms of the contract or work assignment agreement.

2.  SSR Timing - The SSR, typically conducted early in the SDD phase, will occur between the System Functional Review (SFR) and the system PDR, following full system functional definition at SFR.  Scheduling the SFR, SSR, and PDR within a few months of each other severely constrains resources.  Ideally, the SSR can be conducted as a buildup review to PDR.  If it is conducted as a stand alone review, consideration should be given to a reduced TRB focusing on software, with full TRB follow up at PDR.  The content requirements of the SSR are prerequisites for the system PDR.  The SSR should not be scheduled at a particular number of months after contract award; rather, the SSR should occur relative to the maturity of the software requirements baseline as described above.

It is assumed that all prerequisites have been met and the program is post-MS B.  The TRL is at least level 6 and TRA planning has begun.  SRR and SFR actions have been closed out prior to the SSR.  All acquisition documentation has been completed or updated prior to the SSR.  If an incremental development approach is used on this acquisition program then the acquisition documents will only need to be completed for this increment.  Any changes to the requirements since the SFR will be noted during the SSR.

3.  SSR Entry Criteria

a.  Software Requirements and Capabilities:

(1) SwRS or SRD is complete;

(2) Completeness of specification, derived, correlated requirements applicable to the software have been evaluated;

(3) Requirements traceability from CDD, systems specifications, and subsystems specifications to SRS or SRD to SwRS has been verified;

(4) Interface Control Documents and IRS or SIRD completed;

(5) Declassification, Anti-Tamper, Open Architecture, and Information Assurance implementation defined; and,

(6) Logistics requirements identified in the SRS or SRD.

b.  Test, Evaluation, and Certification of Product:

(1) Software Requirements assigned to M&S;

(2) Requirements Verification Matrix, preferably the output of a Requirements Management Tool completed;

(3) Airworthiness criteria defined;

(4) Draft Software Test Plan completed;

(5) Software Engineering Environment defined;

(6) Draft Software Integration Plan completed; and,

(7) TEMP updated, as required.

c.  Engineering Processes, Control, and Analysis:

(1) CSIs/Safety critical software identified;

(2) Software criticality for each CSCI understood;

(3) SDP updated, as required;

(4) Software Safety Program defined and integrated; and,

(5) Quality Assurance Plan updated, as required.

d.  Programmatic Processes, Control, and Analysis:

(1) CPI identified;

(2) MOPs and TPMs;

(3) Risk Management Program;

(4) Measurement Program;

(5) CM Board;

(6) IDE;

(7) Changes to requirements or architecture since SFR; and,

(8) Software Management Plan updated, as required.

e.  Program Master Schedule, Earned Value, Cost:

(1) Software Management Plan updated, as required;

(2) Software schedule is integrated into the IMS with critical path and dependencies identified; and,

(3) EVM or equivalent is complete

f.  Program Execution Risk and Performance Risk:

(1) Software Technical Risks and Mitigation Plans; and,

(2) Software Execution Risks and Mitigation Plans

4.  SSR Planning

a.  TRB Chairperson – Planning for the SSR review should start 90 days prior to the review and can be done in conjunction with planning for the PDR.  Technical working groups in all functional areas should begin in preparation for the SSR.  A request for a TRB Chairperson who is independent of the program team should occur 45 days prior to conduct of the review.  Typically the PMA, assigned IPT leader, or assigned Software Lead requests a TRB chairperson be appointed by AIR-4.1.  Prior to this request, the assigned Software Lead should have coordinated chairperson requirements with the cognizant APMSE and APEO(E).  Chairperson assignments should be reflective of program scope and risk.  The role of the chairperson includes:

(1) Determination of TRB membership;

(2) Approval authority for tailoring of checklist review items;

(3) Identifies elements for in depth review as required;

(4) Development of the final review elements;

(5) Oversight of the technical review and RFA process; and,

(6) Issuance of the Technical Review Summary Report

b.  Technical Review Build-Up TIMs – The Software Lead should establish subsystem TIMs to review requirements maturity and readiness for SSR, establish completeness of documentation, adjudicate requirements disagreements, and ensure SSR presentation material represents the status of the software effort.  These TIMs, usually begin at least 60 days prior to the SSR and are used to prepare the TRB membership for a successful review.  The TRB provides independent oversight of the requirements development. Problem resolution should be completed during the build-up TIMs.

c.  Technical Review Elements – The Software Lead and the assigned Chairperson shall coordinate with the cognizant APMSE and APEO(E) in the development of a preliminary agenda for the planned review.  This agenda should be made available to the IPT 30 days prior to conduct of the review.

d.  Technical Review Participants:

(1) TRB (typical composition):

(a) TRB Chairperson;

(b) Software (AIR-4.1) Representative;

(c) Software PM Representatives (Industry and/or Government); and,

(d) Software Lead, who should;

1. Ensure the performing activity provides the supporting data and participation in the required review;

2. Develop, coordinate, and execute, in cooperation with the performing activity, individual review arrangements;

3. Ensure the preparation of SSR material is coordinated within the software team and across IPTs;

4. Conduct the review for the TRB; and,

5. Organize and supervise the documentation of RFAs in support of the TRB Chairperson

(e) System/Software Safety, who should ensure all safety-critical requirements are identified and the System Safety Hazard Analysis is progressing;

(f) APML, who should ensure all relevant supportability requirements are addressed;

(g) APMT&E who should ensure all test requirements are addressed;

(h) Representatives from all certification authorities;

(i) Cost Team (AIR-4.2) representative;

(j) Counsel, if required;

(k) Contracting Officer;

(l) Recorder; who is responsible for collating RFAs for submission to the TRB.  The recorder should have the Technical Review Report prepared for distribution by the Chairperson;

(m) Resource Sponsor (Requirements Officer); and,

(n) User representatives.

(2) Technical Warrant Holders and Certificate Holders as required addressing system concepts and enabling technologies.  These Technical Warrant Holders represent their NAVAIR competencies in the adjudication of RFAs, to include cost and schedule impacts.  These need to include Certificate Holders for any planned Flight Clearance actions, if applicable.  These assignments should be coordinated with AIR-4.0P.  Certificate Holders should be notified at least 30 days prior to the scheduled review date.

(3) IPT briefer in accordance with the SSR agenda.

e.  Location – The facility chosen should be adequate to ensure complete participation by all required competencies and organizations.  The SSR is typically conducted at a developer’s facility, as mutually agreed upon, or specified in the contract or work assignment agreement.  The facility should support classified discussions at the appropriate level for a complete software requirements review.  The intent is to minimize travel and travel costs.

5.  Conduct of the SSR Review - All TRB participants are to assess the materials at the review, document concerns by means of RFAs, and submit RFAs to the TRB Recorder.

a.  SSR Review Elements:

(1) Introduction/agenda/administrative:

(a) Purpose of Review;

(b) RFA Procedures Overview; and,

(c) Risk Assessment Procedures Overview.

(2) Software Program Overview:

(a) Schedule;

(b) Measures (Metrics);

(c) Software Risks;

(d) Software Life Cycle Support Concept; and,

(e) Changes to requirements or architecture since SFR.

(3) Detailed review software requirements:

(a) Functional overview of the CSCI, including inputs, processing, and outputs of each function;

(b) Overall CSCI performance requirements, including those for execution time, storage requirements, and similar constraints;

(c) Architectural overview of System and CSCIs;

(d) Expected Software Criticality Levels for each CSCI;

(e) Expected classification levels of CSCIs and declassification requirements;

(f) All interface requirements between the CSCI and all other configuration items (CIs) both internal and external to the system;

(g) Test Verification Matrix that identifies applicable levels and methods of testing for the software requirements that comprise the CSCI;

(h) Any special delivery requirements for the CSCI;

(i) Mission requirements of the system and associated operational and support environments; and,

(j) Functions and characteristics of the computer system within the overall system.

(4) Status of Facilities, Tools, Models, and Simulations; and,

(5) Test Planning.

b.  Products:

(1) Technical Review Summary Report, with the following attachments:

(a) List of attendees, to include: name, functional area represented, NAVAIR code, phone number, and email address;

(b) Final Presentations;

(c) Updated risk assessment with mitigation plans;

(d) Measures (Metrics);

(e) Completed RFA forms;

(f) Meeting minutes; and,

(g) Recommendation to PMA on the probability the system will be judged operationally effective and suitable

(2) Completed SSR checklist associated with this instruction

6.  SSR Completion - The SSR is considered complete when all draft RFAs are signed off, and an acceptable level of program risk is ascertained.  After the RFAs are closed, the Software Lead shall prepare a letter for the TRB Chairperson formally closing the review.  An SSR data package shall be prepared containing the products of the review and the closure letter, and submitted to the AIR-4.1 SETR archival database.

Preliminary Design Review

1.  PDR Purpose - PDR is a technical assessment establishing the complete physically allocated baseline to ensure that the system under review has a reasonable expectation of being judged operationally effective and suitable.  This review represents a physically architected system, preliminary detailed design by sub-system suppliers, and critical technologies matured to TRL 6 during the TD Phase prior to MS B.  System level analysis is preformed to support evaluating the breadth of the design.  Preliminary detail design is accomplished for all sub-systems to mature Interface Design Documents to Interface Control Documents which facilitate complete detailed design culminating in a CDR.

This review assesses the allocated design captured in sub-system and component (Weapon Replacement Assembly) product specifications for each configuration item in the system and ensure that each function, in the functional baseline, has been allocated to one or more system configuration items.  This review also ensures that the physical properties of the system (i.e. weight, power, cooling, Center-of-Gravity, etc) have been properly allocated to sub-systems and components in accordance with acceptable design growth margins and analysis.  Sub-system specifications for hardware and software, along with associated Interface Control Documents, enable detailed design or procurement of sub-systems.  Configuration items may consist of hardware and software elements, and include items such as airframe, avionics, weapons, crew systems, engines, trainers/training, etc.  System level analysis is preformed to characterize the compliance of system level attributes such as safety, interoperability, security, and mass properties comply with requirements.  System level analysis is supported by preliminary drawings, not yet build drawings, that are detailed enough to support analysis of the allocated physical attributes, interactions with loads and environment, and system level properties.

The sub-system requirements are evaluated to determine whether they correctly and completely satisfy all system requirements, and whether traceability of sub-system requirements to system design is maintained.  At this point requirements have become stable and requirements changes shall only be made through a formal change review process with the approval based on a thorough understanding of the cost, schedule and technical performance impacts, and resources to implement the change.  After this review, hardware and software enters detailed design by focused engineering teams.  System level coordination and problem resolution becomes more difficult as sub-system teams proceed within the bounds of their Interface Control Documents.  Cross sub-system communication is initiated when the teams identify compliance risks to the ICDs.  Therefore, incorrect interface requirements or conflicting interpretations by design groups on either side of the Interface Control Documents may continue until CDR.  If the sub-systems are individually procured through subcontracts, communication is additionally constrained.  Corrections to these ICDs will result in a contractual action to modify procured product baselines.  As the system passes through PDR, any sub-system inconsistencies will, most likely, be implemented in the hardware configuration.  The top level Software Design Description developed during preliminary design will become the basis for the Detailed Software Design Description to be completed by CDR.

For complex systems, a PDR may be conducted for each sub-system and logistics element.  These incremental reviews, usually defined at Interface Control Documents boundaries, lead to an overall system PDR.  System level performance is supported by compliance with Interface Control Documents, but not assured.  Each incremental PDR results in a further understanding of the sub-system under review and leads to a modification or clarification of the allocations captured in the ICDs.  Sub-systems which have already completed an incremental PDR may need to be reopened if remaining sub-systems cannot achieve desired performance in isolation.  If schedule is being preserved through parallel design decisions, any system deficiencies that lead to reopening design will result in rework and earned value adjustments.  However, it is important to clarify and resolve design conflicts prior to completing the PDR-II and entering detailed design.

If a complete PDR has not been conducted prior to Milestone B, the PM shall plan to accomplish a minimum subset of PDR requirements to support the development of the System Design Specification (SDS).  The SDS is approved at Gate 4 of the Acquisition Governance process established in SECNAVINST 5000.02D. A minimum MS-B preparatory PDR represents a physically architected system based on full engagement of sub-system suppliers and knowledge gained through prototyping CTEs identified in the Technology Development Strategy (TDS).  System level analysis is preformed to support evaluating the breadth of the design.  Limited detail design in the area of CTEs and stressing design areas is conducted to the extent necessary for architecting the system. Sub-system suppliers are engaged, but at a reduced level than normally required to support a full system PDR.  Sub-system PDRs are not conducted until after MS-B to support the complete system PDR post MS-B.

A minimum MS-B preparatory PDR assesses the allocated design captured in sub-system and component (Weapon Replacement Assembly) product specifications for each configuration item in the system and ensures that each function, in the functional baseline, has been allocated to one or more system configuration items.  This review also ensures that the physical properties of the system (i.e. weight, power, cooling, Center-of-Gravity, etc) have been properly allocated to sub-systems and components in accordance with acceptable design growth margins and analysis. Sub-system specifications for hardware and software, along with associated Interface Design Documents (IDDs), enable detailed design or procurement of sub-systems through the MS-B RFP.  Incorrect interface requirements or conflicting interpretations by design groups between sub-systems must be resolved prior to the complete PDR held post MS-B.  If the sub-systems are individually procured through subcontracts, communication is additionally constrained.  Corrections to these IDDs will result in a contractual action to modify procured product baselines.  Configuration items may consist of hardware and software elements, and include items such as airframe, avionics, weapons, crew systems, engines, trainers/training, etc.  System level analysis is preformed to characterize the compliance of system level attributes such as safety, interoperability, security, and mass properties comply with requirements.

For both types of PDRs a successful review is predicated on the IPT’s determination that the sub-system requirements, sub-system preliminary design, results of peer reviews, and plans for development and testing form a satisfactory basis for proceeding into detailed design and test procedure development.

The review may be tailored in accordance with the technical scope of the system.  Under no circumstances should the review be tailored completely out of the development plan.  Details of any tailoring should be described in the SEP.  The TRB Chairperson, who is independent of the program team and a representative of AIR-4.1, shall ensure that the details of any tailoring result in a complete evaluation of the system under review and fully characterizes the risk to successful execution.

2.  PDR Timing - When consistent with Technology Development (TD) phase objectives, associated prototyping activity, and the MDA approved TDS, the PM shall plan a Preliminary Design Review (PDR) before Milestone B.  PDR planning shall be reflected in the TDS and A Preliminary Design Review (PDR) shall be conducted for the candidate design(s) to establish the allocated baseline (hardware, software, human/support systems) and underlying architectures and to define a high-confidence design.  This review occurs after completion of system functional decomposition, baselining of software requirements, preliminary detailed design, and interface definition. In the case of a software-intensive system, the SSR shall have been completed.  A benchmark for requisite system maturity for PDR would be when all sub-systems are ready to release to design teams or subcontracting or when all requirements have been allocated to a top level design to enable detailed design to begin. All system elements (hardware and software) shall be at a level of maturity commensurate with the PDR entrance criteria.  A successful PDR will inform requirements trades; improve cost estimation; and identify remaining design, integration, and manufacturing risks.  The PDR shall be conducted at the system level and include user representatives and associated certification authorities. The PDR Report shall be provided to the MDA at Milestone B and include recommended requirements trades based upon an assessment of cost, schedule, and performance risk.

If a PDR has not been conducted prior to Milestone B, the PM shall plan for a PDR as soon as feasible after program initiation.  PDR planning shall be reflected in the Acquisition Strategy and conducted consistent with the policies specified in DODI 5000.02.  A tailored minimum MS-B preparatory PDR shall be conducted to support SDS development.  Following the complete post MS-B PDR, the PM shall plan and the MDA shall conduct a formal Post-PDR Assessment.  The PDR report shall be provided to the MDA prior to the assessment and reflect any requirements trades based upon the PM’s assessment of cost, schedule, and performance risk.  The MDA will consider the results of the PDR and the PM’s assessment, and determine whether remedial action is necessary to achieve APB objectives.  The results of the MDA's Post-PDR Assessment shall be documented in an Acquisition Decision Memorandum (ADM).

3.  PDR Entry Criteria

a.  System Requirements and Capabilities:

(1) Sub-system Design Specifications complete;

(2) CTEs have achieved TRL 6;

(3) IDDs matured through detailed design Interface Control Documents;

(4) Interface Control Documents between sub-systems complete;

(5) Traceability from CDD to function baseline to sub-systems specification complete;

(6) Human Systems Design Standards flowed to sub-systems;

(7) R&M diagnostics have been completely addressed in design allocations;

(8) Top Level Software Design Description and/or Software Architecture Description complete; and,

(9) Software IDD or equivalent complete.

b.  Test, Evaluation, and Certification of Product:

(1) Test Verification Matrix covers sub-system allocations;

(2) Traceability from design documentation to sub-system test requirements is complete;

(3) Engineering data requirements needed from testing identified and finalized;

(4) Critical Interface Control Documents interfaces identified in test requirements;

(5) Software CSU Test Plan complete and Test Procedures begun;

(6) Representative mission profiles finalized;

(7) Modeling and Simulation role in testing defined;

(8) Software Integration Plan complete; and,

(9) All certification plans have been approved by certifying agency.

c.  Engineering Processes, Control, and Analysis:

(1) All TPMs allocated to Interface Control Documents and sub-systems;

(2) System level analysis accomplished to show compliance with Safety, Security, Information Assurance, and Performance requirements;

(3) All KPPs, MOPs, and MOEs allocated to sub-systems;

(4) Data element identification procedures are established;

(5) Sub-system Hazard Analysis scheduled to support System Hazard Analysis;

(6) Sub-system R&M engineering analysis, FMECA scheduled to support System Hazard Analysis;

(7) CSIs identification process understood;

(8) Detailed design documentation required to support Training, and Modeling and Simulation identified;

(9) SEP updated as required; and,

(10) SDP updated as required.

d.  Programmatic Processes, Control, and Analysis:

(1) CARD updated as required;

(2) PPIP complete and requirements allocated to design;

(3) Subcontract strategy for sub-systems and Tier 2 Vendors;

(4) Logistics Element requirements allocated to design; and,

(5) Training requirements allocated to design.

e.  Program Master Schedule, Earned Value, Cost:

(1) IMS shows critical path through CDR; and,

(2) Earned Value supports PDR-II closure

f.  Program Execution Risk and Performance Risk:

(1) Program technical risks identified, and mitigation plans in place; and,

(2) Program execution risks identified, and mitigation plans in place.

4.  PDR Planning

a.  The TRB Chairperson – Planning for a technical review should start with a request for a TRB Chairperson who is independent of the program team, nominally 45 days prior to conduct of the review.  Typically the PMA, assigned IPT leader, or assigned APMSE requests a TRB chairperson be appointed by the NAVAIR Systems Engineering Department, AIR-4.1.  Prior to this request, the assigned APMSE should have coordinated chairperson requirements with the cognizant (APEO(E)).  Chairperson assignments should be reflective of program scope and risk.  The role of the chairperson includes:

(1) Determination of  TRB membership;

(2) Development of the final review elements;

(3) Oversight of the technical review and RFA process; and,

(4) Issuance of the Technical Review Summary Report

b.  Technical Review Build-Up TIMs – The APMSE should establish sub-system TIMs to review design readiness for PDR-II, establish completeness of documentation, adjudicate design disagreements, and prepare PDR-II presentation material.  These TIMs, referred to as sub-system PDR-IIs, usually begin at least 60 days prior to the PDR-II and are used to prepare the TRB membership for a successful review.  It is also recommended that a SRA following AIR-4.2 guidelines be included in each of these sub-system PDR-IIs.  The TRB provides independent oversight of the design and is not the designing activity.  Problem resolution should be completed during the build-up TIMs.

c.  Technical Review Elements – The APMSE and the assigned Chairperson shall coordinate with the system APEO(E) in the development of a preliminary agenda for the planned review.  This agenda should be made available to the IPT 30 days prior to conduct of the review.

d.  Technical Review Participants

(1) TRB (typical composition):

(a) TRB Chairperson

(b) Program Manager representatives (Industry and Government)

(c) APMSE, who should:

1. Ensure the performing activity provides the supporting data and participation in the required review.

2. Develop, coordinate, and execute, in cooperation with the performing activity, individual review arrangements.

3. Ensure the preparation of requirements performance material is coordinated across IPTs.

4. Conduct the review for the TRB.

5. Organize and supervise the documentation of RFAs in support of the TRB Chairperson.

(d) APML, who should ensure all relevant supportability requirements are addressed.

(e) APMT&E who should ensure all test requirements are addressed.

(f) Representatives from all certification authorities.

(g) Cost Team (AIR-4.2) representative.

(h) Software (AIR-4.1) representative.

(i) Counsel, if required.

(j) Contracting Officer.

(k) Recorder; who is responsible for collating RFAs for submission to the TRB.  The recorder should have the Technical Review Report prepared for distribution by the Chairperson.

(l) Resource Sponsor (Requirements Officer).

(m) User representatives.

(2) Technical Warrant Holders and Certificate Holders as required addressing system concepts and enabling technologies.  These Technical Warrant Holders represent their NAVAIR competencies in the adjudication of RFAs, to include cost and schedule impacts.  These need to include Certificate Holders for any planned Flight Clearance actions, if applicable.  These assignments should be coordinated with AIR-4.0P.  Certificate Holders should be notified at least 30 days prior to the scheduled review date.

(3) IPT briefer in accordance with the PDR-II agenda

e.  Location– The facility chosen should be adequate to ensure complete participation by all required competencies and organizations.  The PDR-II is typically conducted at a contractor or government provided facility, as mutually agreed upon, or specified in the contract.  The facility should support classified discussions at the appropriate level for a complete system review.  The intent is to minimize travel and travel costs.

5.  Conduct of PDR Review - All TRB participants are to assess the materials at the review, document concerns by means of RFAs, and submit RFAs to the TRB Recorder.

a.  PDR Review Elements:

(1) Introduction/agenda/administrative;

(a) Purpose of review;

(b) RFA procedures overview;

(c) Risk Assessment procedures overview; and,

(d) Program overview.

(2) Detailed review of total system, sub-systems, and logistics elements;

(a) Design Overview;

(b) Requirements Trace and Completeness;

(c) Allocated Baselines;

(d) Sufficiency of Design;

(e) Interface Control;

(f) Test and Certification Requirements;

(g) Measurement Data; and,

(h) Program Level Risks and Mitigation Plans for “red” risks

b.  Product - Technical Review Summary Report, with the following attachments:

(1) List of attendees, to include; name, functional area represented, NAVAIR code, phone number, and email address;

(2) Final presentations;

(3) Update risk assessment with mitigation plans;

(4) Completed RFA forms;

(5) Meeting minutes;

(6) Recommendation to PMA on the probability the system will be judged operationally effective and suitable; and,

(7) Completed PDR checklist with comments.

6.  PDR Completion – The PDR  is considered complete when all draft RFAs are signed off, and an acceptable level of program risk is ascertained.  After the RFAs are closed, the system APMSE shall prepare a letter for the TRB Chairperson formally closing the review.  A PDR data package shall be prepared containing the products of the review and the closure letter, and submitted to the AIR-4.1 SETR archival database.

Integrated Baseline Review

1.  IBR Purpose – The IBR is employed by PMs throughout the life of projects where Earned Value Management (EVM) is required.  The process is composed of four steps: (1) the PMs assessment of their understanding of the risks, (2) preparation for an IBR, (3) execution of the IBR, and (4) the management process (the source of on-going mutual understanding).  The key step in the process is execution of the IBR.  The IBR establishes a mutual understanding of the project Performance Management Baseline (PMB) and provides for an agreement on a plan of action to evaluate risks inherent in the PMB and the management processes that operate during project execution.

Completion of the review should result in the assessment of risk within the PMB and the degree to which the following have been established:

a.  Technical scope of work is fully included and is consistent with authorizing documents.  This should include full system focus, and in-depth integration, and software considerations, and CTE maturation plans;

b.  Project schedule key milestones are identified and supporting schedules reflect a logical flow to accomplish the work;

c.  Resources (budgets, facilities, personnel, skills, etc.) are available and are adequate for the assigned tasks;

d.  Tasks are planned and can be measured objectively relative to the technical progress;

e.  Rationales underlying the PMB are reasonable; and,

f.  Management processes support successful execution of the project.

2.  IBR Timing – The on-site portion of the IBR is normally conducted shortly after contract award.  After this initial IBR, PMs are encouraged to utilize the management process to maintain their understanding of risks.  However, changes to PMB over the life of a program are expected, and PMs must determine whether to perform an additional IBR or continue to rely on the management process to provide the necessary information relating to risk.  Changes in PMB risks may result from contract award, authorization to proceed, CTE maturation plans, contract modification, funding, replanning scope/schedule, new PM, acquisition plan, and higher-level authority direction.

3.  IBR Entry Criteria – Since the purpose of the IBR is to assess the PMB, the baseline must be established by the performing organization (Contractor or Government) and should reflect the entire scope of work documented at the appropriate level of detail before the formal IBR can be conducted.  The Program Teams must be familiar with the project scope of work, e.g., SOW or SOO, before the start of IBR.  There needs to be an understanding of management processes including management of subcontractors.

4.  IBR Planning – Preparation is the process step that establishes a foundation for a successful IBR.  A plan should be developed for conducting an IBR consistent with the PMs expectations and program dynamics.  Program dynamics that have an impact on PMB planning include changes in funding, scope of work, acquisition plan, subcontracting, key personnel, and any pending higher authority decisions.

Preparation for the IBR focuses on those risks that may impact the project PMB.  Risks include technical, schedule, cost, resource, or management processes.  The RMP is essential for identifying, analyzing, handling, monitoring, and documenting project risks.  The RMP provides the basis for iterative assessment and management of risk.

a.  PMs – PMs are responsible for the Baseline Review Process and for the following:

(1) Planning and executing the IBR;

(2) Providing an adequate number of qualified technical personnel to serve as the principal IBR team members, supplemented by members with applicable support skills (e.g., EVM specialists, subcontract managers, business managers, and finance managers);

(3) Documenting, in the RMP, risk issues identified during an IBR; and,

(4) Reviewing progress on the actions until issues are resolved.

b.  IBR Team Participants – PMs should select individuals for the IBR team who are experienced with the programmatic and technical disciplines under review.  When appropriate, subcontractor personnel should be included on the team.  Areas of discipline that should be included on the team are program management, business management, subcontract management, and technical management (e.g., system engineering, software engineering, manufacturing, integration and test engineering, and integrated logistics support).  The size and composition of the team should reflect the PMs objectives, expectations, and risk assumptions.

c.  Cost Department - While the PM is responsible for conducting the IBR, AIR-4.2 is the IBR SME for the Command, and provides for the facilitation of the review.  Additionally, AIR-4.2 provides training (in conjunction with the contractor or team site personnel where possible) for the review, and team members for the assessment.

d.  IBR Agenda – The IBR Team Handbook will assist the team members with how the review should be conducted.  Included in this handbook will be a description of the effort, layout of the team assignments, review agenda, discussion guidelines, travel arrangement details, sample documentation, sample discussion questions, risk evaluation criteria, and a glossary of terminology.

e.  IBR Training – Training is essential to ensure that the IBR team can identify and adequately assess the project risk.  The PMs should conduct joint training in which all members of the IBR team participate.  The training provides enough information so the team can mutually understand the cost, schedule, technical, and management processes used on the project.

The essential elements of training include the following:

(1) PMs Expectations;

(2) IBR objectives;

(3) Risk identification and documentation;

(4) Management Processes;

(5) Baseline maintenance;

(6) Risk management;

(7) Business processes (including EVM); and,

(8) Project Management Aspects:

(a) SOW/SOOs;

(b) WBS dictionary/matrix;

(c) Work authorization document;

(d) Control account plans;

(e) Terms and acronyms;

(f) Funding;

(g) Budget and schedule baselines;

(h) Subcontractor management; and,

(i) Management reserve.

f.  IBR Location – The facility chosen should be adequate to ensure complete participation by all cognizant competencies and organizations.  The IBR is typically conducted at a contractor or government facility to ensure availability of documentation, or as mutually agreed or specified in the contract.  Selection of the location should consider minimizing participant travel and associated costs.

5.  Conduct of IBR Review – The IBR objectives are to confirm that the PMB captures the entire technical scope of work.  Work is scheduled to meet project objectives, risks are identified, proper amount and mix of resources have been assigned to accomplish all requirements, and management processes are implemented in order to ensure PMs have an understanding of risk items.  The key events during the IBR are the control account manager discussions.  These discussions focus on key risk areas and management processes.  To be effective, the discussion group must remain small and focused, and be composed of knowledgeable participants who have participated in the preparation and training.

a.  Risk Areas – Examining the PMB and planning processes determine risk.  These risk areas generally can be grouped as technical, schedule, cost, resources, or management processes.  It is important that any real or perceived risks identified in the planning stage be dealt with during preparation for the IBR.  The following are examples of risk areas:

(1) Technical Risk:  The ability of the project’s technical plan to achieve the objectives of the scope of work.  This includes the effects of available technology, software development capability, human systems design options, design maturity, etc.;

(2) Schedule Risk:  The adequacy of the time allocated for performing the defined tasks to achieve successfully the project schedule objectives.  This includes the effects on the schedule of the interdependency of scheduled activities to achieve project milestones and supports the PMs ability, when necessary, to identify critical path;

(3) Cost Risk:  The ability of the PMB to execute successfully the project cost objectives recognizing the relationships of budget, resources, funding, schedule, and scope of work.  This includes the effects of assumptions used, for both estimates and resource allocation, on budgets for work items;

(4) Resource Risk:  The availability of personnel and facilities required for performing the defined tasks to execute the program successfully; and,

(5) Management Processes Risk:  The degree to which the management processes provide effective integrated cost/schedule/technical planning and baseline change control.  This includes the ability of the processes to establish and maintain valid, accurate, and timely performance data, including that from subcontractors, for early visibility into risk.

b.  Management Processes – Risks may change with contract modifications, funding higher-level authority direction, or a new PM raising the question “Is another IBR necessary?”  However, the objective is to ensure that the management processes are used to provide the PMs an ongoing source of understanding on the project baseline maintenance, risk management, and business processes used by the project.  Management processes necessary to support the Baseline Review Process include the following: changes, replanning, scope/schedule changes, changes to the acquisition plan; and,

(1) Risk Management Process:  The risk management process documents and classifies risks associated with the PMB.  Action items from the IBR need to be documented in the RMP.  These action items should be classified as to their probability of occurrence, consequences, handling, and identification of the individuals responsible for mitigation of risk.  This process must accommodate all changes in project risks including those resulting from changes in the PMB;

(2) Baseline Maintenance Process:  This process maintains a PMB that represents the plan for accomplishing the remaining work.  This process must accommodate changes to the PMB caused by contract modification, funding changes, replanning scope/schedule changes, changes to the acquisition plan, higher level authority direction, etc.; and,

(3) Business Processes:  Other business processes, such as scheduling, estimate to complete, earned value methodology, and managerial analysis, support the management of the project.  Inappropriate or inadequate use of these processes may add risks to the project.

6.  IBR Completion - After completing IBR discussions, a review summary and a closure plan need to be documented.  The PMs should agree on a plan of action and who is responsible for each risk item identified.  Items identified, as action items, require PM attention and should be included in the RMP.  Items identified as watch items represent concerns that may require future attention and inclusion in the RMP if they become action items.  Once the IBR is completed, the emphasis shifts to the management processes as the source of ongoing mutual understanding of the project risks.

7.  IBR Point of Contact – For additional information/details on IBRs or EVM, contact AIR-4.2.3 at (301) 342-2394.

Critical Design Review

1.  CDR Purpose - The CDR is a technical assessment establishing the build baseline to ensure that the system under review has a reasonable expectation of being judged operationally effective and suitable.  This review assesses the final design as captured in product specifications for each CI in the system, and ensures that item has been captured in detailed documentation.  Product specifications for hardware enable the fabrication, and include production drawings.  Product specifications for software enable coding of the CSCI.  The CDR brings to closure technical risk mitigation and alternate design paths in detailed system design.  Once the build baseline is established, opportunities to improve performance or reduce life cycle costs are severely limited.  Changes to support equipment, training requirements, logistics and supply elements, interoperability, and performance can only be accomplished through a major Engineering Change Proposal (ECP).  All technical risk should be reduced to acceptable levels and remaining program execution risk resulting from resource or schedule shortfalls must be addressed quickly or will jeopardize program success.

At CDR, the SDD process results in a detailed build baseline for the system, hardware, software, support equipment, training systems, system integration laboratory, and technical data.  The subsystem detailed designs and logistics elements are evaluated to determine whether they correctly and completely implement all allocated system requirements, and whether the CDD traceability to final system detail design is maintained.  Any changes during SDD are incorporated and the CDD evolves to the CPD required at MS C.  The overall system level CDR is not only approval of the system build baseline, but also approval of the build baselines for maintainability, supportability, and logistics elements.

For complex systems, a CDR may be conducted for each subsystem and logistics element.  These incremental reviews lead to an overall system CDR.  Incremental design reviews are usually defined at Interface Control Document boundaries.  System level performance is supported by compliance with Interface Control Documents, but not assured.  When incremental reviews have been conducted; additional risk is introduced until the overall system CDR establishes the complete system build baseline.  Each incremental CDR closes a functional or physical area of design to modification regardless of when it is held.  This completed area of design may need to be reopened if open areas cannot achieve desired performance in isolation.  If schedule is being preserved through parallel design and build decisions, any system deficiencies that lead to reopening design will result in rework and possible material scrap.

The build (product) baseline is only established when testing and certification is fully defined.  The SDD process refines and decomposes the CDD performance requirements into detailed test and data elements.  The system level specification expands through analysis, decomposition, Interface Control Documents, and the specification tree during the progression to CDR.  Critical design considerations are tagged for testing and validated during DT and OT.  The review will ensure that test planning is complete, test procedures are being completed, certifying agencies having technical authority agree to certification procedures, and the design supports instrumentation and test.

A successful review is predicated on the IPT’s determination that the subsystem requirements, subsystem detail design, results of peer reviews, and plans for testing form a satisfactory basis for proceeding into system fabrication, demonstration and test.  The CDR should occur at the point in the design where the “build-to” (product) baseline has been achieved, allowing production, and coding of software deliverables to proceed.

Acquisition programs with an incremental software development approach will need to conduct a CDR for each increment, and the acquisition documents will only need to be completed for this increment.  The review may be tailored in accordance with the technical scope of the system.  Under no circumstances should the review be tailored completely out of the development plan.  Details of any tailoring should be described in the SEP.  The TRB Chairperson, who is independent of the program team and a representative of AIR-4.1, shall ensure that the details of any tailoring result in a complete evaluation of the system under review and fully characterizes the risk to successful execution.

2.  CDR Timing - The CDR is conducted during the SDD acquisition phase, and represents the last opportunity to make changes in design.  The CDR establishes the build baseline for the weapon system, support equipment, other support elements, and production tooling.  This review occurs after completion of final design efforts and product baseline documentation, and prior to system fabrication and testing.  The CDR may be scheduled a particular number of months after contract award; however, CDR should only occur when the maturity of the system technical baseline has been established as defined above.  A benchmark for requisite system maturity for CDR would be when all design drawings and logistics elements are ready for release from engineering to manufacturing.

3.  CDR Entry Criteria – The entry criteria is grouped into six major areas consistent with other design reviews.  Details for each area are included in the CDR Assessment checklist.  A summary is provided here:

a.  System Requirements and Capabilities:

(1) Detailed Design Specifications complete;

(2) Traceability from CDD to CPD to build drawings;

(3) Traceability through design documentation to test plans is complete;

(4) Reliability, Maintainability, and Diagnostics have been completely addressed in design;

(5) Engineering drawings ready for release to manufacturing;

(6) Software Top Level Design Description and/or Software Architecture Description updated; and,

(7) Software Interface Design Description or equivalent updated

b.  Test, Evaluation, and Certification of Product:

(1) Test Verification Matrix complete;

(2) Engineering data requirements from testing are finalized;

(3) Test plans are complete;

(4) CSCI test procedures are complete;

(5) M&S role in testing defined;

(6) V&V of Systems Integration Lab (SIL) Plan finalized, including simulation, stimulation, and models; and,

(7) All certification plans have been approved by certifying agency.

c.  Engineering Processes, Control, and Analysis:

(1) All TPMs indicate MOPs and MOEs will be satisfied;

(2) All KPPs will be satisfied;

(3) All classified information protected and handled correctly;

(4) All interoperability requirements and Net Ready-KPPs will be satisfied;

(5) All trade-off analysis complete - final design complete;

(6) Data reduction and analysis procedures are established;

(7) System Level Hazard Analysis Complete;

(8) System level R&M analyses complete-final allocations, math models, predictions, FMECA, environmental, and diagnostics;

(9) CSIs identification complete;

(10) SEP updated as required; and,

(11) Current technology maturation plans for identified CTEs have progressed satisfactorily.

d.  Programmatic Processes, Control, and Analysis:

(1) CARD updated as required;

(2) PPIP complete and updated as required;

(3) Operations Security Plans reviewed and adequate;

(4) Manufacturing and Production planning complete;

(5) Logistics Analysis complete and plans established;

(6) Facility Planning complete; and,

(7) Training Plan complete.

e.  Program Master Schedule, Earned Value, Cost:

(1) IMS shows critical path through testing; and,

(2) Earned Value supports CDR closure.

f.  Program Execution Risk and Performance Risk:

(1) Program Technical risks identified, and mitigation plans in place; and,

(2) Program Execution risks identified, and mitigation plans in place.

4.  CDR Planning

a.  TRB Chairperson – Planning for a technical review should start at least 90 days prior to the review.  Technical working groups in all functional areas should begin in preparation for the CDR.  A request for a TRB Chairperson who is independent of the program team should occur at least 45 days prior to conduct of the review.  Typically the assigned APMSE requests a TRB chairperson be appointed by AIR-4.1.  Prior to this request, the assigned APMSE should coordinate chairperson requirements with the system APEO(E).  The role of the (AIR-4.1) chairperson includes:

(1) Determination of TRB membership;

(2) Development of the final review elements;

(3) Oversight of the technical review and RFA process; and,

(4) Issuance of the Technical Review Summary Report.

b.  Technical Review Build-Up TIMs – The APMSE should establish subsystem TIMs to review design readiness for CDR, establish completeness of documentation, adjudicate design disagreements, and prepare CDR presentation material.  These TIMs, referred to as subsystem CDRs, usually begin at least 60 days prior to the CDR and are used to prepare the TRB membership for a successful review.  It is also recommended that a Schedule Risk Assessment following AIR-4.2 guidelines be included in each of these subsystem CDRs.  The TRB provides independent oversight of the design and is not the designing activity. Problem resolution should be completed during the build-up TIMs.

c.  Technical Review Elements – The APMSE and the assigned Chairperson shall coordinate with the system APEO(E) in the development of a preliminary agenda for the planned review.  This agenda should be made available to the IPT at least 30 days prior to conduct of the review.

d.  Technical Review Participants:

(1) TRB (typical composition):

(a) TRB Chairperson;

(b) PM representatives (Industry and Government);

(c) APMSE, who should:

1. Ensure the performing activity provides the supporting data and participation in the required review;

2. Develop, coordinate, and execute, in cooperation with the performing activity, individual review arrangements;

3. Ensure the preparation of requirements performance material is coordinated across IPTs;

4. Conduct the review for the TRB; and,

5. Organize and supervise the documentation of RFAs in support of the TRB Chairperson.

(d) APML, who should ensure all relevant supportability requirements are addressed;

(e) APMT&E who should ensure all test requirements are addressed;

(f) Representatives from all certification authorities;

(g) Cost Team (AIR-4.2) representative;

(h) Software (AIR-4.1) Representative;

(i) Counsel, if required;

(j) Contracting Officer;

(k) Recorder; who is responsible for collating RFAs for submission to the TRB.  The recorder should have the Technical Review Report prepared for distribution by the Chairperson;

(l) Resource Sponsor (Requirements Officer); and,

(m) User representatives

(2) Technical Warrant Holders and Certificate Holders as required addressing system concepts and enabling technologies.  These Technical Warrant Holders represent their NAVAIR competencies in the adjudication of RFAs, to include cost and schedule impacts.  These need to include Certificate Holders for any planned Flight Clearance actions, if applicable.  These assignments should be coordinated with AIR-4.0P.  Certificate Holders should be notified at least 30 days prior to the scheduled review date.

(3) IPT briefers in accordance with the CDR agenda

e.  Location – The facility chosen should be adequate to ensure complete participation by all required competencies and organizations.  The CDR is typically conducted at a contractor or government provided facility, as mutually agreed upon, or specified in the contract.  The facility should support classified discussions at the appropriate level for a complete system review.  The intent is to minimize travel and travel costs.

5.  Conduct of CDR Review - All TRB participants are to assess the materials at the review, document concerns by means of RFAs, and submit RFAs to the TRB Recorder.

a.  CDR Review Elements:

(1) Introduction/agenda/administrative:

(a) Purpose of review;

(b) RFA procedures overview;

(c) Risk Assessment procedures overview; and,

(d) Program overview.

(2) Detailed review of total system, subsystems, and logistics elements:

(a) Design Overview;

(b) Requirements Trace and Completeness;

(c) Allocated Baselines;

(d) Sufficiency of Design;

(e) Test and Certification Requirements;

(f) Measurement Data; and,

(h) Program Level Risks and Mitigation Plans.

b.  Product - Technical Review Summary Report, with the following attachments:

(1) List of attendees, to include: name, functional area represented, NAVAIR code, phone number, and email address;

(2) Final presentations;

(3) Update risk assessment with mitigation plans;

(4) Completed RFA forms;

(5) Meeting minutes;

(6) Recommendation to PMA on the probability the system will be judged operationally effective and suitable; and,

(7) Completed CDR checklist with comments.

6.  CDR Completion - The CDR is considered complete when all draft RFAs are signed off, and an acceptable level of program risk is ascertained.  After the RFAs are closed, the system APMSE shall prepare a letter for the TRB Chairperson formally closing the review.  A CDR data package shall be prepared containing the products of the review and the closure letter, and submitted to the AIR-4.1 SETR archival database.

Integration Readiness Review

1.  IRR Purpose - The IRR is a product and process assessment to ensure that hardware and software are ready to begin integrated CI testing. The IRR is a technical assessment establishing the configuration to be used in integration test to ensure that the system has a reasonable expectation of being judged operationally effective and suitable.  The testing is based upon the test plan begun in the requirements phase and completed during design.  It is conducted after the test and/or validation procedures are complete and unit level testing is complete.  The purpose of IRR is for the acquirer to determine whether the developer is ready to begin CI or subsystem integration testing in the laboratory.

The IRR will assess prior component or unit level testing adequacy, test planning, test objectives, test methods and procedures, scope of tests, and determines if required test resources have been properly identified and coordinated to support planned tests.  The IRR verifies the traceability of planned tests to program, engineering data, analysis, and certification requirements.  Each CI is assessed for developmental maturity and readiness to proceed to CI integration testing.  Confidence that the CI will pass testing is evaluated based on the impact of known anomalies.

The IRR occurs prior to fully integrated hardware and software testing which is addressed in the TRR.  The IRR supports systematically maturing the software components on the path to integrated system and unit testing. Additionally, it provides for a logical evaluation of the toolsets used to test software in the form of SIL (or other system integration facilities) prior to these facilities supporting product test.  To minimize the inherent dependence between these facilities and the software under test, it is important to perform V&V of the test facility.  The SIL V&V will determine the adequacy of the system requirements roll down and the fidelity of the SIL replicating the operational environment.  The IRR verifies procedures that recognize this dependence.

An integral part of the SE process is T&E (critical element of system analysis and control; part of the verification loop).  As such, just as the SE process permeates the entire life cycle of an acquisition program so too does T&E.  An important tool to identify and control risk is T&E.  Although this template principally addresses the IRR; which is a derivative of the Test Readiness Review (TRR) specified in references (a) and (b); to support a readiness for a CI to proceed into subsystem or CI integration test, the IRR process is designed to be the first of a building set of IRRs.   For those systems where there are numerous CIs or those where individual CIs progress at different rates, there may be multiple IRRs.  PM's and product leads should tailor the requirements specified herein to the specific planned tests and the identified risk level of their respective programs.  A robust test program will greatly enhance the PM's ability to identify and manage risk, and catch problems earlier in the development cycle, when they are less costly to correct.  The degree of review a given set of tests should receive is directly related to the risk level associated with performing the planned tests and the importance of the test results to overall program success.  Integration test requires the same level of review as the final system or system of system level tests and provides for insight into the maturity of the CI interfaces and how individuals CI interact with each other.

Readiness to convene an IRR is predicated on the Program/ IPT’s determination that integration test preparation forms a satisfactory basis for proceeding with an IRR.  Additionally, readiness relies on the knowledge of the vulnerabilities and limitations through detection and reporting of anomalies in order to assess the level of risk to enter a test phase.

The IRR may be tailored in accordance with the technical scope and risk of the CI under test.  It is highly recommended that this review not be tailored completely out of the development plan as it is designed to catch problems before the developmental or flight testing.  However, if the IRR is tailored out of the development plan, then under no circumstances will the system level TRR be tailored out of the development plan.  As a minimum the testers must understand capabilities added to or corrected in the CI, testing to date, vulnerabilities and limitations of the CI under test, and ability of the CI under test to successfully pass the proposed testing.  Details of any tailoring should be described in the SEMP/SEP, or should occur as part of the Program/IPT's APMSE or systems engineer coordination of the review elements with the AIR-4.1 cognizant authority (APEO(E)).

In general terms the template provides guidance to ensure that test events are carefully planned and properly resourced.  No matter what stage of the acquisition or whether you are planning a component test, a system test, or a system of systems test, the basic tenets of this guidance should apply.

If an incremental software development approach is used on this acquisition program then the acquisition documents will only need to be completed for this increment.

2.  IRR Timing – The IRR is typically conducted during the System Demonstration work effort of the System Development and Demonstration phase.  Like other technical reviews, the IRR should be event driven and should not be scheduled at a particular number of months after contract award; but rather, should occur relative to the readiness/maturity of the CI under test to begin the CI testing required to support the overall program T&E and Risk management plans.  The IRR is used for earlier testing to ensure readiness/maturity to enter subsequent test phases (TRR and FRR).  IRR will be held after all components or units of the CI have been tested and have been integrated together to form the CI.  The results from this test period will be used to determine maturity of the integrated CIs at the systems level testing.

3.  IRR Entry Criteria

a.  Requirements and Capabilities:

(1) All requirements documentation complete;

(2) All design documentation complete;

(3) All interface documentation complete;

(4) Traceability from CDD to CPD to as-built CSCI;

(5) Traceability through design to test plans and procedures is verified;

(6) Requirements traceability to System Integration Lab/Facility is complete; and,

(7) The SIL/Facility Configuration is stable and under CM.

b.  Test, Evaluation, and Certification of Product:

(1) Requirements Verification Matrix, preferably the output of a Requirements Management Tool;

(2) Test Plan;

(3) Test and/or Validation Procedures;

(4) Test Report content;

(5) Anomaly reporting system; and,

(6) The SIL/Facility configuration is built according to requirements, stable, available for testing, and under CM

c.  Engineering Processes, Control, and Analysis:

(1) TPMs traceable to MOEs and MOPs;

(2) CSIs;

(3) SIL/Facility V&V Plan Complete; and,

(4) Current technology maturation plans for identified CTEs have progressed satisfactorily.

d.  Programmatic Processes, Control, and Analysis:

(1) Cost updated, as required;

(2) CPI;

(3) Risk Management Program;

(4) Measurement Program;

(5) CM; and,

(6) IDE functional and accessible by all team members.

e.  Program Master Schedule, Earned Value, Cost:

(1) CSCI integration test tasks are resourced at reasonable levels with realistic performance expectations; and,

(2) CSCI testing dates meet subsequent testing requirements.

f.  Program Execution Risk and Performance Risk:

(1) Program Technical Risks identified and mitigation plans in place; and,

(2) Program Execution Risks identified and mitigation plans in place.

4.  IRR Planning

a.  IRR Chairperson – Planning for an IRR should start with a request for a TRB Chairperson who is independent of the program team, nominally 90 days prior to conduct of the review.  Typically the PMA, assigned IPT leader, assigned APMSE, or Software Lead for software CI testing requests a TRB chairperson be appointed by AIR-4.1.  For an IRR, it may be desirable to include the program’s Test and Evaluation Lead to serve as a co-chairperson of the IRR.  If the IRR is for a CSCI, the TRB Chairperson will be assigned by the NAVAIR Software Organization within AIR-4.1 and the co-chairperson may be the program’s Software Lead.  Prior to this request, the assigned APMSE or Software Lead should have coordinated chairperson requirements with the cognizant (APEO(E)).  Chairperson assignments should be reflective of program scope and risk.  The role of the chairperson includes:

(1) Determination of TRB membership;

(2) Development of the final review elements;

(3) Oversight of the technical review and RFA process; and,

(4) Issuance of the Technical Review Summary Report.

b.  Technical Review Elements – The APMSE and the assigned Chairperson shall coordinate with the cognizant APEO(E) in the development of a preliminary agenda for the planned review.  A sample review agenda is shown below in paragraph 5.a.  This agenda should be made available to the IPT 30 days prior to conduct of the review.  It is also advisable to provide a read ahead brief (no more than 10 slides) to the IPT and chairperson(s) 10 days prior to the conduct of the review.  This action also serves as a good reminder as to date/time of the event.

c.  Technical Review Participants:

(1) TRB typical composition):

(a) TRB Chairperson;

(b) PM Representatives (Industry and/or Government);

(c) APMSE or Software Lead, who should:

1. Ensure the performing activity provides the supporting data and participation in the required review;

2. Develop, coordinate, and execute, in cooperation with the performing activity, individual review arrangements;

3. Ensure the preparation of IRR material is coordinated within the team;

4. Participate in the review; and,

5.	Organize and supervise the documentation of RFAs in support of the TRB Chairperson.

(d) System or Software Safety, who should ensure all safety-critical requirements are identified and the System Safety Hazard Analysis is complete;

(e) Recorder; who is responsible for collating RFAs for submission to the TRB and recording of the minutes of the IRR.  The recorder should have the Technical Review Report prepared for distribution by the Chairperson;

(f) Software (AIR-4.1) Representative;

(g) T&E Lead; and,

(h) User representatives, if appropriate.

(2) SMEs as required to address system concepts and enabling technologies.  These SMEs represent their NAVAIR competencies in the adjudication of RFAs.  SMEs should be notified at least 30 days prior to the scheduled review date.

(3) IPT briefers in accordance with the IRR Agenda.

d.  IRR Location – The facility chosen should be adequate to ensure complete participation by all required competencies and organizations.  The IRR is typically conducted at a developer’s facility, as mutually agreed upon, or specified in the contract or work assignment agreement.  The facility should support classified discussions at the appropriate level for a complete IRR.  The intent is to minimize travel and travel costs.

5.  Conduct of IRR Review - All TRB participants are to assess the materials at the review, document concerns by means of RFAs, and submit RFAs to the TRB Recorder.

a.  IRR Review Elements:

(1) Introduction/agenda/administrative:

(a) Purpose of review;

(b) RFA procedures overview;

(c) Risk Assessment procedures overview; and,

(d) Program overview, and how planned tests support the overall program.

(2) Status on the risks;

(3) Updates to the program schedule;

(4) Software, including Measurement Data (Metrics);

(5) Test Program Overview:

(a) Test Schedule;

(b) Test Verification Matrix;

(c) Laboratory Configuration;

(d) Models and Simulation Accreditation/ Certification Results, as required; and,

(e) Test Anomaly Reporting.

(6) Test Program Staffing:

(a) Organization structure/chart;

(b) Key acquirer/developer interfaces; and,

(c) Roles and Responsibilities.

(7) Unit Level Test Results:

(a) Identify any preliminary testing that has already been conducted and their results; and,

(b) Identify any outstanding discrepancies as a result of any preliminary/informal testing previously conducted and risk to test program.

(8) Test Requirements:

(a) Required test resources (personnel, facilities, test environment, and test assets);

(b) Final reporting process/format defined; and,

(c) Fall back plan for technical issues and showstoppers.

(9) Design changes during implementation;

(10) Follow IRR Program Assessment checklist structure;

(11) Recommendation on Readiness to Commence Integration Testing; and,

(12) Review of RFAs.

b.  IRR Products:

(1) Technical Review Summary Report, with the following attachments:

(a) List of attendees, to include: name, functional area represented, NAVAIR code, phone number, and email address;

(b) Completed RFA forms;

(c) Meeting minutes; and,

(d) Recommendation to PMA as to the technical readiness of the program to enter into the planned tests.

(2) Test Verification Matrix;

(3) Updated Risk Assessment, including identification of risks, recommended mitigation strategy, and assessment of residual risk; and,

(4) Lists of anomalies, limitations, and vulnerabilities.

6.  IRR Completion - The IRR is considered complete when all draft RFAs are signed off, and an acceptable level of program risk is ascertained.  After the RFAs are closed, the APMSE or Software Lead shall prepare a letter for the TRB Chairperson formally closing the review and recommending commencement of the integration testing.  An IRR data package shall be prepared containing the products of the review and the closure letter, and submitted to the AIR-4.1 SETR archival database.

Test Readiness Review

1.  TRR Purpose - The TRR is a technical assessment establishing the configuration used in test to ensure that the system has a reasonable expectation of being judged operationally effective and suitable.  The TRR is a multi-disciplined product and process assessment to ensure that the subsystem, system, or systems of systems has stabilized in configuration and is ready to proceed into formal test.  The TRR assesses prior unit level and system integration testing adequacy, test planning, test objectives, test methods and procedures, scope of tests, and determines if required test resources have been properly identified and coordinated to support planned tests.  The TRR verifies the traceability of planned tests to program, engineering, analysis, and certification requirements.  The TRR determines the completeness of test procedures and their compliance with test plans and descriptions.  The TRR assesses the impact of known discrepancies to determine if testing is appropriate prior to implementation of the corrective fix.  The TRR must be planned, managed, and followed up to be an effective system analysis and control tool.

An integral part of the SE process is T&E (critical element of system analysis and control; part of the verification loop).  The SE process permeates the entire life cycle of an acquisition program to include T&E.  Additionally, T&E is an important tool to identify and control risk.  Although this template principally addresses the TRR specified in references (a) and (b) to support a readiness for a system to proceed into system level DT, the TRR process is equally applicable to all tests in all phases of an acquisition program.  A TRR can be used to determine if maturity of a software product or integrated set of software products is of a sufficient level to proceed into any type of testing.  PM's and their respective T&E IPT's should tailor the requirements specified herein to the specific acquisition phase, the specific planned tests, and the identified risk level of their respective programs.  The level of specific risk will vary as a system proceeds from component level, to system level, to systems of systems level testing.  A robust test program will greatly enhance the PM's ability to identify and manage risk, and catch problems earlier in the development cycle.  Early component level test may not require the same level of review as the final system or system of system level tests.  However, any test plans and products need to undergo a Peer Review to determine the applicability, effectiveness, and completeness of any testing.

Readiness to convene a TRR is predicated on the Program/ IPT’s determination that preliminary testing, functional testing, and pre-qualification testing results form a satisfactory basis for proceeding with a TRR and initiation of formal system level DT.  Additionally, readiness relies on the knowledge of the vulnerabilities and limitations through detection and reporting of anomalies in order to assess the level of risk to enter a test phase.  Results from an IRR will provide additional information for TRR readiness determination.

The TRR may be tailored in accordance with the technical scope and risk of the system under test.  Under no circumstances should the review be tailored completely out of the development plan.  As a minimum, the testers must understand capabilities added to or corrected in the software, testing to date, vulnerabilities and limitations of the system under test, and ability of the system under test to successfully pass the proposed testing.  Details of any tailoring should be described in the SEP, or should occur as part of the Program/IPT's APMSE or systems engineer coordination of the review elements with the AIR-4.1 cognizant authority (APEO(E)).

In general terms, the template provides guidance to ensure that test events are carefully planned and properly resourced.  No matter what stage of the acquisition or whether you are planning a component test, a system test, or a system of systems test, the basic tenets of this guidance should apply.

2.  TRR Timing – The TRR is typically conducted during the System Demonstration work effort of the SDD acquisition phase.  Like other technical reviews, the TRR should be event driven and should not be scheduled at a particular number of months after contract award; but rather, should occur relative to the readiness/maturity of the system under test to begin the subsystem, system, or systems of systems level DT required to support the overall program T&E and Risk management plans.  The TRR may be used for earlier testing to ensure readiness/maturity to enter any test phase.

3.  TRR Entry Criteria

a.  Requirements and Capabilities:

(1) All requirements documentation is complete;

(2) All design documentation is complete;

(3) All interface documentation is complete;

(4) Traceability from CDD to CPD to build is verified;

(5) Traceability through design documentation to test plans is complete;

(6) Requirements traceability to System Integration Lab/Facility is complete; and,

(7) The System Integration Lab/Facility Configuration is stable and under CM.

b.  Test, Evaluation, and Certification of Product:

(1) Requirements Verification Matrix, preferably the output of a Requirements Management Tool, is complete;

(2) Test Plan is complete;

(3) Test and/or Validation Procedures are complete;

(4) Test Report content is agreed upon;

(5) Anomaly reporting system is functional;

(6) Laboratory assets are in the proper configuration and will be available for the testing;

(7) The SIL/Facility configuration is stable and under CM; and,

(8) All test certification or flight approvals have been obtained.

c.  Engineering Processes, Control, and Analysis:

(1) TPMs identified and traceable to MOEs and MOPs;

(2) CSIs identified and verification approach agreed upon;

(3) SIL/Facility V&V Plan Complete;

(4) All Hazard Risks Assessments have been accepted;

(5) Data Reduction Procedures and Responsibilities are documented and accepted;

(6) Data Analysis Procedures and Responsibilities are documented and accepted; and,

(7) Current technology maturation plans for identified CTEs have progressed satisfactorily.

d.  Programmatic Processes, Control, and Analysis:

(1) Cost updated, as required;

(2) CPI Identified;

(3) Risk Management Program Fully Functioning;

(4) Measurement Program Fully Functioning;

(5) CM Board Established and Functioning;

(6) IDE Functioning; and,

(7) Logistics and supply support for testing adequate.

e.  Program Master Schedule, Earned Value, Cost:

(1) Detailed test schedule established and fully resourced; and,

(2) Progressive testing and test dependencies fully identified.

f.  Program Execution Risk and Performance Risk:

(1) Technical risks identified and Mitigation Plan in place; and,

(2) Execution risks identified and Mitigation Plan in place.

4.  TRR Planning

a.  TRR Chairperson – Planning for a TRR should start with a request for a TRB Chairperson who is independent of the program team., nominally 90 days prior to conduct of the review.  Typically the PMA, assigned IPT leader, or assigned APMSE requests a TRB chairperson be appointed by AIR-4.1.  For a TRR it is appropriate to include a senior AIR-5.1 designated person to serve as a co-chairperson.  Prior to this request, the assigned APMSE should have coordinated chairperson requirements with the cognizant APEO(E).  Chairperson assignments should be reflective of program scope and risk.  The role of the chairperson includes:

(1) Determination of TRB membership;

(2) Development of the final review elements;

(3) Oversight of the technical review and RFA process; and,

(4) Issuance of the Technical Review Summary Report

b.  Technical Review Elements – The APMSE and the assigned Chairperson shall coordinate with the cognizant APEO(E) in the development of a preliminary agenda for the planned review.  A sample review agenda is shown below in paragraph 5.a.  This agenda should be made available to the IPT 30 days prior to conduct of the review.  It is also advisable to provide a read ahead brief (no more than 10 slides) to the IPT and chairperson(s) 10 days prior to the conduct of the review.  This action also serves as a good reminder as to date/time of the event.

c.  Technical Review Participants:

(1) TRB (typical composition):

(a) TRB Chairperson/ Co-chairperson;

(b) PM representatives (Industry and Government); and,

(c) APMSE, who should:

1. Ensure the performing activity provides the supporting data and participation in the required review;

2. Develop, coordinate, and execute, in cooperation with the performing activity, individual review arrangements;

3. Ensure the preparation of TRR material is coordinated across IPTs; and,

4. Organize and supervise the documentation of RFAs in support of the TRB Chairperson.

(d) APML, who should ensure all relevant supportability requirements are addressed;

(e) APMT&E, who should ensure T&E requirements are addressed;

(f) Counsel, if required;

(g) Software (AIR-4.1) Representative;

(h) Contracting Officer;

(i) Recorder; who is responsible for collating RFAs for submission to the TRB, and recording the minutes of the TRR.  The recorder should have the Technical Review Report prepared for distribution by the Chairperson;

(j) Resource Sponsor (Requirements Officer);

(k) User representatives, if appropriate; and,

(l) Lead for the software support agency.

(2) SMEs as required to address system concepts, enabling technologies, certification, safety, etc.  These SMEs represent their NAVAIR competencies in the adjudication of RFAs.  (A TRR must have an appropriate AIR-5.1 representative for the system under test).  SMEs should be notified at least 30 days prior to the scheduled review date.

(3) IPT briefers in accordance with the TRR Agenda.

d.  TRR Location – The facility chosen should be adequate to ensure complete participation by all cognizant competencies and organizations.  The TRR is typically conducted at a contractor or government provided facility, as mutually agreed upon, or specified in the contract.  The facility must be able to support a meeting at the appropriate classification level to ensure effective information exchange and to address maturity of the system under test through discussions on anomalies, limitations, and vulnerabilities.  Selection of the location should consider minimizing participant travel and associated costs.

5.  Conduct of TRR Review - All TRB participants are to assess the materials at the review, document concerns by means of RFAs, and submit RFAs to the TRB Recorder.

a.  TRR Review Elements:

(1) Introduction/agenda/administrative:

(a) Purpose of review;

(b) RFA procedures overview;

(c) Risk Assessment procedures overview; and,

(d) Program overview, and how planned tests support the overall program.

(2) Status on the risks;

(3) Updates to the program schedule;

(4) Measurement Data (Metrics);

(5) Test Program Overview, including the test schedule; and

(6) Test Program Staffing:

(a) Organization structure/chart; and,

(b) Key government/contractor interfaces

(7) Preliminary/IRR/informal test results:

(a) Identify any preliminary testing that has already been conducted; and,

(b) Identify any outstanding discrepancies as a result of any preliminary/informal testing previously conducted.

(8) Test Requirements:

(a) Required test resources (personnel, facilities, test environment, and test assets);

(b) Final reporting process/format defined; and,

(c) Fall back plan for technical issues and showstoppers.

(9) Follow TRR Program Assessment checklist structure;

(10) Recommendation on Readiness to Commence Testing;

and,

(11) Review of RFAs.

b.  TRR Products:

(1) Technical Review Summary Report, with the following attachments:

(a) List of attendees, to include: name, functional area represented, NAVAIR code, phone number, and email address;

(b) Completed RFA forms;

(c) Meeting minutes; and,

(d) Recommendation to PMA as to the technical readiness of the program to enter into the planned tests.

(2) Updated Risk Assessment, including identification of risks, recommended mitigation strategy, and assessment of residual risk.

(3) Lists of anomalies, limitations, and vulnerabilities.

6.  TRR Completion - The TRR is considered complete when all draft RFAs are signed off, and an acceptable level of program risk is ascertained.  After the RFAs are closed, the system APMSE shall prepare a letter for the TRB Chairperson formally closing the review.  A TRR data package shall be prepared containing the products of the review and the closure letter, and submitted to the AIR-4.1 SETR archival database.

Flight Readiness Review

1.  FRR Purpose - The FRR is a technical assessment establishing the configuration used in flight test to ensure that the system has a reasonable expectation of being judged operationally effective and suitable.  This review assesses the system and test environment to ensure that the system under review can proceed into flight test with NAVAIR airworthiness standards met, objectives clearly stated, flight test data requirements clearly identified, and an acceptable RMP defined and approved.  Generally, this review ensures that proper coordination has occurred between engineering and flight test, and that all applicable disciplines understand and concur with the scope of effort that has been identified, and how this effort will be executed to derive the data necessary (to satisfy airworthiness and test and evaluation requirements) to ensure the weapon system evaluated is ready to proceed to flight test.  As such, this review shall include appropriate level of detail for each configuration expected to be evaluated within the flight test effort, and specified in both the flight test plan and the flight clearance.  The configuration may consist of hardware and software elements, and include items such as airframe, avionics, weapons, crew systems, engines, trainers/training (supporting flight test), etc.  It is important that software be evaluated in the laboratory to ensure that software is safe to fly, and that test objectives can be met.  The CDR should have established the system product baseline.  The FRR shall include detailed entry criteria.

An FRR shall be conducted prior to the first flight of any new air vehicle.  For complex systems, an FRR shall be conducted with an assessment of each subsystem or CI prior to flight.  An FRR is also required prior to the first flight of any major changes to hardware, software, envelope, or objectives not covered in a previous FRR.  Typical changes that require an FRR include, but are not limited to, configuration changes such as new engine(s); significant changes to hydraulic or electrical systems; new wing; major upgrades to flight control hardware or software; change to number or material selection of propellers or rotors; change in utilization or mission; or changes which affect safety, security or other flight worthiness-related attributes.

The APMSE in conjunction with the Chief Flight Test Engineer, APEO(E), Squadron Chief Engineer, or senior AIR 5.1G individual in the T&E Chain of Command shall recommend whether or not to convene an FRR for major modifications to an existing air vehicle.  The recommendation will then be presented to AIR 4.0, AIR 4.1, and AIR 5.1 competency leadership for their concurrence.  An FRR is typically not required for on-going developmental testing changes or modifications such as: minor software changes (those that can be fully tested in the laboratory and do not affect safety of flight); envelope expansions to an envelope previously reviewed in a flight clearance pre-planning meeting and Executive Review Board (ERB); minor changes to weapons or stores (does not affect release or delivery); minor changes to weight and balance; and wing dressings (such as vortex generators, fences, porous wing fold fairing covers, etc.).

The FRR Chairperson(s) who is (are) independent of the program team, shall review the details and conclusions of peer reviews, laboratory testing, and Independent Review Teams (IRTs) for the final detailed design.  A successful review is predicated on the determination of the chairperson(s) that the subsystem requirements, subsystem detail design, results of peer reviews, IRTs, laboratory testing, and plans for risk mitigation form a satisfactory basis for proceeding into Flight Test.

Tailoring of the review is permissible in accordance with the technical scope of the system under review.  Only the APMSE, in conjunction with the APEO(E), and AIR-4.1 leadership can provide the approval for the review to be tailored completely out of the development plan.  Details of any tailoring must be described in the SEP.

Successful completion of the FRR does not represent concurrence from the procuring authority that testing will result in acceptable system performance.  The FRR, as a component of the SETR process, serves as technical monitoring of program execution by senior functional area experts.  The contractor remains responsible for the system design and performance requirements within the terms of the contract.

2.  FRR Timing - The FRR is typically conducted during the SDD acquisition phase, after completion of the CDR and TRR, and prior to convening an ERB.  The ERB is an AIR-5.1 process as described in NAVAIRINST 3960.4B (Project Test Plan Policy and Guide for Testing Air Vehicles, Air Vehicle Weapons, and Air Vehicle Installed Systems), separate and distinct from the FRR, and is primarily focused on the test planning and test plan approval for the flight test program.  The APMSE should ensure that technical exchanges (TIMs) have taken place in each IPT prior to the FRR, and that outstanding actions are carried forward to the FRR.  IPT members are responsible for briefing their material to their respective competency leadership participating in the FRR.  Each competency is responsible for ensuring that all appropriate areas are being covered by team members, reviewing background material, and receiving a brief from their competency team members prior to the FRR.

A Pre-FRR should be held prior to the FRR, with adequate time to adjudicate any resulting action items.  The FRR is typically conducted approximately two weeks prior to the anticipated first flight of the aviation system.  The Pre-FRR should follow the same format as the FRR, but without the chairperson(s).  The Pre-FRR should be convened by the APMSE with the purpose of identifying critical issues and risks that need resolution prior to the FRR.  The Pre-FRR should be more detailed technically, with the FRR presenting only those technical details necessary to clarify FRR content and risks for the chairperson(s).  There is no mandatory sequence between the FRR and the ERB.  The Test Plan can not be approved until the flight clearance is issued.  Scheduling of FRR should be contingent upon ensuring that entry criteria will be met by the beginning of the FRR, that a reasonable expectation of meeting the entrance criteria exists, that the team believes they can receive go-ahead from the chairperson(s) of the FRR, that the first flight event is coordinated closely with the applicable PMA(s), and that it is consistent with their milestone events.  These expectations should be verified at the Pre-FRR.

3.  FRR Entry Criteria - The following are the minimum entry criteria that should be addressed before each FRR.  The APMSE may desire to tailor these, and may do so with the approval of the chairperson(s).  Tailoring includes adding program specific criteria.

a.  System Requirements and Capabilities:

(1) Final Specifications Complete;

(2) Build Drawings Complete;

(3) Traceability of all system requirements to their verifications plans;

(4) Software media, including loading instructions or Technical Directive, and Version Description Document under configuration control.

b.  Test, Evaluation, and Certification of Product:

(1) Engineering data requirements from testing are finalized;

(2) Data reduction and analysis roles and responsibilities are defined;

(3) Test plans have been drafted, are in the approval cycle, and ready for ERB;

(4) Flight test requirements supporting M&S validation clearly identified; and,

(5) All test plans required for certification have been coordinated with the certifying agency.

c.  Engineering Processes, Control, and Analysis:

(1) TPMs traceable to test plans;

(2) KPPs traceable to test Plans;

(3) EDRAP has been signed;

(4) A flight clearance has been issued or a plan to get an initial flight clearance prior to final test plan approval exists;

(5) R&M scoring guidelines have been established; and,

(6) Current technology maturation plans for identified CTEs have progressed satisfactorily.

d.  Programmatic Processes, Control, and Analysis:

(1) Contractor and Government Test Team responsibilities established and documented;

(2) Critical flight test support has been identified and is coordinated; and,

(3) Yellow sheet process implemented.

e.  Program Master Schedule, Earned Value, Cost:

(1) IMS shows critical path through completion of testing;

(2) IMS includes envelope clearance critical path events; and,

(3) Earned Value supports FRR closure.

f.  Program Execution Risk and Performance Risk:

(1) Program Technical risk medium or lower; and,

(2) Program Execution risk medium or lower

4.  FRR Planning - The FRR is an AIR-4.0 led review.  The FRR normally includes designation of two chairpersons who are independent of the program team: one from AIR-4.0, Chair defaults to AIR-4.1 unless specifically directed otherwise by senior leadership; and the other from AIR-5.1.  It is the responsibility of the APMSE to coordinate all actions except the designation of the chairperson(s).

a.  FRR Chairperson – The chairperson role of the FRR rests with the Head of AIR-4.1, or their designated representative. The FRR may also be co-chaired by the AIR-5.1 Test Wing Commander.  Chairperson(s) assignment(s) should be reflective of program scope.  The roles and responsibilities of the chairperson(s) include:

(1) Concurrence with proposed FRR participants;

(2) Approval of the FRR agenda;

(3) Maintaining focus and direction of the FRR;

(4) Approval of the technical review and RFA process;

(5) Conduct the review for the FRR TRB;

(6) Ensuring Competency technical concerns are understood and briefed to appropriate levels;

(7) Ensuring Risk Assessment is understood and briefed to appropriate levels; and,

(8) Unless otherwise directed by AIR-4.0 or senior leadership, provides approval to close FRR and to proceed to flight test pending flight clearance and approval of the test plan.

b.  FRR APMSE - The APMSE (or designated IPT Leader) is responsible for the conduct of the FRR.  The roles and responsibilities of the APMSE are to:

(1) Convene a Pre-FRR to ensure path to a successful FRR is identified;

(2) Develop a Draft FRR agenda for chairperson(s) approval;

(3) Identify FRR participants and brief the chairperson(s);

(4) Ensure a Pre-Planning flight clearance meeting has been completed and critical data to support flight clearance has been identified;

(5) Ensure flight clearance Warrant Holders and Certificate Holders have access to critical data, CDR results and risk assessments;

(6) Ensure the performing activity provides the supporting data to FRR TRB members, and has participated in the required technical reviews;

(7) Ensure the preparation of design and FRR material is coordinated across IPTs;

(8) Organize and supervise the documentation of RFAs in support of the FRR chairperson(s);

(9) Coordinate RFA responses with action assignees;

(10) Forward RFA actions with responses and recommended action (remain open/defer/closed) to the chairperson(s) for final resolution;

(11) Ensure an independent technical risk assessment has been completed and integrated into the process; and,

(12) Provide email notification to the chairperson(s), AIR-4.1/4.1A, AIR-5.1/5.1A and AIR-4.0P that: the FRR RFAs/actions have been closed in accordance with chairperson(s) guidance; that the FRR is recommended to be officially closed; and that the air vehicle/system is sufficiently mature to proceed to flight test.

c.  FRR Participants - The FRR participants are responsible for ensuring critical technical information and risks are conveyed in a clear and concise manner to the FRR chairperson(s).  In addition to the chairperson(s) and the APMSE, the composition of a typical FRR should include:

(1) NAVAIR Airworthiness Officer (AIR-4.0P)- acts as an advisor to the chairperson(s) who provides a recommendation on the readiness of the air vehicle to proceed with the airworthiness review and flight clearance approval process;

(2) PM and technical representatives;

(3) APEO(E);

(4) Chief Test Engineer, Chief Test Pilot, and appropriate members of the flight test engineering team;

(5) Lead instrumentation engineer;

(6) The APML, who should ensure all relevant supportability issues are addressed;

(7) The APMT&E, who should ensure all test and evaluation requirements are addressed;

(8) Recorder; who is responsible for collating RFAs originated at the FRR.  The recorder should have the FRR Report prepared for distribution by the APMSE after approval by the chairperson(s);

(9) System Safety (AIR-4.1.6) who provides a detailed Risk Assessment;

(10) Program Security representative who provides a critical evaluation of security procedures;

(11) Software (AIR-4.1) Representative;

(12) Technical Warrant Holders and Certificate Holders as required addressing system concepts and enabling technologies.  These Technical Warrant Holders represent their NAVAIR competencies in the adjudication of RFAs, to include cost and schedule impacts.  These need to include Certificate Holders for any planned Flight Clearance actions, if applicable.  These assignments should be coordinated with AIR-4.0P.  Certificate Holders should be notified at least 30 days prior to the scheduled review date.

(13) Operational Testers (as appropriate);

(14) IPT briefer in accordance with the FRR agenda; and,

(15) User representatives.

d.  FRR Location – The facility chosen should be adequate to ensure complete participation by all cognizant competencies and organizations.  The FRR is typically conducted at a contractor or government provided facility, often at a site where the predominant amount of flight test will be conducted, as mutually agreed upon, or specified in the contract.  Selection of the location should consider minimizing participant travel and associated costs.

5.  Conduct of FRR Review - All FRR participants are to assess the materials at the review, document concerns by means of RFAs (and/or verbally), and submit RFAs to the FRR Recorder, as appropriate.  All risks must be understood and documented.  All IPT briefers shall complete the FRR Assessment checklist, and all “Red” and “Yellow” grades must be understood with mitigation plans briefed.

a.  FRR Review Elements - The following are recommended review elements.  The APMSE shall develop an agenda and seek approval from the chairperson(s) prior to releasing the meeting invitations.

(1) Introduction/agenda/administrative/Purpose of review:

(a) RFA procedures overview;

(b) Program, schedule and technical overview;

(c) System Safety/Risk Assessment review; and,

(d) System and/or Program Security Risk assessment review;

(2) New systems and modifications since CDR (if applicable);

(3) Review of the RFAs from the CDR (and prior reviews, if applicable);

(4) Status of identified risks;

(5) Updates to the program schedule;

(6) Metrics;

(7) Airworthiness – Plan for flight clearance;

(8) Recommendation on readiness to conduct flight test; and,

(9) Review of the RFAs from the FRR.

b.  FRR Presentations - All presenters shall present pertinent data to support a summary slide.  All presenters shall use the same format for their summary slides.  Where possible, presentations should reflect the joint position of the IPT and Industry counterpart.

(1) FRR Checklist - Each relevant competency must complete the FRR Assessment checklist for the subcategory tasks within their technical (engineering) disciplines prior to first flight.  The respective competency managers shall agree with the tailoring of the Checklist prior to presentation.  Each task will be assigned a color code of “Red”, “Yellow”, or “Green”.  A summary briefing slide for each individual competency will be prepared that includes the overall evaluations for that engineering discipline, also using that color code.  The APMSE shall use these summary slides to determine the IPT briefers during the FRR.  All competencies with a summary grade of “Red” shall provide a brief at the FRR.  Summary grades of “Yellow” or “Green” are required to present at the FRR at the discretion of the APMSE (or their senior).  The criteria definitions are as follows:

(a) Green - Tasks complete, ready to proceed;

(b) Yellow - Some/all tasks incomplete but scheduled to be completed prior to first flight; and,

(c) Red - Tasks not scheduled to be completed in time to support first flight.  This could result in either postponement of first flight and/or reduction in scope of effort until satisfactory completion.

(2) The summary slides shall contain the following information:

(a) Checklist (does it support a flight clearance to satisfy scope of FRR?);

(b) Competency/Engineering Discipline;

(c) Completeness of planned tests with respect to system requirements;

(d) Adequacy of resources (facilities, instrumentation, logistics elements, equipment, staffing, funding, etc.);

(e) Issues(s);

(f) Impact(s)/Risk(s); and,

(g) Mitigation Plan(s).

c.  FRR Products:

(1) FRR Summary Report, with the following attachments:

(a) List of attendees, to include; name, functional area represented, organizational code, phone number, and email address;

(b) final presentations;

(c) updated risk assessment and mitigation plans;

(d) completed RFA forms;

(e) meeting minutes; and,

(f) recommendation to AIR-4.0/4.1/5.1/PMA as to the technical readiness of the program to commence flight test.

(2) Completed Competency Checklists with each engineering discipline reporting that they are either “Red”, “Yellow” or “Green” to go to flight test.

6.  FRR Completion - The FRR is considered complete when all draft RFAs are signed off, and an acceptable level of program risk is ascertained.  After the RFAs are closed, the system APMSE shall prepare a letter for the TRB Chairperson formally closing the review.  An FRR data package shall be prepared containing the products of the review and the closure letter, and submitted to the AIR-4.1 SETR archival database.

Operational Test Readiness Review

1.  OTRR Purpose - The OTRR is a multi-disciplined product and process assessment to ensure that the system under review can proceed into Operational Test and Evaluation (OT&E) with a high probability the system will successfully complete operational testing.  Successful performance during OT&E generally indicates the system being tested is effective and suitable for Fleet introduction.  The decision to enter production may be based on this successful determination.  Of critical importance to this review is the understanding of available system performance to meet the CDD/CPD.

Notwithstanding successful completion of the OTRR, the contractor remains responsible for the system design/performance requirements within the terms of the contract.

2.  OTRR Guidelines

a.  Reference (k) further defines the requirements of SECNAVINST 5000.2C (Implementation and Operation of the Defense Acquisition System and the Joint Capabilities Integration and Development System) which establishes the minimum criteria required for certification of readiness to commence OPEVAL and follow-on operational test and evaluation (FOT&E).  The policy and procedures defined in NAVAIRINST 3960.2C shall be followed for the conduct of OTRRs.

b.  Operational requirements defined in the CDD/CPD must match the requirements tested to in the TEMP:

(1) System requirements and the time phasing of them must be traceable from the CDD/CPD to the system specification, and the TEMP; and,

(2) Spiral Development, if incorporated, must be supported by the CDD/CPD, SEP, and other acquisition related documentation.

c.  Commander, Operational Test and Evaluation Force (COMOPTEVFOR) must accredit M&S before utilization during OPEVAL.

d.  Information Assurance must be maintained.  If applicable, a PPP must be in place and/or security certification and accreditation policy must be adhered to.

e.  Interoperability capabilities, including ship interfaces, must be assured.

f.  Definition and classification of severity of software deficiencies should be similar to hardware deficiencies.  Software metrics, which demonstrate maturity/stability of the software, are to be provided to the software SME at least 10 working days prior to the review.

g.  Systems containing high Mean Time Between Failure components pose special problems during reliability determination.  Ensure there is agreement with COMOPTEVFOR that this will not impact resolution of Critical Operational Issues.

3.  OTRR Completion

a.  The OTRR is considered complete when all requirements for Navy Certification of Readiness for OT are complete.  SECNAVINST 5000.2C provides the following list of criteria for certification of readiness that applies to all OT&E for all DON programs.  The PM with the concurrence of the Operational Test Agency (OTA) may tailor criteria listed below in sub items 2 through 20 that, at a minimum, implement DoD criteria required in reference (b) (DoDI 5000.2), enclosure 5, paragraph E5.6, including support of the DoD Information Assurance Certification and Accreditation Process {DoDI 5200.40—DITSCAP}.  The MDA may add criteria as necessary to determine readiness for OT.

(1) The TEMP is current and approved.  Testing prior to MS B shall have an approved T&E Strategy as described in the referenced enclosure, paragraph 5.4;

(2) DT&E results indicate DT objectives and performance thresholds identified in the TEMP have been satisfied or are projected to meet system maturity for the ICD/CDD/CPD, as appropriate;

(3) All significant areas of risk have been identified and corrected or mitigation plans are in place;

(4) DT&E data and reports have been provided to the OTA not less than 30 days prior to the commencement of OT, unless otherwise agreed to by the OTA;

(5) Entrance criteria for OT identified in the TEMP have been satisfied;

(6) System operating, maintenance, and training documents have been provided to the OTA 30 days prior to the OTRR, unless otherwise agreed to by the OTA;

(7) Logistic support, including spares, repair parts, and support/ground support equipment is available as documented.  Discuss any logistics support which will be used during OT&E, but will not be used with the system when fielded (e.g., contractor provided depot level maintenance);

(8) The OT&E manning of the system is adequate in numbers, rates, ratings, and experience level to simulate normal operating conditions;

(9) Training has been completed and is representative of that planned for fleet units;

(10) All resources required to execute OT including instrumentation, simulators, targets, expendables, and funding have been identified and are available;

(11) Models, simulators, and targets have been accredited for intended use;

(12) The system provided for OT&E, including software, is production representative.  Differences between the system provided for test and production configuration shall be addressed at the OTRR;

(13) Threat information (e.g., threat system characteristics and performance, electronic countermeasures, force levels, scenarios, and tactics), to include security classification, required for OT&E is available to satisfy OTA test planning;

(14) The system is safe to use as planned in the concept of employment.  Any restrictions to safe employment are stated.  The environmental, safety, and occupational health (ESOH) program requirements have been satisfied.  The system complies with Navy/Marine Corps environmental, safety, and occupational health/hazardous waste requirements, where applicable.  Environmental, safety, and occupational health/hazardous waste reviews and reports have been provided to COMOPTEVFOR or Director, Marine Corps Operational Test and Evaluation Activity (MCOTEA).  When an energetic is employed in the system, Weapon System Explosives Safety Review Board criteria for conduct of test have been met;

(15) All software is sufficiently mature and stable for fleet introduction.  All software Trouble Reports are documented with appropriate impact analyses.  There are no outstanding Trouble Reports that:

(a) Prevent the accomplishment of an essential capability;

(b) Jeopardize safety, security, or other requirements designated "critical";

(c) Adversely affect the accomplishment of an essential capability and no work-around solution is known; or,

(d) Adversely affect technical, cost, or schedule risks to the project or to life-cycle support of the system, and no work-around solution is known.

(16) For software qualification testing (SQT), a Statement of Functionality that describes the software capability has been provided to COMOPTEVFOR and Chief of Naval Operations (code N091).  For programs to be tested by MCOTEA, the SQT Statement of Functionality has been provided to Director, MCOTEA, and Marine Corps Tactical Systems Support Activity.

(17) For aircraft programs, there are no unresolved NAVAIR deficiencies that affect:

(a) Airworthiness;

(b) Capability to accomplish the primary or secondary mission(s);

(c) Safety of the aircrew/operator/maintainer;

(d) Integrity of the system or an essential subsystem; and,

(e) Effectiveness of the operator or an essential subsystem.

(18) For programs with interoperability requirements (e.g., information exchange requirements in ICD/CDD/CPDs), appropriate authority has approved the Integrated Support Plan and Joint Interoperability Test Command concurs that program interoperability demonstrated in development has progressed sufficiently for the phase of OT to be conducted;

(19) Approval of spectrum certification compliance and spectrum supportability has been obtained; and,

(20) For Information Technology systems, including National Security System, the system has been assigned a Medium Access Control and Confidentiality Level.  System certification accreditation documents, including the System Security Authorization Agreement and the Authority to Operate or Interim Authority to Operate, have been provided to the OTA.

b.  For programs employing software, there are no unresolved Priority 1 or 2 software problem reports , and all Priority 3 problems are documented with appropriate impact analyses; and,

c.  Have all applicable, completed OTRR Assessment checklists and any Lessons Learned been entered into the AIR-4.1 SETR archival database?

System Verification Review / Production Readiness Review

1.  SVR/PRR Purpose – The SVR is a multi-disciplined product and process assessment to ensure that the system under review can proceed into Low Rate Initial Production (LRIP) and Full Rate Production (FRP) within cost (program budget), schedule (program schedule), risk, and other system constraints.  (A Functional Configuration Audit (FCA) may be conducted concurrent with SVR, if desired).  Generally this review is an audit trail from the CDR, and assesses that the system final product, as evidenced in its production configuration, meets the functional requirements as derived from the Capability Production Document (CPD) to the Functional, Allocated, and Product Baselines.  The SVR establishes and verifies final product performance.

The Production Readiness Review (PRR) is an examination of a program to determine if the design is ready for production and the producer has accomplished adequate production planning without incurring unacceptable risks that will breach thresholds of schedule, performance, cost, or other established criteria.  The full, production-configured system is evaluated to determine that it correctly and completely implements all system requirements, and whether the traceability of final system requirements to the final production system is maintained.  At this review the IPT shall also review the readiness of the manufacturing processes, the Quality System, and the production planning, i.e. facilities, tooling and test equipment capacity, personnel development and certification, process documentation, inventory management, supplier management, etc.  A successful review is predicated on the IPT’s determination that the system requirements are fully met in the final production configuration, and that production capability form a satisfactory basis for proceeding into LRIP and FRP.

The PRR(s) should be conducted on the prime contractor and on major subcontractors, as applicable.  The PRR should be conducted in an iterative manner concurrent with other major program reviews, such as SFR, PDR, and CDR, during the SDD acquisition phase.  These periodic production readiness assessments should be conducted during the System Demonstration work effort to identify and mitigate risks as the design progresses, with a final PRR conducted at the completion of the SDD phase.

A follow-on tailored PRR may also be appropriate in the production phase for the prime contractor and major subcontractors for:

a.  Changes from the SDD Phase and during the Production and Deployment Phase of the design, materials and manufacturing processes;

b.  Production start-up after a significant shut-down period;

c.  Production start-up with a new contractor; and,

d.  Relocation of a manufacturing site.

The review may be tailored in accordance with the technical scope and risk of the system.  Under no circumstances should the review be tailored completely out of the development plan.  Tailoring should occur as part of the APMSE or systems engineer coordination of the review agenda with the AIR-4.1 cognizant authority (APEO(E)).

Notwithstanding successful completion of the PRR, the contractor remains responsible for the system design/performance requirements within the terms of the contract.

2.  SVR/PRR Timing - The final PRR is typically conducted at the conclusion of the SDD Phase and at the start of the Production and Deployment Phase to assess the manufacturing and quality risk as the program proceeds into LRIP and FRP.  As stated above, the PRR should be conducted in an iterative manner concurrent with other major program reviews, such as SFR, PDR, CDR and, if applicable, the MS C TRA, during the SDD Phase.  These periodic production readiness assessments should be conducted during the System Demonstration work effort to identify and mitigate risks as the design progresses, with a final PRR conducted at the completion of SDD Phase.

3.  Entry Criteria For SDD Phase Final PRR - The entry criteria discussed below are applicable to the final SDD Phase PRR.  It should be tailored for application to a specific program.  The PM may decide for programmatic reasons to proceed with the PRR prior to completing all of the entry criteria listed below.  This PM decision should be based on a risk assessment, identification of risks and their acceptance.  In this case, a delta PRR may be applicable depending upon the extent of changes resulting from late completion of the entry criteria.  It is desired to have the MS C TRA results prior to PRR in order to verify all CTEs are at prescribed levels outlined in the program approved CTE maturation plan.  Note that the target TRL for CTEs at MS C is TRL 7 with a goal of TRL 8.

a.  A preliminary agenda has been coordinated (nominally) 30 days prior to the PRR;

b.  PRR technical products have been made available to the cognizant PRR participants prior to the review:

(1) Results of the PRRs conducted at the major suppliers;

(2) Transition to Production and/or Manufacturing Plan;

(3) Change control process has been established and the customer has approved the production configuration baseline;

(4) Manufacturing/Producibility and Quality requirements have been addressed during the design/development phase; and,

(5) Current risk assessment

c.  A CDR milestone event has been successfully completed, if applicable;

d.  All CDR action items have been responded to, if applicable;

e.  All CDR completion key issues have been satisfied, if applicable; and,

f.  All system specification qualification test requirements have been successfully completed, if applicable.

4.  SVR/PRR Planning

a.  PRR Chairperson – Planning for a PRR should start with a request for a PRR Chairperson who is independent of the program team, nominally 45 days prior to conduct of the review.  Typically the PMA, assigned IPT leader, or assigned APMSE requests a PRR chairperson be appointed by AIR-4.1.  Prior to this request, the assigned APMSE should have coordinated chairperson requirements with the cognizant (APEO(E)).  Chairperson assignments should be reflective of program scope and risk.  The role of the chairperson includes:

(1) determination of PRR membership;

(2) development of the final review elements;

- oversight of the PRR and RFA process; and,

(4) issuance of the PRR Summary Report.

b.  Production Readiness Review Elements – The APMSE and the assigned Chairperson shall coordinate with the cognizant APEO(E) in the development of a preliminary agenda for the planned review.  The following areas should be addressed in the PRR:

(1) Program Management;

(2) Engineering/Product Design;

(3) Production Engineering and Planning;

(4) Materials and Purchased Parts;

(5) Industrial Resources;

(6) Quality Assurance;

(7) Logistics;

(8) Software Engineering; and,

(9) Technology Readiness consistent with TRA results A more detailed listing the PRR elements can be found in the PRR Assessment checklist

c.  Technical Review Participants:

(1) Production Readiness Review Board (typical composition):

(a) Production Readiness Review Board Chairperson;

(b) PM representatives (Industry and Government);

(c) APMSE;

(d) APML, who should ensure all relevant supportability requirements are addressed;

(e) APMT&E who should ensure all T&E requirements are addressed;

(f) Cost Team (AIR-4.2) representative, if required;

(g) Software(AIR-4.1) Representative;

(h) Counsel, if required;

(i) Contracting Officer, if required; and,

(j) Recorder who is responsible for collating RFAs for submission to the TRB.  The recorder should have the Technical Review Report prepared for distribution by the Chairperson.

2) The SMEs are required to address system concepts, certification, environmental, safety, enabling technologies, etc..  These SMEs represent their NAVAIR competencies in the adjudication of RFAs, to include cost and schedule impacts.  The SMEs should be notified at least 30 days prior to the scheduled review date.

d.  SVR/PRR Location – The facility chosen should be adequate to ensure participation by all cognizant competencies and organizations.  The PRR is typically conducted at a contractor or government provided facility, as mutually agreed upon, or specified in the contract.  Selection of the location should consider minimizing participant travel and associated costs.

5.  Conduct of SVR/PRR Review - All PRR participants are to assess the materials at the review, document concerns by means of RFAs, and submit RFAs to the PRR Recorder.

a.  PRR Review Elements:

(1) Introduction/agenda/administrative:

(a) Purpose of review;

(b) RFA procedures overview;

(c) Risk Assessment procedures overview; and,

(d) Program overview.

(2) Production Plan:

(a) Production schedule;

(b) Cost per unit;

(c) Acceptance testing; and,

(d) Software maintenance and measurement data.

(3)	Follow SVR/PRR (as appropriate) Program Assessment checklist structure

b.  PRR Products:

(1) Production Readiness Review Summary Report, with the following attachments:

(a) List of attendees, to include: name, functional area represented, NAVAIR code, phone number, and email address;

(b) Completed RFA forms;

(c) Meeting minutes; and,

(d) Recommendation to PMA as to the readiness of the program to enter the next phase of production.

(2) Updated Risk Assessment, including risks and mitigation options.  It should specifically address OPEVAL and transition to production risks.

6.  SVR/PRR Completion -

a.  The PRR is considered complete when all draft RFAs are signed off, and an acceptable level of program risk is ascertained.  After the RFAs are closed, the system APMSE shall prepare a letter for the TRB Chairperson formally closing the review.  A PRR data package shall be prepared containing the products of the review and the closure letter, and submitted to the AIR-4.1 SETR archival database.

b.  The PM will approve entering LRIP or FRP based upon acceptable PRR results and manageable program risk.

Physical Configuration Audit

1.  PCA Purpose - The purpose of a PCA is to examine the actual configuration of an item being produced in order to verify that the related design documentation matches the item as specified in the contract.  In addition to the standard practice of assuring product verification, the PCA confirms that the manufacturing processes, quality control system, measurement and test equipment, and training are adequately planned, followed, and controlled.  It is also used to validate many of the supporting processes used by the contractor in the production of the item and to verify other elements of the item that may have been impacted/redesigned after completion of the SVR.  A PCA is normally conducted when the government plans to control the detail design of the item it is acquiring via the Technical Data Package (TDP).  When the government does not plan to exercise such control or purchase the item's TDP (e.g. performance based procurement) the contractor must still conduct an internal PCA in order to define the starting point for controlling the detail design of the item and to establish a product baseline.

2.  PCA Timing - Prior to final acceptance (DD 250) of the deliverable item(s).  The schedule must be compatible with availability of items being reviewed as well as applicable information, personnel, etc.  The supporting CDRL/DD Form 1423 or equivalent must also be scheduled to correspond with planned timing.

3.  PCA Entry Criteria - A new production contract or an ECP may call for the development of a new item and incorporation of the new item into a system via a modification program.  The expected configuration, performance and TDP of the new item will have to be verified by the conduct of a PCA.  It is normal that the first units of an item in the Production and Deployment, and Operations and Support Phases be subjected to a PCA.  Depending on whether the acquisition strategy was based on a detail design or performance design specification could influence whether the PCA is to be conducted by the contractor or government.

The following is entry criteria for the PCA.  It should be tailored for application to a specific program.  The PM may decide for programmatic reasons to proceed with the PCA prior to completing all of the Entry Criteria listed below.  This PM decision should be based on a risk assessment, identification of risks and their acceptance.

a.  A preliminary agenda has been coordinated (nominally) 30 days prior to the PCA;

b.  PCA technical products have been made available to the cognizant PCA participants prior to the review:

(1) Results of the PCAs conducted at the major suppliers;

(2) Manufacturing Plan;

(3) Quality Control plan; and,

(4) Current risk assessment

c.  A PRR milestone event has been successfully completed, if applicable;

d.  All PRR action items have been responded to, if applicable; and,

e.  All PRR completion key issues have been satisfied, if applicable.

4.  PCA Planning - PCA requirements should be included in the SOW tasking.  A specific plan (whether done incrementally or in whole) should be targeted at least 60 days prior to the planned review, and based upon availability of the item and its associated documentation.  The review should be planned well in advance of the production delivery schedule so as to allow sufficient time for correcting any deficiencies found during the PCA that could compromise the contract delivery schedule.  A PCA applicable to software items may be delayed until after integration testing.

a.  PCA Chairperson - The government and contractor PMs or designees co-chair what is often referred to as the PCA Executive Panel.  Chairperson assignments should be reflective of program scope and risk.  The role of the chairperson(s) includes:

(1) Determination of PCA membership;

(2) Development of the final review elements;

(3) Oversight of the PCA and RFA process; and,

(4) Issuance of the PCA Summary Report.

b.  PCA Elements – A representative number of drawings and associated manufacturing instructions for each item shall be reviewed to determine their accuracy in accordance to the final product configuration/design.  Unless otherwise directed by the Government co-chairperson, inspection of the drawings and the associated manufacturing instruction may be accomplished on a valid sampling basis.  The purpose of the PCA is to ensure that the manufacturing instructions (and/or Computer Aided Manufacturing data) accurately reflect all design details contained in the drawings (and/or Computer Aided Design presentations).  Since the hardware is built in accordance with the manufacturing instructions, any discrepancies between the manufacturing instruction and the design details and changes in the drawings will be reflected in the hardware.  The following areas should be addressed in the PCA:

(1) Quality Control System;

(2) Control of Purchases;

(3) Shipping;

(4) Software;

(5) Training;

(6) Measurement and Test Equipment;

(7) Non-Conforming Material; and,

(8) Manufacturing.

A more detailed list of the PCA elements can be found in the PCA Assessment checklist.

c.  PCA Participants - Personnel needs are based on the type and complexity of the item(s) being reviewed.  Experts in engineering design, CM, computer-aided design/manufacturing, production, assembly and acceptance test processes are normally required.  The SMEs should be notified at least 30 days prior to the scheduled review date.  Defense Contract Management Agency plant representatives should also be tasked to review and certify engineering release, configuration control and in house product verification processes.

d.  PCA Location - Unless otherwise specified, the PCA is generally performed at the Prime or Sub Contractor's facility where the item to be reviewed is manufactured or where the test/verification data is located.

5.  Conduct of PCA Review/Review Process - All PCA participants are to assess the materials at the review, document concerns by means of RFAs, and submit RFAs.

a.  PCA Review Elements:

(1) Introduction/agenda/administrative:

(a) Purpose of review;

(b) RFA procedures overview;

(c) Risk Assessment procedures overview; and,

(d) Program overview.

(2) Follow PCA Program Assessment checklist structure.

b.  PCA Products:

(1) PCA Summary Report including approved issue/problem write-ups and assigned actions;

(2) Approved Product Baseline and TDP (formal PCA close out); and,

(3) Updated Risk Assessment, including risks and mitigation options.

6.  PCA Completion

a.  The PCA is considered complete when all draft RFAs are signed off, and an acceptable level of program risk is ascertained;

b.  The design and manufacturing documentation matches the item as specified in the contract;

c.  Results approved by the PCA Executive Panel or Co-Chairs; and,

d.  Have all applicable, completed PCA Assessment checklists and any Lessons Learned been entered into the AIR-4.1 SETR archival database?

In-Service Review

1.  ISR Purpose - The ISR is a multi-disciplined product and process assessment to ensure that the system under review is operationally employed with well-understood and managed risk.  This review is intended to characterize in-service technical and operational health of the deployed system by providing an assessment of risk, readiness, technical status, and trends in a measurable form that will substantiate in-service support budget priorities.  The ISR objectives are met through the consistent application of sound programmatic, SE and logistics management plans, processes, and sub-tier in-service stakeholder reviews, such as System Safety Working Group, Integrated Logistics Support Management Team (ILSMT), etc., and the effective use of available government and commercial data sources.  In-Service safety and readiness issues are grouped by priority to form an integrated picture of in-service health, operational system risk, system readiness, and future in-service support requirements.

Completion of this review should provide:

a.  An overall System Hazard Risk Assessment;

b.  An operational readiness assessment in terms of system problems (hardware, software, and production discrepancies); and,

c.  Status of current system problem (discrepancy) report inflow, resolution rate, and trends and updated metrics as required for prioritizing budget requirements.

Successful completion of this review should provide the PM, the APMSE, the APML, the assigned Fleet Support Team (FST), and other stakeholders with the integrated information they need to establish priorities and to develop execution and out year budget requirements.

2.  ISR Timing – The ISR is typically conducted prior to, and in support of, the initiation of the following fiscal year (FY) Operation and Maintenance, Navy (O&M,N) requirements determination process.  Since the O&M,N requirements Data Calls typically occur in early second quarter timeframe of any given FY, the ISR should be conducted in the months prior.

3.  ISR Entry Criteria

a.  A preliminary agenda has been coordinated (nominally) 30 days prior to the ISR;

b.  ISR technical products for the operational system have been made available to the appropriate ISR participants prior to the review:

(1) Program Risk Assessment:

(a) System Safety Hazard Risk Assessment; and,

(b) Programmatic Risk Assessment.

(2) Current In-Service Hazards:

(a) Safety Assessment Reports status;

(b) Active Mishap Reports;

(c) Active Hazard Reports;

(d) Active safety Engineering Investigations

(e) Active bulletin Technical Directives;

(f) Original Equipment Manufacturer Reports:

1. Service Bulletins; and,

2. Alerts

(g) Federal Aviation Administration:

1. Airworthiness Directives;

2. Rule Changes

(h) Other Service Hazards.

(3) Aging Aircraft Status:

(a) Fatigue Life;

(b) Wiring; and,

(c) Obsolescence and Supportability

(4) Naval Aviation Maintenance Discrepancy Reporting Program (NAMDRP) Status:

(a) Routine Engineering Investigations;

(b) Hazard Material Reports;

(c) Technical Publication Deficiency Reports; and,

(d) Production Quality Deficiency Reports.

(5) CM Status

(a) Technical Directive Status Accounting status; and,

(b) ECP status.

(6) Software Management Status:

(a) Software Trouble Reports status;

(b) FORCEnet compliance; and,

(c) Other

(7) Operational Advisory Group (OAG) Priorities status:

(a) PMA actions relative to Top 10 OAG Priorities.

(8) Operational Requirements Status and Assessment:

(a) Fielded Systems:

1. Number of Systems;

2. Permanent Sites; and,

3. Unclassified Deployed Sites.

(b) New Mission Capability;

(c) Interoperability;

(d) Communication, Navigation Systems;

(e) Logistics Footprint Assessment (Baseline/Annual Review); and,

(f) Other

(9) System Readiness and Maintenance Program Status:

(a) Naval Aviation Readiness Integrated Improvement Program (NAVRIIP):

1. Cross Functional Team 1 (Readiness) Status;

2. Cross Functional Team 2 (Providers) Status;

3. Cross Functional Team 3 (Planning and  Programming) Status; and,

4. Cost Wise Readiness Status.

(b) Reliability Centered Maintenance (RCM) and Integrated Maintenance Program (IMP);

1. Airframe Management Board status;

2. Status Comparison of RCM/IMP plans to baselines; and,

3. Adequacy of staffing to sustain RCM and IMP efforts.

(10) ILSMT Status:

(a) Integrated Logistics Support Element Issues and Priorities; and,

(b) PMA actions relative to ILSMT priorities.

(11) Program O&M,N budget requirements tied to system metrics and prioritized in accordance with NAVAIR requirements determination priority categories, including the delta between requirements and funding:

(a) Current Execution Year;

(b) Pending Execution Year; and,

(c) Future Years Defense Program (FYDP).

(12) Program Aircraft Procurement, Navy budget requirements for fielded aircraft tied to system metrics and prioritized, including the delta between requirements and funding:

(a) Current Execution Year;

(b) Pending Execution Year; and,

(c) FYDP.

(13) Program Staffing Status:

(a) Organization structure/chart supporting program management, technical and logistics requirements;

(b) Key government/contractor interfaces; and,

(c) Planned versus actual resource curve.

(14) Open Action Items from previous reviews.

4.  ISR Planning

a.  In-Service Review Board (ISRB) Chairperson - Planning for an ISR should start with a request for an ISRB Chairperson, nominally 45 days prior to conducting the review.  The APMSE assigned to conduct the review requests an ISRB Chairperson who is independent of the program team be appointed by AIR-4.1.  Prior to this request, the assigned APMSE should have coordinated chairperson requirements with the cognizant APEO(E).  ISRB Chairperson assignments should be reflective of program scope and risk.

b.  In-Service Review Elements – The APMSE, APML, and the assigned ISRB Chairperson shall coordinate with the appropriate APEO(E) in the development of a preliminary agenda for the planned review.  This agenda should be made available to the ISR participant’s 30 days prior to conducting the review.  Review elements are shown below in paragraph 6.a.

c.  ISR Participants:

(1) ISR Board  (required membership):

(a) ISR Board Chairperson;

(b) Government PM;

(c) Industry PM (as applicable);

(d) APMSE;

(e) APML;

(f) FST Leader;

(g) Resource Sponsor (OPNAV); and,

(h) Requirements Officer, as applicable

(2) User representatives;.

(3) SMEs as determined by the APMSE, APML, and ISRB Chairperson;

(4) Counsel, if required;

(5) Contracting Officer, if required; and,

(6) Support personnel as required by the ISR agenda - at a minimum to include the ISR Recorder.

d.  ISR Roles and Responsibilities:

(1) ISRB Chairperson - The role of the ISRB Chairperson includes:

(a) Determination of ISRB membership;

(b) Development of the final review elements; and,

(c) Oversight of the ISR, RFA process, and Issuance of the ISR Summary Report.

(2) APMSE - The role of the APMSE assigned to conduct the review includes:

(a) Ensuring that the engineering activities provide the supporting data and participate in the required review;

(b) Develop, coordinate, and execute, in cooperation with the performing activity, individual review arrangements;

(c) Ensuring that the preparation of requirements performance material is coordinated across IPTs;

(d) Conducting the review for the ISRB; and,

(e) Organizing and supervising the documentation of RFAs in support of the ISRB Chairperson.

(3) APML – The role of the APML includes:

(a) Providing ILSMT and NAVRIIP pertinent data;

(b) Ensure all relevant supportability requirements are addressed;

(c) Ensure logistics activities provide the supporting data; and,

(d) Participate in the required review

(4) ISR Recorder - responsible for collating RFAs for submission to the ISRB.  The recorder should have the ISR Report prepared for distribution by the Chairperson.

5.  ISR Location – The facility chosen should be adequate to ensure complete participation by all appropriate competencies and organizations.  The ISR is typically conducted at a contractor or government provided facility, as mutually agreed upon, or specified in the contract.  Selection of the location should consider minimizing participant travel and associated costs.

6.  Conduct of ISR Review - All ISRB participants are to assess the materials at the review, document concerns by means of RFAs, and submit RFAs to the ISRB Recorder.

a.  ISR Review Elements:

(1) Introduction/agenda/administrative:

(a) Purpose of review;

(b) RFA procedures overview; and,

(c) Risk Assessment procedures overview.

(2) Program Overview:

(a) Production Overview, Status;

(b) Fielded Status;

(c) Modification Program Status;

(d) Engineering and Logistics Overview;

(e) Program Staffing Status; and,

(f) Budget Overview

(3) Program Risk Assessment:

(a) Operational System Hazard Risk Index status;

(b) Risk items and mitigation options; and,

(c) Cost and schedule impacts of risk and/or mitigation options.

(4) In-Service Management Metrics:

(a)Safety Program status;

(b) Aging Aircraft status;

(c) NAMDRP Program status;

(d) CM Program status;

(e) Software Program status;

(f) OAG status;

(g) Readiness and Maintenance status;

(h) ILSMT status;

(i) Funding status; and,

(j) ISR Action Items status.

(5) Process Review (Provide Status of following to ensure plans and processes are current)

(a) Program Management Plan;

(b) Operational Requirements Management Plan;

(c) System Safety Management Plan;

(d) RMP;

(e) CM Plan;

(f) NAVRIIP; and,

(g) RCM and IMP Plans.

b.  ISR Products:

(1) ISR Summary Report, with the following attachments:

(a) List of attendees, to include: name, functional area represented, NAVAIR code, phone number, and email address;

(b) Completed RFA forms;

(c) Meeting minutes;

(d) Assessment of the technical health (system operational risk and system readiness) of the program to the PMA; and,

(e) Assessment of program O&M,N budget requirements tied to system metrics and prioritized in accordance with NAVAIR requirements determination priority categories, including the delta between requirements and funding.

(2) Updated Operational System Hazard Risk Assessment, including risks and mitigation options; and,

(3) Summary report due within 20 days of review.

7.  ISR Completion - The ISR is considered complete when all draft RFAs are signed off, and program operational risk, and relation of this risk to O&M,N budgets is ascertained.  After the RFAs are closed, the system APMSE shall prepare a letter for the TRB Chairperson formally closing the review.  An ISR data package shall be prepared containing the products of the review and the closure letter, and submitted to the AIR-4.1 SETR archival database.